## JAN 2020
MASTER NAME : TAUFIK FAISAL
PHONE NO : 081231667177
C/E NAME : RUNDI
PHONE NO : 082135105585
EMAIL : asd-rhayden@ekanuri.com
VESSEL NAME | TB. ASD. ENC RHAYDEN
VESSEL STATUS | OPERATION
CLIENT/CHARTERER | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
VESSEL LOCATION | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
ON HIRE DATE | 31-01-2019
CONTRACT DURATION | 1460 DAYS
END CONTRACT DATE
LAST EXTERNAL INSPECTION OVID/CMID | 29-08-2019 (Mr Dave Whiting & Pak Andi Basri)
LAST MANAGEMENT VISIT | 28-12-2019 (Pak Yosef/PEIP)
LAST TECHNICAL SUPERINTENDENT VISIT | 28-11-2019 (Bas Ricco / SISM)
LAST MASTER ASSESMENT | 2019-04-27
LAST JOB VERIFICATION
LAST BPI SUPPLIED ONBOARD | BPI 01/27.12.2019 / Dowload Internet
LAST NTM SUPPLIED ONBOARD | N/A
CERTIFICATE EXPIRING IN 60 DAYS
NAME OF CERTIFICATE | EXPIRY DATE
SPOGK | 10 JANUARY 2020
MEDICAL CHEST CONTROL POLICY | 10 JANUARY 2020 (progress)
CLASS CERTIFICATE
NEXT ANNUAL SURVEY WINDOW | 09-Oct-2019 ( ANNUAL SURVEY 2 )
NEXT DOCKING WINDOW | 2021-04-29
INTERMEDIATE WINDOW | 2020-01-26
SPECIAL SURVEY WINDOW | 2022-07-26
DEFECT REPORT
DEFECT | STATUS
1. ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN RPM 750 | OPEN
2. PANEL MSB AUX ENGINE, KW METER AE 1 & 2 NOT FUCTIONING PROPERLY | OPEN
3. PARAMETER FW COOLING ME PORT SIDE ON BRIDGE NOT FUNCTIONING PROPERLY | OPEN
4. SW VALVE SUCTION COOLING PUMP ME PORTSIDE | OPEN
5. SW VALVE COOLING PUMP AE 1 | OPEN
6. COMPRESSOR QUINCY | OPEN
FUEL CONSUMPTION OVER
OVER QUANTITY | FUEL REPORT DATE
NIL | NIL
CREW ROTATION IN 30 DAYS
CREW SIGN OFF | TENTATIVE DATE
PURWANDOYO / CHIEF OFFICER | SISM 27.11.2019
DIAN APRIZAL / CHIEF ENGINEER | SISM 27.11.2019
AWALUDIN / AB | SISM 27.11.2019
CREW RELIEVER | TENTATIVE DATE SIGN ON
TAUFIK FAISAL / MASTER | SISM 27.11.2019
RUNDI / PROMOTE CHIEF ENGINEER | SISM 27.11.2019
YONATHAN RAMBA / PROMOTE 2ND ENGINEER | SISM 27.11.2019
CREW EXPIRED CERTIFICATE IN 90 DAYS
NAME OF CERTIFICATE /HOLDER | EXPIRY DATE
SAMGAR ARTHUR (2O) / SAT | 07 APRIL 2019 | Note :
SAMGAR ARTHUR (2O) / SDSD | 26 NOVEMBER 2019 | Mohon dikomunikasikn dgn MPD perihal kapan wktu pelaksanaan utk memperpanjang cert tsbt
FERRY FIRMANTO (AB) / SAT | 11 AGUSTUS 2019
FERRY FIRMANTO (AB) / SDSD | 28 NOVEMBER 2019
BAYU TRI PRABOWO (OILER) / SAT | 04 NOVEMBER 2019
BAYU TRI PRABOWO (OILER) / SDSD | 16 AGUSTUS 2019
INSPECTION OUTSTANDING
NC/OBSERVATION ITEMS | STATUS
NIL
DECK REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
009/DD/MEI/2018 | STORES EQUIPMENT | 2018-02-05 | 9 | CAMERA DIGITAL | 1 | UNIT | 2018-05-05 | URGENT |  | OPEN (akan dibelikan dgn menggunakan kas kapal)
149/DD/OCT/2019 | DECK EQUIPMENT | 21/10/2019 | 56 | MOORING ROPE 12" | 1 | ROLL |  | URGENT |  | 0PEN
153/DD/DEC/2019 | PUBLIKASI NAUTICA | 2019-02-12 | 57 | PUBLIKASI NAUTICA | 5 | PCS |  | URGENT |  | 0PEN
Outstanding Requisition
ENGINE REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
06/ED/MARCH/2018 | AIR COMP | 2018-03-21 | 6 | YANMAR |  |  |  | NORMAL |  | OPEN (penawaran harga baru masuk 1 vendor)
07/ED/MARCH/2018 | EM'CY PORTABLE | 2018-03-21 | 7 |  |  |  |  | NORMAL |  | CANCEL
08/ED/MARCH/2018 | RUNNING STORE | 2018-03-22 | 8 |  |  |  |  | NORMAL |  | OPEN
24/ED/JUNI/2018 | SPARE PART CUMMINS | 2018-06-05 | 28 | CUMMINS B33 |  |  |  | URGENT |  | OPEN (kita akan hold dulu karena baru dilakukan GO, akan dibudgetkan thn depan)
011/ED/JUNI/2018 | CRANES | 2018-06-26 | 36 | PM 10021 |  |  |  | URGENT |  | OPEN
012/ED/JUNI/2018 | CRANES | 2018-06-26 | 37 | PM 10021 |  |  |  | URGENT |  | OPEN
013/ED/JUNI/2018 | AUXILIARY ENGINE | 2018-06-26 | 38 | PERKINS 6TWGM |  |  |  | URGENT |  | OPEN
015/ED/JULI/2018 | SPARE PART CRANES | 2018-07-10 | 40 | PM 10021 |  |  |  | URGENT |  | OPEN
016/ED/JULI/2018 | RUNNING STORE | 2018-07-10 | 41 |  |  |  |  | URGENT |  | OPEN
023/ED/JULI/2O18 | WIRE CRANE | 2018-08-01 | 46 | PM 10021 |  |  |  | NORMAL |  | OPEN (akan kita budgetkan di tahun depan) | Reminder req (akhir june 2019 sdh on board)
028/ED/JULI/2018 | SPECIAL TOOL REXPELLER | 28-JULI-2018 | 47 | KAWASAKI KST-165ZF/A |  |  |  | NORMAL |  | OPEN (kita hold dulu utk req tool nya)
029/ED/JULI/2018 | REXPELLER HIDRAULIC PUMP | 28-JULI-2018 | 48 | KAWASAKI KST-165ZF/A |  |  |  | NORMAL |  | OPEN (kita hold dulu utk suppy part2nya, karena seal sealnya sdh ada diatas kapal)
45/ED/SEPTEMBER/2018 | SEAL POMPA REXPELLER | 2018-09-03 | 58 | KAWASAKI KST-165ZF/A |  |  |  | URGENT |  | OPEN (akan dicheck kembali receive nya, karena sdh dibelikan)
47/ED/SEPTEMBER/2018 | FILTER OWS | 2018-09-05 | 60 |  |  |  |  | URGENT |  | OPEN (filter2 tsb sangat sulit dicari yg sama persis, harus dibawa turun dan dicocokkan di supplayer)
054/ED/OKTOBER/2018 | RUNNING STORE | 2018-10-01 | 65 |  |  |  |  | URGENT |  | OPEN
055/ED/OKTOBER/2018 | RUNNING STORE | 2- OCT-2018 | 66 | [6 empty] | OPEN
059/ED/OCTOBER/2018 | RUNNING STORE | 8-OCT-2018 | 68 | [6 empty] | OPEN
060/ED/OCTOBER/2018 | HYDROLICK OIL | 10-OCT-2018 | 69 | YANMAR |  |  |  | URGENT |  | OPEN (ini req untuk lub oil governor SAE 20 -40)
065/ED/OCTOBER/2018 | WATER TREATMANT | 23-OCT-2018 | 71 | AE |  |  |  | URGENT |  | OPEN
073/ED/NOVEMBER/2018 | MAIN ENGINE | 2018-11-04 | 76 | YANMAR 8N21A-EN |  |  |  | URGENT |  | OPEN
078/ED/NOEMBER/2018 | MAIN ENGINE | 2018-11-12 | 80 | YANMAR 8N21A-EN |  |  |  | URGENT |  | OPEN
086/ED/DESEMBER/2018 | HARBOUR GENERATOR | 2018-12-08 | 84 | CUMMINS B33 |  |  |  | NORMAL |  | OPEN
100/ED/JANUARY/2019 | HARBOUR GENERATOR | 2019-01-09 | 89 | CUMMINS B33 |  |  |  | URGENT |  | OPEN (kita akan hold dulu karena baru dilakukan GO, akan dibudgetkan thn depan)
106/ED/JANUARY/2019 | MAIN ENGINE | 2019-01-26 | 91 | PISTON |  |  |  | URGENT |  | OPEN
108/ED/JANUARY/2019 | MAIN AIR COMPRESSOR | 2019-01-02 | 92 | YANMAR SC5N-TP |  |  |  | URGENT |  | OPEN (penawaran harga baru masuk 1 vendor)
110/ED/FEBRUARY/2019 | AUXILIARY ENGINE | 2019-02-11 | 93 | SENSOR |  |  |  | NORMAL |  | OPEN
111/ED/FEBRUARY/2019 | RUNNING STORE | 2019-01-11 | 94 | VALVE |  |  |  | NORMAL |  | OPEN
125/ED/MARCH/2019 | COMPRESSOR YANMAR 1 UNIT | 22-Marc-2019 | 96 | YANMAR SC5N-TP | 1 | Unit |  | URGENT |  | OPEN (penawaran harga baru masuk 1 vendor)
133/ED/MAY/2019 | FUEL INJACTION PUMP | 17-May-2019 | 100 | YANMAR 8N21A |  | PCS |  | NORMAL |  | OPEN
134/ED/MAY/2019 | DINAMO STARTER ASSY | 18-MAY-2019 | 101 | YANMAR 8N21A | 1 | SET |  | NORMAL |  | OPEN
135/ED/MAY/2019 | PARA METER FW AT BRIDGE | 20-MAY-2019 | 102 | YANMAR 8N21A | 2 | PCS |  | NORMAL |  | OPEN
136/ED/JUNE/2019 | AVR MX341 | 11-JUNE-2019 | 102 | PERKINS 6TWGM | 2 | PCS |  | NORMAL |  | OPEN
137/ED/JUNE/2019 | DROP KIT 150 KVA | 11-JUNE-2019 | 103 | PERKINS 6TWGM | 2 | PCS |  | NORMAL |  | OPEN
138/ED/JUNE/2019 | SEA WATER COOLING PUMP ASSY | 29-JUNE-2019 | 104 | YANMAR 8N21A | 1 | SET |  | NORMAL |  | OPEN
139/ED/JULY/2019 | AE RAW WATER PUMP | 04-JULY-2019 | 105 | PERKINS 6TWGM | 1 | SET |  | NORMAL |  | OPEN
140/ED/JULY/2019 | SW VALVE ME & AE | 08-JULY-2019 | 106 | YANMAR 8N21A | 2 | PCS |  | URGENT |  | OPEN
141/ED/AUGUST/2019 | LO | 17-AUGT-2019 | 107 | SAE 40 | 5 | DRUM |  | NORMAL |  | OPEN
147/ED/OCT/2019 | SEWAGE EQUIPMENT | 2019-10-10 | 110 | SEWAGE TREATMENT SWITCH |  |  |  | URGENT |  | OPEN
148/ED/OCT/2019 | SAFETY EQUIPMENT | 2019-10-10 | 111 | PORTABLE PUMP/ALKON | 1 | UNIT |  | URGENT |  | OPEN
150/ED/OCT/2019 | ENGINE EQUIPMENT | 2019-10-30 | 112 | FILTER RACOR |  |  |  | URGENT |  | OPEN
155/ED/DEC/2019 | SAFETY EQUIPMENT | 20-Dec-2019 | 113 | CCTV FIFI | 1 | UNIT |  | URGENT |  | OPEN
156/ED/DEC/2019 | ENGINE EQUIPMENT | 24-DEC-2019 | 114 | Bottle sample | 30 | Pcs |  | NORMAL |  | OPEN
157/ED/DEC/2019 | ENGINE EQUIPMENT | 25-DEC-2019 | 115 | Majun | 50 | Kg |  | NORMAL |  | OPEN
158/ED/DEC/2019 | ENGINE EQUIPMENT | 30-DEC-2019 | 116 | BATTERY SPARE FIFI | 2 | Pcs |  | URGENT |  | OPEN
Outstanding Defect
Defect description | Date reported Based on statement Of fact | Status Open / Closed date | Action Taken | Target Complete
ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 2019-05-17 | OPEN | O/H
ME PORT SIDE CYL NO. 7, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 15-July-2019 | OPEN | O/H
Note on B37: SISM RICCO: Docking list dibuat oleh TS dan target selesai tanggal 30 Juli 2019, dari PEIP akan menyiapkan kapal pengganti, renewal notifikasi lebih dr 15 thun
Note on B42: SISM RICCO: akan kita rencanakan di waktu perawtatan dibulan january/feb 2020
Note on B43: SISM RICCO: masih meunggu konfirmasi dr kontraktor mas slamet (peip kintraktor)
Note on B44: SISM RICCO: kondisi saat ini sdh baik
Note on B45: SISM RICCO: diupyakn dilakukan saat docking
Note on B47: SISM RICCO: est tiba di muntok tgl 3 jan 2020

## FEB 2020
MASTER NAME : TAUFIK FAISAL
PHONE NO : 081231667177
C/E NAME : DIAN APRIZAL
PHONE NO : 081326714831
EMAIL : asd-rhayden@ekanuri.com
VESSEL NAME | TB. ASD. ENC RHAYDEN
VESSEL STATUS | OPERATION
CLIENT/CHARTERER | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
VESSEL LOCATION | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
ON HIRE DATE | 31-01-2019
CONTRACT DURATION | 1460 DAYS
END CONTRACT DATE
LAST EXTERNAL INSPECTION OVID/CMID | 29-08-2019 (Mr Dave Whiting & Pak Andi Basri)
LAST MANAGEMENT VISIT | 28-12-2019 (Pak Yosef/PEIP)
LAST TECHNICAL SUPERINTENDENT VISIT | 28-11-2019 (Bas Ricco / SISM)
LAST MASTER ASSESMENT | 2019-04-27
LAST JOB VERIFICATION
LAST BPI SUPPLIED ONBOARD | BPI 06/31.01.2020 / Dowload Internet
LAST NTM SUPPLIED ONBOARD | N/A
CERTIFICATE EXPIRING IN 60 DAYS
NAME OF CERTIFICATE | EXPIRY DATE
SPOGK | 10 FEBRUARY 2020
CARGO SHIP SAFETY CONTRUCTION CERTF | 10 FEBRUARY 2020
CARGO SHIP SAFETY RADIO CERTF | 10 FEBRUARY 2020
CARGO SHIP SAFETY EQUIPMENT CERTF | 10 FEBRUARY 2020
RENCANA POLA TRAYEK | 28 MARCH 2020
CLASS CERTIFICATE
NEXT ANNUAL SURVEY WINDOW | 09-Oct-2019 ( ANNUAL SURVEY 2 )
NEXT DOCKING WINDOW | 2021-04-29
INTERMEDIATE WINDOW | 2020-01-26
SPECIAL SURVEY WINDOW | 2022-07-26
DEFECT REPORT
DEFECT | STATUS
1. ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN RPM 750 | OPEN
2. PANEL MSB AUX ENGINE, KW METER AE 1 & 2 NOT FUCTIONING PROPERLY | OPEN
3. PARAMETER FW COOLING ME PORT SIDE ON BRIDGE NOT FUNCTIONING PROPERLY | OPEN
4. SW VALVE SUCTION COOLING PUMP ME PORTSIDE | OPEN
5. SW VALVE COOLING PUMP AE 1 | OPEN
6. COMPRESSOR QUINCY | CLOSED
7. RUBBER BOAT | OPEN
8. CONTACTOR SWITCH COMPRESSOR | OPEN
FUEL CONSUMPTION OVER
OVER QUANTITY | FUEL REPORT DATE
NIL | NIL
CREW ROTATION IN 30 DAYS
CREW SIGN OFF | TENTATIVE DATE
BAHKTIAR / CHIEF OFFICER | SISM 08.01.2020
RUNDI / CHIEF ENGINEER | SISM 08.01.2020
ISHAK SUHERMAN / AB | SISM 08.01.2020
HASRUL GUNAWAN / OILER | SISM 08.01.2020
CREW RELIEVER | TENTATIVE DATE SIGN ON
PURWANDOYO / CHIEF OFFICER | SISM 08.01.2020
DIAN APRIZAL / CHIEF ENGINEER | SISM 08.01.2020
AWALUDIN / AB | SISM 08.01.2020
BAYU TRI PRABOWO / OILER | SISM 08.01.2020
CREW EXPIRED CERTIFICATE IN 90 DAYS
NAME OF CERTIFICATE /HOLDER | EXPIRY DATE
Note :
INSPECTION OUTSTANDING
NC/OBSERVATION ITEMS | STATUS
NIL
DECK REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
009/DD/MEI/2018 | STORES EQUIPMENT | 2018-02-05 | 9 | CAMERA DIGITAL | 1 | UNIT | 2018-05-05 | URGENT |  | OPEN (akan dibelikan dgn menggunakan kas kapal)
149/DD/OCT/2019 | DECK EQUIPMENT | 21/10/2019 | 56 | MOORING ROPE 12" | 1 | ROLL |  | URGENT |  | 0PEN
159/DD/JAN/2020 | DECK EQUIPMENT | 2020-02-01 | 173 | RUBBER BOAT | 1 | UNIT |  | URGENT |  | OPEN
Outstanding Requisition
ENGINE REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
06/ED/MARCH/2018 | AIR COMP | 2018-03-21 | 6 | YANMAR |  |  |  | NORMAL |  | OPEN (penawaran harga baru masuk 1 vendor)
07/ED/MARCH/2018 | EM'CY PORTABLE | 2018-03-21 | 7 |  |  |  |  | NORMAL |  | CANCEL
08/ED/MARCH/2018 | RUNNING STORE | 2018-03-22 | 8 |  |  |  |  | NORMAL |  | OPEN
24/ED/JUNI/2018 | SPARE PART CUMMINS | 2018-06-05 | 28 | CUMMINS B33 |  |  |  | URGENT |  | OPEN (kita akan hold dulu karena baru dilakukan GO, akan dibudgetkan thn depan)
011/ED/JUNI/2018 | CRANES | 2018-06-26 | 36 | PM 10021 |  |  |  | URGENT |  | OPEN
012/ED/JUNI/2018 | CRANES | 2018-06-26 | 37 | PM 10021 |  |  |  | URGENT |  | OPEN
013/ED/JUNI/2018 | AUXILIARY ENGINE | 2018-06-26 | 38 | PERKINS 6TWGM |  |  |  | URGENT |  | OPEN
015/ED/JULI/2018 | SPARE PART CRANES | 2018-07-10 | 40 | PM 10021 |  |  |  | URGENT |  | OPEN
016/ED/JULI/2018 | RUNNING STORE | 2018-07-10 | 41 |  |  |  |  | URGENT |  | OPEN
023/ED/JULI/2O18 | WIRE CRANE | 2018-08-01 | 46 | PM 10021 |  |  |  | NORMAL |  | OPEN (akan kita budgetkan di tahun depan) | Reminder req (akhir june 2019 sdh on board)
028/ED/JULI/2018 | SPECIAL TOOL REXPELLER | 28-JULI-2018 | 47 | KAWASAKI KST-165ZF/A |  |  |  | NORMAL |  | OPEN (kita hold dulu utk req tool nya)
029/ED/JULI/2018 | REXPELLER HIDRAULIC PUMP | 28-JULI-2018 | 48 | KAWASAKI KST-165ZF/A |  |  |  | NORMAL |  | OPEN (kita hold dulu utk suppy part2nya, karena seal sealnya sdh ada diatas kapal)
45/ED/SEPTEMBER/2018 | SEAL POMPA REXPELLER | 2018-09-03 | 58 | KAWASAKI KST-165ZF/A |  |  |  | URGENT |  | OPEN (akan dicheck kembali receive nya, karena sdh dibelikan)
47/ED/SEPTEMBER/2018 | FILTER OWS | 2018-09-05 | 60 |  |  |  |  | URGENT |  | OPEN (filter2 tsb sangat sulit dicari yg sama persis, harus dibawa turun dan dicocokkan di supplayer)
054/ED/OKTOBER/2018 | RUNNING STORE | 2018-10-01 | 65 |  |  |  |  | URGENT |  | OPEN
055/ED/OKTOBER/2018 | RUNNING STORE | 2- OCT-2018 | 66 | [6 empty] | OPEN
059/ED/OCTOBER/2018 | RUNNING STORE | 8-OCT-2018 | 68 | [6 empty] | OPEN
060/ED/OCTOBER/2018 | HYDROLICK OIL | 10-OCT-2018 | 69 | YANMAR |  |  |  | URGENT |  | OPEN (ini req untuk lub oil governor SAE 20 -40)
065/ED/OCTOBER/2018 | WATER TREATMANT | 23-OCT-2018 | 71 | AE |  |  |  | URGENT |  | OPEN
073/ED/NOVEMBER/2018 | MAIN ENGINE | 2018-11-04 | 76 | YANMAR 8N21A-EN |  |  |  | URGENT |  | OPEN
078/ED/NOEMBER/2018 | MAIN ENGINE | 2018-11-12 | 80 | YANMAR 8N21A-EN |  |  |  | URGENT |  | OPEN
086/ED/DESEMBER/2018 | HARBOUR GENERATOR | 2018-12-08 | 84 | CUMMINS B33 |  |  |  | NORMAL |  | OPEN
100/ED/JANUARY/2019 | HARBOUR GENERATOR | 2019-01-09 | 89 | CUMMINS B33 |  |  |  | URGENT |  | OPEN (kita akan hold dulu karena baru dilakukan GO, akan dibudgetkan thn depan)
106/ED/JANUARY/2019 | MAIN ENGINE | 2019-01-26 | 91 | PISTON |  |  |  | URGENT |  | OPEN
108/ED/JANUARY/2019 | MAIN AIR COMPRESSOR | 2019-01-02 | 92 | YANMAR SC5N-TP |  |  |  | URGENT |  | OPEN (penawaran harga baru masuk 1 vendor)
110/ED/FEBRUARY/2019 | AUXILIARY ENGINE | 2019-02-11 | 93 | SENSOR |  |  |  | NORMAL |  | OPEN
111/ED/FEBRUARY/2019 | RUNNING STORE | 2019-01-11 | 94 | VALVE |  |  |  | NORMAL |  | OPEN
125/ED/MARCH/2019 | COMPRESSOR YANMAR 1 UNIT | 22-Marc-2019 | 96 | YANMAR SC5N-TP | 1 | Unit |  | URGENT |  | OPEN (penawaran harga baru masuk 1 vendor)
133/ED/MAY/2019 | FUEL INJACTION PUMP | 17-May-2019 | 100 | YANMAR 8N21A |  | PCS |  | NORMAL |  | OPEN
134/ED/MAY/2019 | DINAMO STARTER ASSY | 18-MAY-2019 | 101 | YANMAR 8N21A | 1 | SET |  | NORMAL |  | OPEN
135/ED/MAY/2019 | PARA METER FW AT BRIDGE | 20-MAY-2019 | 102 | YANMAR 8N21A | 2 | PCS |  | NORMAL |  | OPEN
136/ED/JUNE/2019 | AVR MX341 | 11-JUNE-2019 | 102 | PERKINS 6TWGM | 2 | PCS |  | NORMAL |  | OPEN
137/ED/JUNE/2019 | DROP KIT 150 KVA | 11-JUNE-2019 | 103 | PERKINS 6TWGM | 2 | PCS |  | NORMAL |  | OPEN
138/ED/JUNE/2019 | SEA WATER COOLING PUMP ASSY | 29-JUNE-2019 | 104 | YANMAR 8N21A | 1 | SET |  | NORMAL |  | OPEN
139/ED/JULY/2019 | AE RAW WATER PUMP | 04-JULY-2019 | 105 | PERKINS 6TWGM | 1 | SET |  | NORMAL |  | OPEN
140/ED/JULY/2019 | SW VALVE ME & AE | 08-JULY-2019 | 106 | YANMAR 8N21A | 2 | PCS |  | URGENT |  | OPEN
141/ED/AUGUST/2019 | LO | 17-AUGT-2019 | 107 | SAE 40 | 5 | DRUM |  | NORMAL |  | OPEN
147/ED/OCT/2019 | SEWAGE EQUIPMENT | 2019-10-10 | 110 | SEWAGE TREATMENT SWITCH |  |  |  | URGENT |  | OPEN
148/ED/OCT/2019 | SAFETY EQUIPMENT | 2019-10-10 | 111 | PORTABLE PUMP/ALKON | 1 | UNIT |  | URGENT |  | OPEN
150/ED/OCT/2019 | ENGINE EQUIPMENT | 2019-10-30 | 112 | FILTER RACOR |  |  |  | URGENT |  | OPEN
156/ED/DEC/2019 | ENGINE EQUIPMENT | 24-DEC-2019 | 114 | Bottle sample | 30 | Pcs |  | NORMAL |  | OPEN
157/ED/DEC/2019 | ENGINE EQUIPMENT | 25-DEC-2019 | 115 | Majun | 50 | Kg |  | NORMAL |  | OPEN
158/ED/DEC/2019 | ENGINE EQUIPMENT | 30-DEC-2019 | 116 | BATTERY SPARE FIFI | 2 | Pcs |  | URGENT |  | OPEN
Outstanding Defect
Defect description | Date reported Based on statement Of fact | Status Open / Closed date | Action Taken | Target Complete
ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 2019-05-17 | OPEN | O/H
ME PORT SIDE CYL NO. 7, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 15-July-2019 | OPEN | O/H
Note on B37: SISM RICCO: Docking list dibuat oleh TS dan target selesai tanggal 30 Juli 2019, dari PEIP akan menyiapkan kapal pengganti, renewal notifikasi lebih dr 15 thun
Note on B42: SISM RICCO: akan kita rencanakan di waktu perawtatan dibulan january/feb 2020
Note on B43: SISM RICCO: masih meunggu konfirmasi dr kontraktor mas slamet (peip kintraktor)
Note on B44: SISM RICCO: kondisi saat ini sdh baik
Note on B45: SISM RICCO: diupyakn dilakukan saat docking
Note on B47: SISM RICCO: est tiba di muntok tgl 3 jan 2020

## MAR 2020
MASTER NAME : TAUFIK FAISAL
PHONE NO : 081231667177
C/E NAME : DIAN APRIZAL
PHONE NO : 081326714831
EMAIL : asd-rhayden@ekanuri.com
VESSEL NAME | TB. ASD. ENC RHAYDEN
VESSEL STATUS | OPERATION
CLIENT/CHARTERER | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
VESSEL LOCATION | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
ON HIRE DATE | 31-01-2019
CONTRACT DURATION | 1460 DAYS
END CONTRACT DATE
LAST EXTERNAL INSPECTION OVID/CMID | 29-08-2019 (Mr Dave Whiting & Pak Andi Basri)
LAST MANAGEMENT VISIT | 28-12-2019 (Pak Yosef/PEIP)
LAST TECHNICAL SUPERINTENDENT VISIT | 28-11-2019 (Bas Ricco / SISM)
LAST MASTER ASSESMENT | 2019-04-27
LAST JOB VERIFICATION
LAST BPI SUPPLIED ONBOARD | BPI 10/28.02.2020 / Dowload Internet
LAST NTM SUPPLIED ONBOARD | N/A
CERTIFICATE EXPIRING IN 60 DAYS
NAME OF CERTIFICATE | EXPIRY DATE
SPOGK | 13 MARET 2020
RENCANA POLA TRAYEK | 28 MARET 2020
CLASS CERTIFICATE
NEXT ANNUAL SURVEY WINDOW | 09-Oct-2019 ( ANNUAL SURVEY 2 )
NEXT DOCKING WINDOW | 2021-04-29
INTERMEDIATE WINDOW | 2020-01-26
SPECIAL SURVEY WINDOW | 2022-07-26
DEFECT REPORT
DEFECT | STATUS
1. ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN RPM 750 | OPEN
2. PANEL MSB AUX ENGINE, KW METER AE 1 & 2 NOT FUCTIONING PROPERLY | OPEN
3. PARAMETER FW COOLING ME PORT SIDE ON BRIDGE NOT FUNCTIONING PROPERLY | OPEN
4. SW VALVE SUCTION COOLING PUMP ME PORTSIDE | OPEN
5. SW VALVE COOLING PUMP AE 1 | OPEN
6. COMPRESSOR QUINCY | CLOSED
7. RUBBER BOAT | OPEN
8. CONTACTOR SWITCH COMPRESSOR | CLOSED
FUEL CONSUMPTION OVER
OVER QUANTITY | FUEL REPORT DATE
NIL | NIL
CREW ROTATION IN 30 DAYS
CREW SIGN OFF | TENTATIVE DATE
CREW RELIEVER | TENTATIVE DATE SIGN ON
CREW EXPIRED CERTIFICATE IN 90 DAYS
NAME OF CERTIFICATE /HOLDER | EXPIRY DATE
Note :
SEAMAN BOOK / SAMGAR ARTHUR (2/O) | 11 APRIL 2020 | SUDAH KAMI SAMPAIKAN KEPADA YANG BERSANGKUTAN
BOCT / SAMGAR ARTHUR (2/O) | 11 MARET 2020
SCRB / YONATHAN RAMBA (2/E) | 04 MARET 2020
AFF / YONATHAN RAMBA (2/E) | 04 MARET 2020
ERM / MISBAK (3/E) | 12 JUNE 2020
AFF / MISBAK (3/E) | 22 JANUARY 2020
INSPECTION OUTSTANDING
NC/OBSERVATION ITEMS | STATUS
NIL
DECK REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
009/DD/MEI/2018 | STORES EQUIPMENT | 2018-02-05 | 9 | CAMERA DIGITAL | 1 | UNIT | 2018-05-05 | URGENT |  | OPEN (akan dibelikan dgn menggunakan kas kapal)
149/DD/OCT/2019 | DECK EQUIPMENT | 21/10/2019 | 56 | MOORING ROPE 12" | 1 | ROLL |  | URGENT |  | 0PEN
159/DD/JAN/2020 | DECK EQUIPMENT | 2020-02-01 | 173 | RUBBER BOAT | 1 | UNIT |  | URGENT |  | OPEN
Outstanding Requisition
ENGINE REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
06/ED/MARCH/2018 | AIR COMP | 2018-03-21 | 6 | YANMAR |  |  |  | NORMAL |  | OPEN (penawaran harga baru masuk 1 vendor)
07/ED/MARCH/2018 | EM'CY PORTABLE | 2018-03-21 | 7 |  |  |  |  | NORMAL |  | CANCEL
08/ED/MARCH/2018 | RUNNING STORE | 2018-03-22 | 8 |  |  |  |  | NORMAL |  | OPEN
24/ED/JUNI/2018 | SPARE PART CUMMINS | 2018-06-05 | 28 | CUMMINS B33 |  |  |  | URGENT |  | OPEN (kita akan hold dulu karena baru dilakukan GO, akan dibudgetkan thn depan)
011/ED/JUNI/2018 | CRANES | 2018-06-26 | 36 | PM 10021 |  |  |  | URGENT |  | OPEN
012/ED/JUNI/2018 | CRANES | 2018-06-26 | 37 | PM 10021 |  |  |  | URGENT |  | OPEN
013/ED/JUNI/2018 | AUXILIARY ENGINE | 2018-06-26 | 38 | PERKINS 6TWGM |  |  |  | URGENT |  | OPEN
015/ED/JULI/2018 | SPARE PART CRANES | 2018-07-10 | 40 | PM 10021 |  |  |  | URGENT |  | OPEN
016/ED/JULI/2018 | RUNNING STORE | 2018-07-10 | 41 |  |  |  |  | URGENT |  | OPEN
023/ED/JULI/2O18 | WIRE CRANE | 2018-08-01 | 46 | PM 10021 |  |  |  | NORMAL |  | OPEN (akan kita budgetkan di tahun depan) | Reminder req (akhir june 2019 sdh on board)
028/ED/JULI/2018 | SPECIAL TOOL REXPELLER | 28-JULI-2018 | 47 | KAWASAKI KST-165ZF/A |  |  |  | NORMAL |  | OPEN (kita hold dulu utk req tool nya)
029/ED/JULI/2018 | REXPELLER HIDRAULIC PUMP | 28-JULI-2018 | 48 | KAWASAKI KST-165ZF/A |  |  |  | NORMAL |  | OPEN (kita hold dulu utk suppy part2nya, karena seal sealnya sdh ada diatas kapal)
45/ED/SEPTEMBER/2018 | SEAL POMPA REXPELLER | 2018-09-03 | 58 | KAWASAKI KST-165ZF/A |  |  |  | URGENT |  | OPEN (akan dicheck kembali receive nya, karena sdh dibelikan)
47/ED/SEPTEMBER/2018 | FILTER OWS | 2018-09-05 | 60 |  |  |  |  | URGENT |  | OPEN (filter2 tsb sangat sulit dicari yg sama persis, harus dibawa turun dan dicocokkan di supplayer)
054/ED/OKTOBER/2018 | RUNNING STORE | 2018-10-01 | 65 |  |  |  |  | URGENT |  | OPEN
055/ED/OKTOBER/2018 | RUNNING STORE | 2- OCT-2018 | 66 | [6 empty] | OPEN
059/ED/OCTOBER/2018 | RUNNING STORE | 8-OCT-2018 | 68 | [6 empty] | OPEN
060/ED/OCTOBER/2018 | HYDROLICK OIL | 10-OCT-2018 | 69 | YANMAR |  |  |  | URGENT |  | OPEN (ini req untuk lub oil governor SAE 20 -40)
065/ED/OCTOBER/2018 | WATER TREATMANT | 23-OCT-2018 | 71 | AE |  |  |  | URGENT |  | OPEN
073/ED/NOVEMBER/2018 | MAIN ENGINE | 2018-11-04 | 76 | YANMAR 8N21A-EN |  |  |  | URGENT |  | OPEN
078/ED/NOEMBER/2018 | MAIN ENGINE | 2018-11-12 | 80 | YANMAR 8N21A-EN |  |  |  | URGENT |  | OPEN
086/ED/DESEMBER/2018 | HARBOUR GENERATOR | 2018-12-08 | 84 | CUMMINS B33 |  |  |  | NORMAL |  | OPEN
100/ED/JANUARY/2019 | HARBOUR GENERATOR | 2019-01-09 | 89 | CUMMINS B33 |  |  |  | URGENT |  | OPEN (kita akan hold dulu karena baru dilakukan GO, akan dibudgetkan thn depan)
106/ED/JANUARY/2019 | MAIN ENGINE | 2019-01-26 | 91 | PISTON |  |  |  | URGENT |  | OPEN
108/ED/JANUARY/2019 | MAIN AIR COMPRESSOR | 2019-01-02 | 92 | YANMAR SC5N-TP |  |  |  | URGENT |  | OPEN (penawaran harga baru masuk 1 vendor)
110/ED/FEBRUARY/2019 | AUXILIARY ENGINE | 2019-02-11 | 93 | SENSOR |  |  |  | NORMAL |  | OPEN
111/ED/FEBRUARY/2019 | RUNNING STORE | 2019-01-11 | 94 | VALVE |  |  |  | NORMAL |  | OPEN
125/ED/MARCH/2019 | COMPRESSOR YANMAR 1 UNIT | 22-Marc-2019 | 96 | YANMAR SC5N-TP | 1 | Unit |  | URGENT |  | OPEN (penawaran harga baru masuk 1 vendor)
133/ED/MAY/2019 | FUEL INJACTION PUMP | 17-May-2019 | 100 | YANMAR 8N21A |  | PCS |  | NORMAL |  | OPEN
134/ED/MAY/2019 | DINAMO STARTER ASSY | 18-MAY-2019 | 101 | YANMAR 8N21A | 1 | SET |  | NORMAL |  | OPEN
135/ED/MAY/2019 | PARA METER FW AT BRIDGE | 20-MAY-2019 | 102 | YANMAR 8N21A | 2 | PCS |  | NORMAL |  | OPEN
136/ED/JUNE/2019 | AVR MX341 | 11-JUNE-2019 | 102 | PERKINS 6TWGM | 2 | PCS |  | NORMAL |  | OPEN
137/ED/JUNE/2019 | DROP KIT 150 KVA | 11-JUNE-2019 | 103 | PERKINS 6TWGM | 2 | PCS |  | NORMAL |  | OPEN
138/ED/JUNE/2019 | SEA WATER COOLING PUMP ASSY | 29-JUNE-2019 | 104 | YANMAR 8N21A | 1 | SET |  | NORMAL |  | OPEN
139/ED/JULY/2019 | AE RAW WATER PUMP | 04-JULY-2019 | 105 | PERKINS 6TWGM | 1 | SET |  | NORMAL |  | OPEN
140/ED/JULY/2019 | SW VALVE ME & AE | 08-JULY-2019 | 106 | YANMAR 8N21A | 2 | PCS |  | URGENT |  | OPEN
147/ED/OCT/2019 | SEWAGE EQUIPMENT | 2019-10-10 | 110 | SEWAGE TREATMENT SWITCH |  |  |  | URGENT |  | OPEN
148/ED/OCT/2019 | SAFETY EQUIPMENT | 2019-10-10 | 111 | PORTABLE PUMP/ALKON | 1 | UNIT |  | URGENT |  | OPEN
150/ED/OCT/2019 | ENGINE EQUIPMENT | 2019-10-30 | 112 | FILTER RACOR |  |  |  | URGENT |  | OPEN
156/ED/DEC/2019 | ENGINE EQUIPMENT | 24-DEC-2019 | 114 | Bottle sample | 30 | Pcs |  | NORMAL |  | OPEN
157/ED/DEC/2019 | ENGINE EQUIPMENT | 25-DEC-2019 | 115 | Majun | 50 | Kg |  | NORMAL |  | OPEN
Outstanding Defect
Defect description | Date reported Based on statement Of fact | Status Open / Closed date | Action Taken | Target Complete
ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 2019-05-17 | OPEN | O/H
ME PORT SIDE CYL NO. 7, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 15-July-2019 | OPEN | O/H
Note on B37: SISM RICCO: Docking list dibuat oleh TS dan target selesai tanggal 30 Juli 2019, dari PEIP akan menyiapkan kapal pengganti, renewal notifikasi lebih dr 15 thun
Note on B42: SISM RICCO: akan kita rencanakan di waktu perawtatan dibulan january/feb 2020
Note on B43: SISM RICCO: masih meunggu konfirmasi dr kontraktor mas slamet (peip kintraktor)
Note on B44: SISM RICCO: kondisi saat ini sdh baik
Note on B45: SISM RICCO: diupyakn dilakukan saat docking
Note on B47: SISM RICCO: est tiba di muntok tgl 3 jan 2020

## APR 2020
MASTER NAME : TAUFIK FAISAL
PHONE NO : 081231667177
C/E NAME : DIAN APRIZAL
PHONE NO : 081326714831
EMAIL : asd-rhayden@ekanuri.com
VESSEL NAME | TB. ASD. ENC RHAYDEN
VESSEL STATUS | OPERATION
CLIENT/CHARTERER | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
VESSEL LOCATION | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
ON HIRE DATE | 31-01-2019
CONTRACT DURATION | 1460 DAYS
END CONTRACT DATE
LAST EXTERNAL INSPECTION OVID/CMID | 29-08-2019 (Mr Dave Whiting & Pak Andi Basri)
LAST MANAGEMENT VISIT | 28-12-2019 (Pak Yosef/PEIP)
LAST TECHNICAL SUPERINTENDENT VISIT | 28-11-2019 (Bas Ricco / SISM)
LAST MASTER ASSESMENT | 2019-04-27
LAST JOB VERIFICATION
LAST BPI SUPPLIED ONBOARD | BPI 14/27.03.2020 / Dowload Internet
LAST NTM SUPPLIED ONBOARD | N/A
CERTIFICATE EXPIRING IN 60 DAYS
NAME OF CERTIFICATE | EXPIRY DATE
SPOGK | 13 MARET 2020
CARGO SHIP SAFETY CONTRUCTION CERTF | 13 MEI 2020
CARGO SHIP SAFETY RADIO CERTF | 13 MEI 2020
CARGO SHIP SAFETY EQUIPMENT CERTF | 13 MEI 2020
CLASS CERTIFICATE
NEXT ANNUAL SURVEY WINDOW | 09-Oct-2019 ( ANNUAL SURVEY 2 )
NEXT DOCKING WINDOW | 2021-04-29
INTERMEDIATE WINDOW | 2020-01-26
SPECIAL SURVEY WINDOW | 2022-07-26
DEFECT REPORT
DEFECT | STATUS
1. ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN RPM 750 | OPEN
2. PANEL MSB AUX ENGINE, KW METER AE 1 & 2 NOT FUCTIONING PROPERLY | OPEN
3. PARAMETER FW COOLING ME PORT SIDE ON BRIDGE NOT FUNCTIONING PROPERLY | OPEN
4. SW VALVE SUCTION COOLING PUMP ME PORTSIDE | OPEN
5. SW VALVE COOLING PUMP AE 1 | OPEN
6. RUBBER BOAT | OPEN
7. ANCHOR WINCDLASS | OPEN
FUEL CONSUMPTION OVER
OVER QUANTITY | FUEL REPORT DATE
NIL | NIL
CREW ROTATION IN 30 DAYS
CREW SIGN OFF | TENTATIVE DATE
AMRAN BONE PASAU / COOK | 11 MARET 2020
CREW RELIEVER | TENTATIVE DATE SIGN ON
ISHAK SUHERMAN / AB-COOK | 11 MARET 2020
CREW EXPIRED CERTIFICATE IN 90 DAYS
NAME OF CERTIFICATE /HOLDER | EXPIRY DATE
Note :
SEAMAN BOOK / SAMGAR ARTHUR (2/O) | 11 APRIL 2020 | SUDAH KAMI SAMPAIKAN KEPADA YANG BERSANGKUTAN
BOCT / SAMGAR ARTHUR (2/O) | 11 MARET 2020
SCRB / YONATHAN RAMBA (2/E) | 04 MARET 2020
AFF / YONATHAN RAMBA (2/E) | 04 MARET 2020
ERM / MISBAK (3/E) | 12 JUNE 2020
AFF / MISBAK (3/E) | 22 JANUARY 2020
INSPECTION OUTSTANDING
NC/OBSERVATION ITEMS | STATUS
NIL
DECK REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
009/DD/MEI/2018 | STORES EQUIPMENT | 2018-02-05 | 9 | CAMERA DIGITAL | 1 | UNIT | 2018-05-05 | URGENT |  | OPEN (akan dibelikan dgn menggunakan kas kapal)
149/DD/OCT/2019 | DECK EQUIPMENT | 21/10/2019 | 56 | MOORING ROPE 12" | 1 | ROLL |  | URGENT |  | 0PEN
159/DD/JAN/2020 | DECK EQUIPMENT | 2020-02-01 | 173 | RUBBER BOAT | 1 | UNIT |  | URGENT |  | OPEN
162/DD/MAR/2020 | RUNNING STORE | 2020-05-03 | 176 |  |  |  |  | NORMAL |  | OPEN
164/DD/MAR/2020 | SAFETY EQUIPMENT | 2020-12-03 | 178 | LIFEBOUY LIGHT & SMOKE | 2 | SET |  | NORMAL |  | OPEN
165/DD/MAR/2020 | GALLEY EQUIPMENT | 16/03/2020 | 179 | RICE COOKER | 1 | UNIT |  | URGENT |  | OPEN
166/DD/MAR/2020 | RUNNING STORE | 24/03/2020 | 181 | ALKYD PRIMER & THINNER |  |  |  | NORMAL |  | OPEN
Outstanding Requisition
ENGINE REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
06/ED/MARCH/2018 | AIR COMP | 2018-03-21 | 6 | YANMAR |  |  |  | NORMAL |  | OPEN (penawaran harga baru masuk 1 vendor)
07/ED/MARCH/2018 | EM'CY PORTABLE | 2018-03-21 | 7 |  |  |  |  | NORMAL |  | CANCEL
08/ED/MARCH/2018 | RUNNING STORE | 2018-03-22 | 8 |  |  |  |  | NORMAL |  | OPEN
24/ED/JUNI/2018 | SPARE PART CUMMINS | 2018-06-05 | 28 | CUMMINS B33 |  |  |  | URGENT |  | OPEN (kita akan hold dulu karena baru dilakukan GO, akan dibudgetkan thn depan)
011/ED/JUNI/2018 | CRANES | 2018-06-26 | 36 | PM 10021 |  |  |  | URGENT |  | OPEN
012/ED/JUNI/2018 | CRANES | 2018-06-26 | 37 | PM 10021 |  |  |  | URGENT |  | OPEN
013/ED/JUNI/2018 | AUXILIARY ENGINE | 2018-06-26 | 38 | PERKINS 6TWGM |  |  |  | URGENT |  | OPEN
015/ED/JULI/2018 | SPARE PART CRANES | 2018-07-10 | 40 | PM 10021 |  |  |  | URGENT |  | OPEN
016/ED/JULI/2018 | RUNNING STORE | 2018-07-10 | 41 |  |  |  |  | URGENT |  | OPEN
023/ED/JULI/2O18 | WIRE CRANE | 2018-08-01 | 46 | PM 10021 |  |  |  | NORMAL |  | OPEN (akan kita budgetkan di tahun depan) | Reminder req (akhir june 2019 sdh on board)
028/ED/JULI/2018 | SPECIAL TOOL REXPELLER | 28-JULI-2018 | 47 | KAWASAKI KST-165ZF/A |  |  |  | NORMAL |  | OPEN (kita hold dulu utk req tool nya)
029/ED/JULI/2018 | REXPELLER HIDRAULIC PUMP | 28-JULI-2018 | 48 | KAWASAKI KST-165ZF/A |  |  |  | NORMAL |  | OPEN (kita hold dulu utk suppy part2nya, karena seal sealnya sdh ada diatas kapal)
45/ED/SEPTEMBER/2018 | SEAL POMPA REXPELLER | 2018-09-03 | 58 | KAWASAKI KST-165ZF/A |  |  |  | URGENT |  | OPEN (akan dicheck kembali receive nya, karena sdh dibelikan)
47/ED/SEPTEMBER/2018 | FILTER OWS | 2018-09-05 | 60 |  |  |  |  | URGENT |  | OPEN (filter2 tsb sangat sulit dicari yg sama persis, harus dibawa turun dan dicocokkan di supplayer)
054/ED/OKTOBER/2018 | RUNNING STORE | 2018-10-01 | 65 |  |  |  |  | URGENT |  | OPEN
055/ED/OKTOBER/2018 | RUNNING STORE | 2- OCT-2018 | 66 | [6 empty] | OPEN
059/ED/OCTOBER/2018 | RUNNING STORE | 8-OCT-2018 | 68 | [6 empty] | OPEN
060/ED/OCTOBER/2018 | HYDROLICK OIL | 10-OCT-2018 | 69 | YANMAR |  |  |  | URGENT |  | OPEN (ini req untuk lub oil governor SAE 20 -40)
065/ED/OCTOBER/2018 | WATER TREATMANT | 23-OCT-2018 | 71 | AE |  |  |  | URGENT |  | OPEN
073/ED/NOVEMBER/2018 | MAIN ENGINE | 2018-11-04 | 76 | YANMAR 8N21A-EN |  |  |  | URGENT |  | OPEN
078/ED/NOEMBER/2018 | MAIN ENGINE | 2018-11-12 | 80 | YANMAR 8N21A-EN |  |  |  | URGENT |  | OPEN
086/ED/DESEMBER/2018 | HARBOUR GENERATOR | 2018-12-08 | 84 | CUMMINS B33 |  |  |  | NORMAL |  | OPEN
100/ED/JANUARY/2019 | HARBOUR GENERATOR | 2019-01-09 | 89 | CUMMINS B33 |  |  |  | URGENT |  | OPEN (kita akan hold dulu karena baru dilakukan GO, akan dibudgetkan thn depan)
106/ED/JANUARY/2019 | MAIN ENGINE | 2019-01-26 | 91 | PISTON |  |  |  | URGENT |  | OPEN
108/ED/JANUARY/2019 | MAIN AIR COMPRESSOR | 2019-01-02 | 92 | YANMAR SC5N-TP |  |  |  | URGENT |  | OPEN (penawaran harga baru masuk 1 vendor)
110/ED/FEBRUARY/2019 | AUXILIARY ENGINE | 2019-02-11 | 93 | SENSOR |  |  |  | NORMAL |  | OPEN
111/ED/FEBRUARY/2019 | RUNNING STORE | 2019-01-11 | 94 | VALVE |  |  |  | NORMAL |  | OPEN
125/ED/MARCH/2019 | COMPRESSOR YANMAR 1 UNIT | 22-Marc-2019 | 96 | YANMAR SC5N-TP | 1 | Unit |  | URGENT |  | OPEN (penawaran harga baru masuk 1 vendor)
133/ED/MAY/2019 | FUEL INJACTION PUMP | 17-May-2019 | 100 | YANMAR 8N21A |  | PCS |  | NORMAL |  | OPEN
134/ED/MAY/2019 | DINAMO STARTER ASSY | 18-MAY-2019 | 101 | YANMAR 8N21A | 1 | SET |  | NORMAL |  | OPEN
135/ED/MAY/2019 | PARA METER FW AT BRIDGE | 20-MAY-2019 | 102 | YANMAR 8N21A | 2 | PCS |  | NORMAL |  | OPEN
136/ED/JUNE/2019 | AVR MX341 | 11-JUNE-2019 | 102 | PERKINS 6TWGM | 2 | PCS |  | NORMAL |  | OPEN
137/ED/JUNE/2019 | DROP KIT 150 KVA | 11-JUNE-2019 | 103 | PERKINS 6TWGM | 2 | PCS |  | NORMAL |  | OPEN
138/ED/JUNE/2019 | SEA WATER COOLING PUMP ASSY | 29-JUNE-2019 | 104 | YANMAR 8N21A | 1 | SET |  | NORMAL |  | OPEN
139/ED/JULY/2019 | AE RAW WATER PUMP | 04-JULY-2019 | 105 | PERKINS 6TWGM | 1 | SET |  | NORMAL |  | OPEN
140/ED/JULY/2019 | SW VALVE ME & AE | 08-JULY-2019 | 106 | YANMAR 8N21A | 2 | PCS |  | URGENT |  | OPEN
147/ED/OCT/2019 | SEWAGE EQUIPMENT | 2019-10-10 | 110 | SEWAGE TREATMENT SWITCH |  |  |  | URGENT |  | OPEN
148/ED/OCT/2019 | SAFETY EQUIPMENT | 2019-10-10 | 111 | PORTABLE PUMP/ALKON | 1 | UNIT |  | URGENT |  | OPEN
150/ED/OCT/2019 | ENGINE EQUIPMENT | 2019-10-30 | 112 | FILTER RACOR |  |  |  | URGENT |  | OPEN
156/ED/DEC/2019 | ENGINE EQUIPMENT | 24-DEC-2019 | 114 | Bottle sample | 30 | Pcs |  | NORMAL |  | OPEN
157/ED/DEC/2019 | ENGINE EQUIPMENT | 25-DEC-2019 | 115 | Majun | 50 | Kg |  | NORMAL |  | OPEN
167/ED/MAR/2020 | ENGINE EQUIPMENT | 2020-03-25 | 182 | AE FILTER | 24 | Pcs |  | NORMAL |  | OPEN
Outstanding Defect
Defect description | Date reported Based on statement Of fact | Status Open / Closed date | Action Taken | Target Complete
ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 2019-05-17 | OPEN | O/H
ME PORT SIDE CYL NO. 7, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 15-July-2019 | OPEN | O/H
Note on B37: SISM RICCO: Docking list dibuat oleh TS dan target selesai tanggal 30 Juli 2019, dari PEIP akan menyiapkan kapal pengganti, renewal notifikasi lebih dr 15 thun
Note on B42: SISM RICCO: akan kita rencanakan di waktu perawtatan dibulan january/feb 2020
Note on B43: SISM RICCO: masih meunggu konfirmasi dr kontraktor mas slamet (peip kintraktor)
Note on B44: SISM RICCO: kondisi saat ini sdh baik
Note on B45: SISM RICCO: diupyakn dilakukan saat docking

## 29 APR 2020
MASTER NAME : TAUFIK FAISAL
PHONE NO : 081231667177
C/E NAME : DIAN APRIZAL
PHONE NO : 081326714831
EMAIL : asd-rhayden@ekanuri.com
VESSEL NAME | TB. ASD. ENC RHAYDEN
VESSEL STATUS | OPERATION
CLIENT/CHARTERER | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
VESSEL LOCATION | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
ON HIRE DATE | 31-01-2019
CONTRACT DURATION | 1460 DAYS
END CONTRACT DATE
LAST EXTERNAL INSPECTION OVID/CMID | 29-08-2019 (Mr Dave Whiting & Pak Andi Basri)
LAST MANAGEMENT VISIT | 28-12-2019 (Pak Yosef/PEIP)
LAST TECHNICAL SUPERINTENDENT VISIT | 28-11-2019 (Bas Ricco / SISM)
LAST MASTER ASSESMENT | 2019-04-27
LAST JOB VERIFICATION
LAST BPI SUPPLIED ONBOARD | BPI 18/24.04.2020 / Dowload Internet
LAST NTM SUPPLIED ONBOARD | N/A
CERTIFICATE EXPIRING IN 60 DAYS
NAME OF CERTIFICATE | EXPIRY DATE
SPOGK | 13 MEI 2020
CARGO SHIP SAFETY CONTRUCTION CERTF | 13 MEI 2020 (extent 3 bulan/nota dinas)
CARGO SHIP SAFETY RADIO CERTF | 13 MEI 2020 (extent 3 bulan/nota dinas)
CARGO SHIP SAFETY EQUIPMENT CERTF | 13 MEI 2020 (extent 3 bulan/nota dinas)
MINIMUM SAFE MANNING | 06 JUNI 2020
NATIONAL ANTI FOULING SYSTEM CERTF | 26 JUNI 2020
RENCANA POLA TRAYEK | 28 JUNI 2020
CLASS CERTIFICATE
NEXT ANNUAL SURVEY WINDOW | 09-Oct-2019 ( ANNUAL SURVEY 2 )
NEXT DOCKING WINDOW | 2021-04-29
INTERMEDIATE WINDOW | 2020-01-26
SPECIAL SURVEY WINDOW | 2022-07-26
DEFECT REPORT
DEFECT | STATUS
1. ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN RPM 750 | OPEN
2. PANEL MSB AUX ENGINE, KW METER AE 1 & 2 NOT FUCTIONING PROPERLY | OPEN
3. PARAMETER FW COOLING ME PORT SIDE ON BRIDGE NOT FUNCTIONING PROPERLY | CLOSE
4. SW VALVE SUCTION COOLING PUMP ME PORTSIDE | OPEN
5. SW VALVE COOLING PUMP AE 1 | OPEN
6. RUBBER BOAT | OPEN
7. ANCHOR WINCDLASS | OPEN
FUEL CONSUMPTION OVER
OVER QUANTITY | FUEL REPORT DATE
NIL | NIL
CREW ROTATION IN 30 DAYS
CREW SIGN OFF | TENTATIVE DATE
SAMGAR ARTHUR / 2ND OFFICER | 01 APRIL 2020
YONATHAN RAMBA / 2ND ENGINEER | 02 APRIL 2020
BAYU TRI PRABOWO / OILER | 02 APRIL 2020
CREW RELIEVER | TENTATIVE DATE SIGN ON
BAHKTIAR / 2ND OFFICER | 01 APRIL 2020
RUNDI / 2ND ENGINEER | 02 APRIL 2020
HASRUL GUNAWAN / OILER | 02 APRIL 2020
CREW EXPIRED CERTIFICATE IN 90 DAYS
NAME OF CERTIFICATE /HOLDER | EXPIRY DATE
Note :
SEAMAN BOOK / SAMGAR ARTHUR (2/O) | 11 APRIL 2020 | 1. Sudah disampaikan ke crew dan office agar dpt diproses saat rotasi cuti
BOCT / SAMGAR ARTHUR (2/O) | 11 MARET 2020 | 2. Dengan adanya polemic issue Covid-19 maka untuk kegiatan perpanjang cert dpt diexten 3 bulan
SCRB / YONATHAN RAMBA (2/E) | 04 MARET 2020
AFF / YONATHAN RAMBA (2/E) | 04 MARET 2020
ERM / MISBAK (3/E) | 12 JUNI 2020
AFF / MISBAK (3/E) | 22 JANUARI 2020
MCU / PURWANDOYO (C/O) | 09 JULI 2020
MCU / DIAN APRIZAL (C/E) | 05 JULI 2020
MCU / MISBAK (3/E) | 04 FEBRUARI 2020
MCU / FERRY FIRMANTO (A/B) | 13 JUNI 2020
MCU / AWALUDIN (A/B) | 22 FEBRUARI 2020
INSPECTION OUTSTANDING
NC/OBSERVATION ITEMS | STATUS
NIL
DECK REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
159/DD/JAN/2020 | DECK EQUIPMENT | 2020-02-01 | 173 | RUBBER BOAT | 1 | UNIT |  | URGENT |  | OPEN | PO sdh terbit
162/DD/MAR/2020 | RUNNING STORE | 2020-05-03 | 176 |  |  |  |  | NORMAL |  | OPEN | PO sdh terbit
164/DD/MAR/2020 | SAFETY EQUIPMENT | 2020-12-03 | 178 | LIFEBOUY LIGHT & SMOKE | 2 | SET |  | NORMAL |  | OPEN | PO sdh terbit
165/DD/MAR/2020 | GALLEY EQUIPMENT | 16/03/2020 | 179 | RICE COOKER | 1 | UNIT |  | URGENT |  | OPEN | PO sdh terbit
166/DD/MAR/2020 | RUNNING STORE | 24/03/2020 | 181 | ALKYD PRIMER & THINNER |  |  |  | NORMAL |  | OPEN | PO sdh terbit
Outstanding Requisition
ENGINE REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
167/ED/MAR/2020 | ENGINE EQUIPMENT | 2020-03-25 | 182 | AE FILTER | 24 | Pcs |  | NORMAL |  | OPEN | PO sdh terbit
Outstanding Defect
Defect description | Date reported Based on statement Of fact | Status Open / Closed date | Action Taken | Target Complete
ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 2019-05-17 | OPEN | O/H | Plan Docking
ME PORT SIDE CYL NO. 7, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 15-July-2019 | OPEN | O/H | Plan Docking
Note on B37: SISM RICCO: Docking list dibuat oleh TS dan target selesai tanggal 30 Juli 2019, dari PEIP akan menyiapkan kapal pengganti, renewal notifikasi lebih dr 15 thun
Note on B42: SISM RICCO: plan docking
Note on B43: SISM RICCO: masih meunggu konfirmasi dr kontraktor mas slamet (peip kintraktor)
Note on B44: SISM RICCO: kondisi saat ini sdh baik
Note on B45: SISM RICCO: diupyakn dilakukan saat docking
Note on B46: SISM RICCO: plan docking
Note on B47: SISM RICCO: PO sdh terbit, proses pengiriman
Note on B48: SISM RICCO: plan docking, DR sdh dikirim, dilakukan temporary repaire oleh crew
Note on B60: SISM RICCO: polemic covid-19
Note on B61: SISM RICCO: polemic covid-19
Note on B62: SISM RICCO: polemic covid-19

## MAY 2020
MASTER NAME : TAUFIK FAISAL
PHONE NO : 081231667177
C/E NAME : DIAN APRIZAL
PHONE NO : 081326714831
EMAIL : asd-rhayden@ekanuri.com
VESSEL NAME | TB. ASD. ENC RHAYDEN
VESSEL STATUS | OPERATION
CLIENT/CHARTERER | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
VESSEL LOCATION | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
ON HIRE DATE | 31-01-2019
CONTRACT DURATION | 1460 DAYS
END CONTRACT DATE
LAST EXTERNAL INSPECTION OVID/CMID | 29-08-2019 (Mr Dave Whiting & Pak Andi Basri)
LAST MANAGEMENT VISIT | 28-12-2019 (Pak Yosef/PEIP)
LAST TECHNICAL SUPERINTENDENT VISIT | 28-11-2019 (Bas Ricco / SISM)
LAST MASTER ASSESMENT | 2019-04-27
LAST JOB VERIFICATION
LAST BPI SUPPLIED ONBOARD | BPI 23/29.04.2020 / Dowload Internet
LAST NTM SUPPLIED ONBOARD | N/A
CERTIFICATE EXPIRING IN 60 DAYS
NAME OF CERTIFICATE | EXPIRY DATE
SPOGK | 13 JUNE 2020
MINIMUM SAFE MANNING | 06 JUNE 2020
NATIONAL ANTI FOULING SYSTEM CERTF | 26 JUNE 2020
RENCANA POLA TRAYEK | 28 JUNE 2020
SHIP'S CERTF OF MEDICINE CHEST | 14 JULY 2020
CLASS CERTIFICATE
NEXT ANNUAL SURVEY WINDOW | 09-Oct-2019 ( ANNUAL SURVEY 2 )
NEXT DOCKING WINDOW | 2021-04-29
INTERMEDIATE WINDOW | 2020-01-26
SPECIAL SURVEY WINDOW | 2022-07-26
DEFECT REPORT
DEFECT | STATUS
1. ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN RPM 750 | OPEN
2. PANEL MSB AUX ENGINE, KW METER AE 1 & 2 NOT FUCTIONING PROPERLY | OPEN
3. PARAMETER FW COOLING ME PORT SIDE ON BRIDGE NOT FUNCTIONING PROPERLY | CLOSE
4. SW VALVE SUCTION COOLING PUMP ME PORTSIDE | OPEN
5. SW VALVE COOLING PUMP AE 1 | OPEN
6. RUBBER BOAT | CLOSE
7. ANCHOR WINCDLASS | OPEN
8. REPAIR & SERVICE AC SPLIT | OPEN
FUEL CONSUMPTION OVER
OVER QUANTITY | FUEL REPORT DATE
NIL | NIL
CREW ROTATION IN 30 DAYS
CREW SIGN OFF | TENTATIVE DATE
CREW RELIEVER | TENTATIVE DATE SIGN ON
CREW EXPIRED CERTIFICATE IN 90 DAYS
NAME OF CERTIFICATE /HOLDER | EXPIRY DATE
Note :
SEAMAN BOOK / SAMGAR ARTHUR (2/O) | 11 APRIL 2020 | 1. Sudah disampaikan ke crew dan office agar dpt diproses saat rotasi cuti
BOCT / SAMGAR ARTHUR (2/O) | 11 MARET 2020 | 2. Dengan adanya polemic issue Covid-19 maka untuk kegiatan perpanjang cert dpt diexten 3 bulan
SCRB / YONATHAN RAMBA (2/E) | 04 MARET 2020
AFF / YONATHAN RAMBA (2/E) | 04 MARET 2020
ERM / MISBAK (3/E) | 12 JUNI 2020
AFF / MISBAK (3/E) | 22 JANUARI 2020
MCU / PURWANDOYO (C/O) | 09 JULI 2020
MCU / DIAN APRIZAL (C/E) | 05 JULI 2020
MCU / MISBAK (3/E) | 04 FEBRUARI 2020
MCU / FERRY FIRMANTO (A/B) | 13 JUNI 2020
MCU / AWALUDIN (A/B) | 22 FEBRUARI 2020
INSPECTION OUTSTANDING
NC/OBSERVATION ITEMS | STATUS
NIL
DECK REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
162/DD/MAR/2020 | RUNNING STORE | 2020-05-03 | 176 |  |  |  |  | NORMAL |  | OPEN | PO sdh terbit
164/DD/MAR/2020 | SAFETY EQUIPMENT | 2020-12-03 | 178 | LIFEBOUY LIGHT & SMOKE | 2 | SET |  | NORMAL |  | OPEN | PO sdh terbit
165/DD/MAR/2020 | GALLEY EQUIPMENT | 16/03/2020 | 179 | RICE COOKER | 1 | UNIT |  | URGENT |  | OPEN | PO sdh terbit
166/DD/MAR/2020 | RUNNING STORE | 24/03/2020 | 181 | ALKYD PRIMER & THINNER |  |  |  | NORMAL |  | OPEN | PO sdh terbit
Outstanding Requisition
ENGINE REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
Outstanding Defect
Defect description | Date reported Based on statement Of fact | Status Open / Closed date | Action Taken | Target Complete
ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 2019-05-17 | OPEN | O/H | Plan Docking
ME PORT SIDE CYL NO. 7, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 15-July-2019 | OPEN | O/H | Plan Docking
Note on B37: SISM RICCO: Docking list dibuat oleh TS dan target selesai tanggal 30 Juli 2019, dari PEIP akan menyiapkan kapal pengganti, renewal notifikasi lebih dr 15 thun
Note on B42: SISM RICCO: plan docking
Note on B43: SISM RICCO: masih meunggu konfirmasi dr kontraktor mas slamet (peip kintraktor)
Note on B44: SISM RICCO: kondisi saat ini sdh baik
Note on B45: SISM RICCO: diupyakn dilakukan saat docking
Note on B46: SISM RICCO: plan docking
Note on B47: SISM RICCO: PO sdh terbit, proses pengiriman
Note on B48: SISM RICCO: plan docking, DR sdh dikirim, dilakukan temporary repaire oleh crew
Note on B49: SISM RICCO: plan docking, DR sdh dikirim, dilakukan temporary repaire oleh crew
Note on B61: SISM RICCO: polemic covid-19
Note on B62: SISM RICCO: polemic covid-19
Note on B63: SISM RICCO: polemic covid-19

## JUNE 2020
MASTER NAME : PURWANDOYO
PHONE NO : 081227427746
C/E NAME : DIAN APRIZAL
PHONE NO : 081326714831
EMAIL : asd-rhayden@ekanuri.com
VESSEL NAME | TB. ASD. ENC RHAYDEN
VESSEL STATUS | OPERATION
CLIENT/CHARTERER | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
VESSEL LOCATION | CONOCOPHILIPS, GRISSIK, MUNTOK, BANGKA.
ON HIRE DATE | 31-01-2019
CONTRACT DURATION | 1460 DAYS
END CONTRACT DATE
LAST EXTERNAL INSPECTION OVID/CMID | 29-08-2019 (Mr Dave Whiting & Pak Andi Basri)
LAST MANAGEMENT VISIT | 28-12-2019 (Pak Yosef/PEIP)
LAST TECHNICAL SUPERINTENDENT VISIT | 28-11-2019 (Bas Ricco / SISM)
LAST MASTER ASSESMENT | 2020-06-25
LAST JOB VERIFICATION
LAST BPI SUPPLIED ONBOARD | BPI 27/26.06.2020 / Dowload Internet
LAST NTM SUPPLIED ONBOARD | N/A
CERTIFICATE EXPIRING IN 60 DAYS
NAME OF CERTIFICATE | EXPIRY DATE
SPOGK | 13 JULY 2020
NATIONAL ANTI FOULING SYSTEM CERTF | 26 JUNE 2020
SHIP'S CERTF OF MEDICINE CHEST | 14 JULY 2020
CARGO SHIP SAFETY CONTRUCTION CERTF | 13 AUGT 2020
CARGO SHIP SAFETY RADIO CERTF | 13 AUGT 2020
CARGO SHIP SAFETY EQUIPMENT CERTF | 13 AUGT 2020
CLASS CERTIFICATE
NEXT ANNUAL SURVEY WINDOW | 09-Oct-2019 ( ANNUAL SURVEY 2 )
NEXT DOCKING WINDOW | 2021-04-29
INTERMEDIATE WINDOW | 2020-01-26
SPECIAL SURVEY WINDOW | 2022-07-26
DEFECT REPORT
DEFECT | STATUS
1. ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN RPM 750 | OPEN
2. PANEL MSB AUX ENGINE, KW METER AE 1 & 2 NOT FUCTIONING PROPERLY | OPEN
3. PARAMETER FW COOLING ME PORT SIDE ON BRIDGE NOT FUNCTIONING PROPERLY | CLOSE
4. SW VALVE SUCTION COOLING PUMP ME PORTSIDE | OPEN
5. SW VALVE COOLING PUMP AE 1 | OPEN
6. RUBBER BOAT | CLOSE
7. ANCHOR WINCDLASS | OPEN
8. REPAIR & SERVICE AC SPLIT | OPEN
FUEL CONSUMPTION OVER
OVER QUANTITY | FUEL REPORT DATE
NIL | NIL
CREW ROTATION IN 30 DAYS
CREW SIGN OFF | TENTATIVE DATE
TAUFIK FAISAL (MASTER) | 25/06/2020
MISBAK (3RD ENGINEER) | 25/06/2020
FERRY FIRMANTO (AB) | 25/06/2020
CREW RELIEVER | TENTATIVE DATE SIGN ON
PURWANDOYO ( PROMOTE MASTER) | 25/06/2020
BAHKTIAR (PROMOTE CHIEF OFF) | 25/06/2020
SAMGAR ARTHUR (2ND OFFICER) | 25/06/2020
YONATHAN RAMBA (3RD ENGINEER) | 25/06/2020
AMRAN BONE PASAU (COOK) | 25/06/2020
CREW EXPIRED CERTIFICATE IN 90 DAYS
NAME OF CERTIFICATE /HOLDER | EXPIRY DATE
SCRB / YONATHAN RAMBA (2/E) | 04 MARET 2020 | 1. Sementara dalam proses update menunggu sertifikat terbit
AFF / YONATHAN RAMBA (2/E) | 04 MARET 2020 | 2. Sementara dalam proses update menunggu sertifikat terbit
ERM / MISBAK (3/E) | 12 JUNI 2020 | 3. Sudah disampaikan ke crew dan office agar dpt diproses saat rotasi cuti
AFF / MISBAK (3/E) | 22 JANUARI 2020 | 4. Sudah disampaikan ke crew dan office agar dpt diproses saat rotasi cuti
2. Sudah disampaikan ke crew dan office agar dpt diproses saat rotasi cuti
2. Sudah disampaikan ke crew dan office agar dpt diproses saat rotasi cuti
2. Sudah disampaikan ke crew dan office agar dpt diproses saat rotasi cuti
2. Sudah disampaikan ke crew dan office agar dpt diproses saat rotasi cuti
MCU / PURWANDOYO (C/O) | 09 JULI 2020 | 5. Sudah disampaikan ke crew dan office agar dpt diproses saat rotasi cuti
MCU / DIAN APRIZAL (C/E) | 05 JULI 2020 | 6. Sudah disampaikan ke crew dan office agar dpt diproses saat rotasi cuti
MCU / AWALUDIN (A/B) | 22 FEBRUARI 2020 | 7. Dengan adanya polemic issue Covid-19 maka untuk kegiatan perpanjang cert dpt diexten 3 bulan
INSPECTION OUTSTANDING
NC/OBSERVATION ITEMS | STATUS
NIL
DECK REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
162/DD/MAR/2020 | RUNNING STORE | 2020-05-03 | 176 |  |  |  |  | NORMAL |  | OPEN | PO sdh terbit
164/DD/MAR/2020 | SAFETY EQUIPMENT | 2020-12-03 | 178 | LIFEBOUY LIGHT & SMOKE | 2 | SET |  | NORMAL |  | OPEN | PO sdh terbit
165/DD/MAR/2020 | GALLEY EQUIPMENT | 16/03/2020 | 179 | RICE COOKER | 1 | UNIT |  | URGENT |  | OPEN | PO sdh terbit
166/DD/MAR/2020 | RUNNING STORE | 24/03/2020 | 181 | ALKYD PRIMER & THINNER |  |  |  | NORMAL |  | OPEN | PO sdh terbit
169/DD/JUN/2020 | RUNNING STORE | 2020-07-06 | 182 | LOGBOOK DECK & ENGINE | 10 | PCS |  | NORMAL |  | OPEN
170/DD/JUN/2020 | RUNNING STORE | 2020-12-06 | 183 | STIKER SIMBOL ISM CODE | 25 | PCS |  | NORMAL |  | OPEN
171/DD/JUN/2020 | GALLEY EQUIPMENT | 15/06/2020 | 184 | KULKAS | 1 | UNIT |  | NORMAL |  | OPEN
Outstanding Requisition
ENGINE REQUISITION
Req Number | Subject | Req Date | No | Part Name | Qty | Unit | Needed Date | Req Priority | Supplied Date | Remarks
Outstanding Defect
Defect description | Date reported Based on statement Of fact | Status Open / Closed date | Action Taken | Target Complete
ME STB SIDE CYL NO. 3, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 2019-05-17 | OPEN | O/H | Plan Docking
ME PORT SIDE CYL NO. 7, GASKET CYL HEAD LEAKING WHEN GIVEN 750 RPM | 15-July-2019 | OPEN | O/H | Plan Docking
Note on B36: SISM RICCO: Docking list dibuat oleh TS dan target selesai tanggal 30 Juli 2019, dari PEIP akan menyiapkan kapal pengganti, renewal notifikasi lebih dr 15 thun
Note on B41: SISM RICCO: plan docking
Note on B42: SISM RICCO: masih meunggu konfirmasi dr kontraktor mas slamet (peip kintraktor)
Note on B43: SISM RICCO: kondisi saat ini sdh baik
Note on B44: SISM RICCO: diupyakn dilakukan saat docking
Note on B45: SISM RICCO: plan docking
Note on B46: SISM RICCO: PO sdh terbit, proses pengiriman
Note on B47: SISM RICCO: plan docking, DR sdh dikirim, dilakukan temporary repaire oleh crew
Note on B48: SISM RICCO: plan docking, DR sdh dikirim, dilakukan temporary repaire oleh crew
Note on B60: SISM RICCO: polemic covid-19
Note on B61: SISM RICCO: polemic covid-19
Note on B62: SISM RICCO: polemic covid-19
Note on B68: SISM RICCO: polemic covid-19
Note on B69: SISM RICCO: polemic covid-19
Note on B70: SISM RICCO: polemic covid-19
Note on B71: SISM RICCO: polemic covid-19
Note on B72: SISM RICCO: polemic covid-19