## Vessel daily report
BOAT ACTIVITIES DAILY REPORT FOR ASD ENC RHAYDEN - CALL SIGN : YDA6366
REPORTED DATE 01 DESEMBER 2020 | [12 empty] | POSITION : MUNTOK CST - BANGKA STRAIT
TIME | WINDS |  |  |  | SEA |  | SWELL |  |  |  |  | VISIBILITY | WEATHER CONDITION |  |  | ISPS Port Status
| DIR | SPEED
00:00 hrs | NNE | 04 - 10 KNOTS |  |  | SLIGHT |  | 0,2 -0,3 M |  |  |  |  | GOOD | CLAUDY |  |  | Level 1
VESSEL STATUS
Start Onhire Date |  |  |  | 24/10/2020 16:30:00 PM |  |  | Down Time 02/10/2020 18:00:00 PM |  |  |  |  | 0:00
Last Fuel Meter Calibration | [6 empty] | Start Time
Last Dry Docking | [6 empty] | Finish Time
Scheduled out of Service Start | [6 empty] | Reason
Scheduled out of Service End
|  |  |  | Running Hrs | FO Consumption |  | CONSUMABLES SUMMARY
[7 empty] | Fuel Oil | [7 empty] | Remarks
Main Engine |  |  |  | 01.30 | 480.3 | Liters | MDO Open stock | [5 empty] | 21385 | Liters
[7 empty] | MDO Received | [5 empty] | 60016.3 | Liters
Auxiliary Engine No.1 |  |  |  | 24.0 | 320 | Liters | MDO Transferred | [6 empty] | Liters
Auxiliary Engine No.2 |  |  |  | 0:00 |  | Liters | ROB MDO | [5 empty] | 80601 | Liters
Auxiliary Engine No.3 |  |  |  | 0 |  | Liters | FW Open Stock | [5 empty] | 29000 | Liters
[7 empty] | FW Consumption | [5 empty] | 3700 | Liters
Bow Thruster |  |  |  | 0 |  | Liters | FW Received | [6 empty] | Liters
[7 empty] | FW Transferred | [6 empty] | Liters
FI - FI |  |  |  | 0 |  | Liters | ROB FW | [5 empty] | 25300 | Liters
|  | Total FO Consumption |  |  | 800.3 | Liters
VESSEL ACTIVITY DETAIL REPORT
HSE: | [7 empty] | CONTRACT NUMBER : |  |  |  | CS-17629760
Incident |  | : Nil | [5 empty] | CONTRACT OWNER : |  |  |  | CST OPERATION
I Care |  | : (Safe Cond) Deck Dept : | [5 empty] | LOCATION : |  |  |  | CONOCOPHILLIPS (GRISSIK) LTD - CST MUNTOK | [5 empty] | 1 hour | 0.041667
: (Safe Cond) Engine Dept :
Immediate Action Taken |  | : Nil
Near Miss |  | : Nil
Hazard Hunting |  | : Nil
Start | Finish | Main Engine Status | Auxiliary Engine No.1 | Auxiliary Engine No.2 | Auxiliary Engine No.3 | Bow Thruster | FI - FI | Remarks |  |  |  |  | Detail Activity |  |  | Location |  | Durations | Main Engine Status | Aux 1 | Aux 2 | Aux 3 | Bow | FI - FI
00:00 | 02:00 |  | RUN |  |  |  |  | Tug Tidy Up SHIP 111 |  |  |  |  | Berthing/ Berthing
02:00 | 02:30 | RUN | RUN |  |  |  |  | SBE RE- Position |  |  |  |  | Berthing/ Berthing
02:30 | 02:42 | RUN | RUN |  |  |  |  | Continue Re-position |  |  |  |  | Berthing/ Berthing
02:42 | 03:00 |  | RUN |  |  |  |  | F.W.E |  |  |  |  | Berthing/ Berthing
03:00 | 04:00 |  | RUN |  |  |  |  | Tug Tidy Up SHIP 111 |  |  |  |  | Berthing/ Berthing
04:00 | 08:00 |  | RUN |  |  |  |  | Tug Tidy Up SHIP 111 |  |  |  |  | Berthing/ Berthing
08:00 | 08:12 |  | RUN |  |  |  |  | Tug Tidy Up SHIP 111 |  |  |  |  | Berthing/ Berthing
08:12 | 08:24 | RUN | RUN |  |  |  |  | SBE Shifting Portside SHIP 111 |  |  |  |  | Berthing/ Berthing
08:24 | 08:35 | RUN | RUN |  |  |  |  | Cast Off SHIP 111 |  |  |  |  | Berthing/ Berthing
08:35 | 08:44 | RUN | RUN |  |  |  |  | Arrival (P) Bunker Station |  |  |  |  | Berthing/ Berthing
08:44 | 09:00 | RUN | RUN |  |  |  |  | Finish alongside (P) SHIP 111 |  |  |  |  | Berthing/ Berthing
09:00 | 09:06 |  | RUN |  |  |  |  | F.W.E, Continue Connect hose Bunker |  |  |  |  | Berthing/ Berthing
09:06 | 11:36 |  | RUN |  |  |  |  | Start Fill FO |  |  |  |  | Bunker/ Transfer In
11:36 | 11:42 |  | RUN |  |  |  |  | Finish Fill FO |  |  |  |  | Bunker/ Transfer In
11:42 | 12:00 |  | RUN |  |  |  |  | Disconnect Hose |  |  |  |  | Berthing/ Berthing
12:00 | 16:00 |  | RUN |  |  |  |  | Tug Alongside Portside SHIP 111 |  |  |  |  | Berthing/ Berthing
16:00 | 20:00 |  | RUN |  |  |  |  | Tug Alongside Portside SHIP 111 |  |  |  |  | Berthing/ Berthing
20:00 | 24:00 |  | RUN |  |  |  |  | Tug Alongside Portside SHIP 111 |  |  |  |  | Berthing/ Berthing
STATUS SHIPS / CREW DOCUMENT TO BE EXPIRED NEXT MONTH | [6 empty] | MA / SATGAS ON BOARD
No | Name |  |  |  | Remark |  | No | Name
1 | Shifting Permit / SPOGK |  |  |  | Exp : 13 OCTOBER 2020
1 | Shifting Permit / SPOGK |  |  |  | Exp : 22 DESEMBER 2020
QTY | STATUS COMMUNICATION EQUIPMENT |  |  |  | REMARK
1 | asd-rhayden@ekanuri.com |  |  |  | GOOD
2 | VHF |  |  |  | GOOD
6 | HT |  |  |  | GOOD
PERSONNEL ON BOARD
No. | Name |  |  |  |  | Position |  |  | Onboard Date | Estimate Sign off |  | MCU / Expired |  | PTS Number
1 | PURWANDOYO |  |  |  |  | Master |  |  | 23 OCTOBER 2020 | AFTER 2/0 |  | 15 OCKTOBER 2021 |  | 19820365
2 | B.LOIS MANGALIK |  |  |  |  | Chief Officer |  |  | 2020-10-24 | AFTER MASTER |  | 21 OCTOBER 2021 |  | 19827309
3 | SAMGAR ARTHUR |  |  |  |  | 2nd Officer |  |  | 25 JUNE 2020 | 2020-11-26 |  | 19 JUNE 2021 |  | 19816083
4 | DIAN APRIZAL |  |  |  |  | Chief Engineer |  |  | 2020-10-23 | AFTER 3RD ENGINEER |  | 05 OCTOBER 2021 |  | 19820757
5 | YONATHAN RAMBA |  |  |  |  | 2nd Engineer |  |  | 25 JUNE 2020 | 2020-11-26 |  | 19 JUNE 2021 |  | 19821563
6 | MISBAK |  |  |  |  | 3rd Engineer |  |  | 21 AUGUST 2020 | "24 June 2020 | AFTER 2ND ENGINEER |  | 03 AUGUST 2021 | 19822822
7 | AWALUDIN |  |  |  |  | AB I |  |  | 15 SEPTEMBER 2020 | AFTER RISKI WIBOWO |  | 15 SEPTEMBER 2021 |  | 19816081
8 | RISKI WIBOWO |  |  |  |  | AB II |  |  | 15 SEPTEMBER 2020 | AFTER COOK |  | 01 SEPTEMBER 2021 |  | 19822993
9 | BAYU TRI PRABOWO |  |  |  |  | Oiler |  |  | 21 AUGUST 2020 | 26 NOVEMBER 2020 |  | 28 JUNE 2021 |  | 19820179
10 | AMRAN BONE PASAU |  |  |  |  | COOK |  |  | 25 JUNE 2020 | 2020-11-26 |  | 22 JUNE 2021 |  | 19820178 |  |  | Level 2
Level 3
[18 empty] | RUN |  | Asst Exp Tanker/Assist Maintenance |  |  |  | Batam | 0:00
[18 empty] | STOP |  | Asst Exp Tanker/ to Berthing |  |  |  | Bayat
[20 empty] | Asst Exp Tanker/ to Unberthing |  |  |  | Belanak FPSO | 0:00
[20 empty] | Berthing/ Berthing |  |  |  | Belanak WHPA | 0:00
[20 empty] | Berthing/ Unberthing |  |  |  | Belanak WHPB | 0:00
[20 empty] | Bunker/ Transfer In |  |  |  | Belida DPPA
[20 empty] | Drop off/ Cargo |  |  |  | Kerisi
[20 empty] | Drop off/ Combination |  |  |  | Kabil
[20 empty] | Inspection |  |  |  | Matak
[20 empty] | Pick Up/ Meals |  |  |  | North Belut CPP
[20 empty] | Pick Up/ Pax |  |  |  | North Belut WHPC
[20 empty] | Pick and Drop/ Cargo |  |  |  | North Belut WHPD
[20 empty] | Pick and Drop/ Combination |  |  |  | OOB Belanak
[20 empty] | Pick and Drop / Meals |  |  |  | Sailing
[20 empty] | Sailing |  |  |  | Tanjung Uban
[20 empty] | Security Patrol |  |  |  | Belida DPPA Buoy
[20 empty] | Stand By/ Chopper |  |  |  | Belida WHPB Buoy
[20 empty] | Stand By/ Drifting |  |  |  | Belanak Spar Buoy
[20 empty] | Stand By/ Steaming |  |  |  | North Belut CPP Buoy
Stattic/ Towing
Vessel hire/ Vessel Offhire
Vessel hire / Vessel Onhire
Port Activity / Anchor
Port Activity / Loading Cargo
Port Activity / Unloading Cargo
Port Activity / Fresh water Bunker
Note on F11: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F12: Format: MM/DD/YY Example: 4/14/15
Note on O12: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on O13: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F14: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F15: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15

## Compatibility Report
Compatibility Report for DOL CONOCO 25 SEPTEMBER 2017.xls
Run on 9/25/2017 17:13
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 80 | Excel 97-2003