## Vessel daily report
BOAT ACTIVITIES DAILY REPORT FOR ASD ENC RHAYDEN - CALL SIGN : YDA6366
REPORTED DATE 14 DECEMBER 2019 | [12 empty] | POSITION : MUNTOK CST - BANGKA STRAIT
TIME | WINDS |  |  |  | SEA |  | SWELL |  |  |  |  | VISIBILITY | WEATHER CONDITION |  |  | ISPS Port Status
| DIR | SPEED
00:00 hrs | E | 05- 10 KNOT |  |  | CALM |  | 0.2 - 0.5 M |  |  |  |  | GOOD | CLAUDY |  |  | Level 1
VESSEL STATUS
Start Onhire Date |  |  |  | 31/01/2019 08:00:00 PM |  |  | Down Time |  |  |  |  | 0:00
Last Fuel Meter Calibration | [6 empty] | Start Time
Last Dry Docking | [6 empty] | Finish Time
Scheduled out of Service Start | [6 empty] | Reason
Scheduled out of Service End
|  |  |  | Running Hrs | FO Consumption |  | CONSUMABLES SUMMARY
[7 empty] | Fuel Oil | [7 empty] | Remarks
Main Engine |  |  |  | 0:00 | 0 | Liters | MDO Open stock | [5 empty] | 82932 | Liters
[7 empty] | MDO Received | [6 empty] | Liters
Auxiliary Engine No.1 |  |  |  | 0:00 | 0 | Liters | MDO Transferred | [6 empty] | Liters
Auxiliary Engine No.2 |  |  |  | 24.00 | 320 | Liters | ROB MDO | [5 empty] | 82612 | Liters
Auxiliary Engine No.3 |  |  |  | 0 |  | Liters | FW Open Stock | [5 empty] | 33700 | Liters
[7 empty] | FW Consumption | [5 empty] | 4000 | Liters
Bow Thruster |  |  |  | 0 |  | Liters | FW Received | [6 empty] | Liters
[7 empty] | FW Transferred | [6 empty] | Liters
FI - FI |  |  |  | 0 |  | Liters | ROB FW | [5 empty] | 29700 | Liters
|  | Total FO Consumption |  |  | 320 | Liters
VESSEL ACTIVITY DETAIL REPORT
HSE: | [7 empty] | CONTRACT NUMBER : |  |  |  | CS-17629760
Incident |  | : Nil | [5 empty] | CONTRACT OWNER : |  |  |  | CST OPERATION
I Care |  | : (Safe Cond) Deck Dept : Saat mengerjakan pemeliharaan dapra bagian linggi haluan menggunakan perahu untuk mengganti sling belt yang putus tidak ada crew yang standby di deck sebagai pengawas untuk membantu apa bila ada hal yang tidak diinginkan.By Samgar Arthur. | [5 empty] | LOCATION : |  |  |  | CONOCOPHILLIPS (GRISSIK) LTD - CST MUNTOK | [5 empty] | 1 hour | 0.041667
: (Safe Cond) Engine Dept : Crew engine rutin cleaning gudang spare part dan memakai PPE.By Misbak
Immediate Action Taken |  | : Nil
Near Miss |  | : Nil
Hazard Hunting |  | : Nil
Start | Finish | Main Engine Status | Auxiliary Engine No.1 | Auxiliary Engine No.2 | Auxiliary Engine No.3 | Bow Thruster | FI - FI | Remarks |  |  |  |  | Detail Activity |  |  | Location |  | Durations | Main Engine Status | Aux 1 | Aux 2 | Aux 3 | Bow | FI - FI
0 | 0.16667 |  |  | RUN |  |  |  | Tug standby anchor at Tg Kalian anchorage |  |  |  |  | Port Activity / Anchor
0.16667 | 0.33333 |  |  | RUN |  |  |  | Tug standby anchor at Tg Kalian anchorage |  |  |  |  | Port Activity / Anchor
0.33333 | 0.5 |  |  | RUN |  |  |  | Tug standby anchor at Tg Kalian anchorage |  |  |  |  | Port Activity / Anchor
0.5 | 0.66667 |  |  | RUN |  |  |  | Tug standby anchor at Tg Kalian anchorage |  |  |  |  | Port Activity / Anchor
0.66667 | 0.83333 |  |  | RUN |  |  |  | Tug standby anchor at Tg Kalian anchorage |  |  |  |  | Port Activity / Anchor
0.83333 | 1899-12-31 |  |  | RUN |  |  |  | Tug standby anchor at Tg Kalian anchorage |  |  |  |  | Port Activity / Anchor
STATUS SHIPS / CREW DOCUMENT TO BE EXPIRED NEXT MONTH | [6 empty] | MA / SATGAS ON BOARD
No | Name |  |  |  | Remark |  | No | Name
1 | Shifting Permit / SPOGK |  |  |  | Exp : 10 JANUARY 2020
QTY | STATUS COMMUNICATION EQUIPMENT |  |  |  | REMARK
1 | asd-rhayden@ekanuri.com |  |  |  | GOOD
2 | VHF |  |  |  | GOOD
6 | HT |  |  |  | GOOD
PERSONNEL ON BOARD
No. | Name |  |  |  |  | Position |  |  | Onboard Date | Estimate Sign off |  | MCU / Expired |  | PTS Number
1 | TAUFIK FAISAL |  |  |  |  | Master |  |  | 2019-11-27 | 2020-02-27 |  | 29 Oct 2020 |  | 19820365
2 | BAHKTIAR |  |  |  |  | Chief Officer |  |  | 04 Sept 2019 | 20 Dec 2019 |  | 07 Jan 2021 |  | 19822289
3 | SAMGAR ARTHUR RATUMBANUA |  |  |  |  | 2nd Officer |  |  | 09 Oct 2019 | 09 Jan 2020 |  | 16 Apr 2021 |  | 19816083
4 | RUNDI |  |  |  |  | Chief Engineer |  |  | 04 Sept 2019 | 20 Dec 2019 |  | 25 Apr 2021 |  | 19823281
5 | YONATHAN RAMBA |  |  |  |  | 2nd Engineer |  |  | 09 Oct 2019 | 09 Jan 2020 |  | 06 Sept 2020 |  | 19821563
6 | MISBAK |  |  |  |  | 3rd Engineer |  |  | 2019-11-27 |  | 2020-02-27 |  | 2021-02-04 | 19822822
7 | FERRY FIRMANTO |  |  |  |  | AB I |  |  | 2019-11-27 | 2020-02-27 |  | 2020-06-13 |  | 19820177 |  |  | Level 2
8 | ISHAK SUHERMAN |  |  |  |  | AB II |  |  | 11 Sept 2019 | 20 Des 2019 |  | 10 Apr 2021 |  | 19821095 |  |  | Level 3
9 | HASRUL GUNAWAN |  |  |  |  | Oiler |  |  | 11 Sept 2019 | 13 Des 2019 |  | 01 Augt 2021 |  | 19823732
10 | AMRAN BONE PASAU |  |  |  |  | Cook |  |  | 17 Oct 2019 | 17 Jan 2020 |  | 04 Dec 2020 |  | 19820178
[18 empty] | RUN |  | Asst Exp Tanker/Assist Maintenance |  |  |  | Batam | 0:00
[18 empty] | STOP |  | Asst Exp Tanker/ to Berthing |  |  |  | Bayat
[20 empty] | Asst Exp Tanker/ to Unberthing |  |  |  | Belanak FPSO | 0:00
[20 empty] | Berthing/ Berthing |  |  |  | Belanak WHPA | 24:00
[20 empty] | Berthing/ Unberthing |  |  |  | Belanak WHPB | 0:00
[20 empty] | Bunker/ Transfer In |  |  |  | Belida DPPA
[20 empty] | Drop off/ Cargo |  |  |  | Kerisi
[20 empty] | Drop off/ Combination |  |  |  | Kabil
[20 empty] | Inspection |  |  |  | Matak
[20 empty] | Pick Up/ Meals |  |  |  | North Belut CPP
[20 empty] | Pick Up/ Pax |  |  |  | North Belut WHPC
[20 empty] | Pick and Drop/ Cargo |  |  |  | North Belut WHPD
[20 empty] | Pick and Drop/ Combination |  |  |  | OOB Belanak
[20 empty] | Pick and Drop / Meals |  |  |  | Sailing
[20 empty] | Sailing |  |  |  | Tanjung Uban
[20 empty] | Security Patrol |  |  |  | Belida DPPA Buoy
[20 empty] | Stand By/ Chopper |  |  |  | Belida WHPB Buoy
[20 empty] | Stand By/ Drifting |  |  |  | Belanak Spar Buoy
[20 empty] | Stand By/ Steaming |  |  |  | North Belut CPP Buoy
Stattic/ Towing
Vessel hire/ Vessel Offhire
Vessel hire / Vessel Onhire
Port Activity / Anchor
Port Activity / Loading Cargo
Port Activity / Unloading Cargo
Port Activity / Fresh water Bunker
Note on F11: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F12: Format: MM/DD/YY Example: 4/14/15
Note on O12: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on O13: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F14: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F15: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15

## Compatibility Report
Compatibility Report for DOL CONOCO 25 SEPTEMBER 2017.xls
Run on 9/25/2017 17:13
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 80 | Excel 97-2003