## Vessel daily report
BOAT ACTIVITIES DAILY REPORT FOR ASD ENC RHAYDEN - CALL SIGN : YDA6366
REPORTED DATE 27 SEPTEMBER 2020 | [12 empty] | POSITION : MUNTOK CST - BANGKA STRAIT
TIME | WINDS |  |  |  | SEA |  | SWELL |  |  |  |  | VISIBILITY | WEATHER CONDITION |  |  | ISPS Port Status
| DIR | SPEED
00:00 hrs | SE | 05 - 10 KNOTS |  |  | SMOOTH |  | 0,0 -0,5 M |  |  |  |  | GOOD | CLAUDY |  |  | Level 1
VESSEL STATUS
Start Onhire Date |  |  |  | 31/01/2019 08:00:00 PM |  |  | Down Time |  |  |  |  | 0:00
Last Fuel Meter Calibration | [6 empty] | Start Time
Last Dry Docking | [6 empty] | Finish Time
Scheduled out of Service Start | [6 empty] | Reason
Scheduled out of Service End
|  |  |  | Running Hrs | FO Consumption |  | CONSUMABLES SUMMARY
[7 empty] | Fuel Oil | [7 empty] | Remarks
Main Engine |  |  |  | 5:12 | 1664 | Liters | MDO Open stock | [5 empty] | 38477 | Liters
[7 empty] | MDO Received | [6 empty] | Liters
Auxiliary Engine No.1 |  |  |  | 0:00 | 0 | Liters | MDO Transferred | [6 empty] | Liters
Auxiliary Engine No.2 |  |  |  | 24.00 | 320 | Liters | ROB MDO | [5 empty] | 36493 | Liters
Auxiliary Engine No.3 |  |  |  | 0 |  | Liters | FW Open Stock | [5 empty] | 35400 | Liters
[7 empty] | FW Consumption | [5 empty] | 4000 | Liters
Bow Thruster |  |  |  | 0 |  | Liters | FW Received | [6 empty] | Liters
[7 empty] | FW Transferred | [6 empty] | Liters
FI - FI |  |  |  | 0 |  | Liters | ROB FW | [5 empty] | 31400 | Liters
|  | Total FO Consumption |  |  | 1984 | Liters
VESSEL ACTIVITY DETAIL REPORT
HSE: | [7 empty] | CONTRACT NUMBER : |  |  |  | CS-17629760
Incident |  | : Nil | [5 empty] | CONTRACT OWNER : |  |  |  | CST OPERATION
I Care |  | : (Safe Cond) Deck Dept : Proses assist berthing SPOB Musi Prosperity Prosperity berjalan aman, Crew yang bertugas di Deck memakai PPE dan bebas dari Snab back zona.By Taufik Faisal. | [5 empty] | LOCATION : |  |  |  | CONOCOPHILLIPS (GRISSIK) LTD - CST MUNTOK | [5 empty] | 1 hour | 0.041667
: (Safe Cond) Engine Dept : Crew enginbe Standby di ruang mesin minimal 2 (Dua) orang pada saat kapal operasional untuk saling membantu dan mengawasi keselamatan dan keamanan.By Yonathan R.
Immediate Action Taken |  | : Nil
Near Miss |  | : Nil
Hazard Hunting |  | : Nil
Start | Finish | Main Engine Status | Auxiliary Engine No.1 | Auxiliary Engine No.2 | Auxiliary Engine No.3 | Bow Thruster | FI - FI | Remarks |  |  |  |  | Detail Activity |  |  | Location |  | Durations | Main Engine Status | Aux 1 | Aux 2 | Aux 3 | Bow | FI - FI
0 | 0.16667 |  | RUN |  |  |  |  | Tug standby along side at port side CST Ship 111 |  |  |  |  | Berthing/ Unberthing
0.16667 | 0.22917 |  | RUN |  |  |  |  | Tug standby along side at port side CST Ship 111 |  |  |  |  | Berthing/ Unberthing
0.22917 | 0.25 | RUN | RUN |  |  |  |  | SBE, Prepare assist Berthing SPOB Musi Prosperity |  |  |  |  | Berthing/ Unberthing
0.25 | 0.27431 | RUN | RUN |  |  |  |  | Cast off from CST Ship 111, Process to SPOB Musi Prosperity |  |  |  |  | Asst Exp Tanker/ to Berthing
0.27431 | 0.30556 | RUN | RUN |  |  |  |  | Arrival at SPOB Musi Prosperity, Connect tug line assist Berthing |  |  |  |  | Asst Exp Tanker/ to Berthing
0.30556 | 0.32292 | RUN | RUN |  |  |  |  | Disconnect tug line, process pick up passenger from zona 500 meters at Boat |  |  |  |  | Pick Up/ Pax
0.32292 | 0.33333 | RUN | RUN |  |  |  |  | Pasenger on board, process drop to SPOB Musi Prosperity |  |  |  |  | Pick Up/ Pax
0.33333 | 0.34028 | RUN | RUN |  |  |  |  | Finish drop passenger at SPOB Musi Prosperity, process to aft CST Ship 111 |  |  |  |  | Berthing/ Unberthing
0.34028 | 0.34722 | RUN | RUN |  |  |  |  | Arrival aft CST Ship 111, Process connect tug line tide up |  |  |  |  | Berthing/ Unberthing
0.34722 | 0.35069 | RUN | RUN |  |  |  |  | Tug line tide up secure |  |  |  |  | Berthing/ Unberthing
0.35069 | 0.35417 |  | RUN |  |  |  |  | F.W.E. |  |  |  |  | Berthing/ Unberthing
0.35417 | 0.5 |  | RUN |  |  |  |  | Tug standby tide at aft CST Ship 111 |  |  |  |  | Berthing/ Unberthing
0.5 | 0.66667 |  | RUN |  |  |  |  | Tug standby tide at aft CST Ship 111 |  |  |  |  | Berthing/ Unberthing
0.66667 | 0.6875 | RUN | RUN |  |  |  |  | SBE, Prepare assist Unberthing SPOB Musi Prosperity |  |  |  |  | Asst Exp Tanker/ to Unberthing
0.6875 | 0.69444 | RUN | RUN |  |  |  |  | Disconnect tug line tide up, Process to SPOB Musi Prosperity |  |  |  |  | Asst Exp Tanker/ to Unberthing
0.69444 | 0.74306 | RUN | RUN |  |  |  |  | Arrival at SPOB Musi prosperity, Connect tug line assist Unberthing |  |  |  |  | Asst Exp Tanker/ to Unberthing
0.74306 | 0.75 | RUN | RUN |  |  |  |  | Disconnect tug line, Proces To aft side CST Ship 111 |  |  |  |  | Berthing/ Unberthing
0.75 | 0.75417 | RUN | RUN |  |  |  |  | Arrival aft CST Ship 111, process connect tug line tide up |  |  |  |  | Berthing/ Unberthing
0.75417 | 0.75694 | RUN | RUN |  |  |  |  | Tug line tide up secure |  |  |  |  | Berthing/ Unberthing
0.75694 | 0.75833 |  | RUN |  |  |  |  | F.W.E. |  |  |  |  | Berthing/ Unberthing
0.75833 | 0.83333 |  | RUN |  |  |  |  | Tug standby tide at aft CST Ship 111 |  |  |  |  | Berthing/ Unberthing
0.83333 | 1899-12-31 |  | RUN |  |  |  |  | Tug standby tide at aft CST Ship 111 |  |  |  |  | Berthing/ Unberthing
STATUS SHIPS / CREW DOCUMENT TO BE EXPIRED NEXT MONTH | [6 empty] | MA / SATGAS ON BOARD
No | Name |  |  |  | Remark |  | No | Name
1 | Shifting Permit / SPOGK |  |  |  | Exp : 13 OCTOBER 2020
2 | Certicate Fire Extinguishers |  |  |  | Exp : 23 OCTOBER 2020
3 | Cerftificate Inlatable Life Raft |  |  |  | Exp : 23 OCTOBER 2020
QTY | STATUS COMMUNICATION EQUIPMENT |  |  |  | REMARK
1 | asd-rhayden@ekanuri.com |  |  |  | GOOD
2 | VHF |  |  |  | GOOD
6 | HT |  |  |  | GOOD
PERSONNEL ON BOARD
No. | Name |  |  |  |  | Position |  |  | Onboard Date | Estimate Sign off |  | MCU / Expired |  | PTS Number
1 | TAUFIK FAISAL |  |  |  |  | Master |  |  | 21 AUGUST 2020 | 26 NOVEMBER 2020 |  | 29 OCKTOBER 2020 |  | 19821581
2 | BAHKTIAR |  |  |  |  | Chief Officer |  |  | 2020-04-01 | 01 OCKTOBER 2020 |  | 10 JANUARY 2021 |  | 19822289
3 | SAMGAR ARTHUR |  |  |  |  | 2nd Officer |  |  | 25 JUNE 2020 | After C/O |  | 19 JUNE 2021 |  | 19816083
4 | RUNDI |  |  |  |  | Chief Engineer |  |  | 2020-04-02 | 01 OCKTOBER 2020 |  | 30 MARCH 2021 |  | 19823281
5 | YONATHAN RAMBA |  |  |  |  | 2nd Engineer |  |  | 25 JUNE 2020 | AFTER CH. ENGINEER |  | 19 JUNE 2021 |  | 19821563
6 | MISBAK |  |  |  |  | 3rd Engineer |  |  | 21 AUGUST 2020 | "24 June 2020 | AFTER 2ND ENGINEER |  | 03 AUGUST 2021 | 19822822
7 | ISHAK SUHERMAN |  |  |  |  | AB I |  |  | 11 MARCH 2020 | 22 OCTOBER 2020 |  | 21 FEBRUARY 2021 |  | 19821095
8 | RISKI WIBOWO |  |  |  |  | AB II |  |  | 15 SEPTEMBER 2020 | 15 DECEMBER 2020 |  | 01 SEPTEMBER 2021 |  | 19822993
9 | BAYU TRI PRABOWO |  |  |  |  | Oiler |  |  | 21 AUGUST 2020 | 26 NOVEMBER 2020 |  | 28 JUNE 2021 |  | 19820179 |  |  | Level 2
10 | AMRAN BONE PASAU |  |  |  |  | COOK |  |  | 25 JUNE 2020 | AFTER ISHAK SUHERMAN (AB) |  | 22 JUNE 2021 |  | 19820178 |  |  | Level 3
[18 empty] | RUN |  | Asst Exp Tanker/Assist Maintenance |  |  |  | Batam | 5:05
[18 empty] | STOP |  | Asst Exp Tanker/ to Berthing |  |  |  | Bayat
[20 empty] | Asst Exp Tanker/ to Unberthing |  |  |  | Belanak FPSO | 24:00
[20 empty] | Berthing/ Berthing |  |  |  | Belanak WHPA | 0:00
[20 empty] | Berthing/ Unberthing |  |  |  | Belanak WHPB | 0:00
[20 empty] | Bunker/ Transfer In |  |  |  | Belida DPPA
[20 empty] | Drop off/ Cargo |  |  |  | Kerisi
[20 empty] | Drop off/ Combination |  |  |  | Kabil
[20 empty] | Inspection |  |  |  | Matak
[20 empty] | Pick Up/ Meals |  |  |  | North Belut CPP
[20 empty] | Pick Up/ Pax |  |  |  | North Belut WHPC
[20 empty] | Pick and Drop/ Cargo |  |  |  | North Belut WHPD
[20 empty] | Pick and Drop/ Combination |  |  |  | OOB Belanak
[20 empty] | Pick and Drop / Meals |  |  |  | Sailing
[20 empty] | Sailing |  |  |  | Tanjung Uban
[20 empty] | Security Patrol |  |  |  | Belida DPPA Buoy
[20 empty] | Stand By/ Chopper |  |  |  | Belida WHPB Buoy
[20 empty] | Stand By/ Drifting |  |  |  | Belanak Spar Buoy
[20 empty] | Stand By/ Steaming |  |  |  | North Belut CPP Buoy
Stattic/ Towing
Vessel hire/ Vessel Offhire
Vessel hire / Vessel Onhire
Port Activity / Anchor
Port Activity / Loading Cargo
Port Activity / Unloading Cargo
Port Activity / Fresh water Bunker
Note on F11: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F12: Format: MM/DD/YY Example: 4/14/15
Note on O12: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on O13: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F14: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F15: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15

## Compatibility Report
Compatibility Report for DOL CONOCO 25 SEPTEMBER 2017.xls
Run on 9/25/2017 17:13
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 80 | Excel 97-2003