## Vessel daily report
BOAT ACTIVITIES DAILY REPORT FOR ASD ENC RHAYDEN - CALL SIGN : YDA6366
REPORTED DATE 29 DESEMBER 2020 | [12 empty] | POSITION : MUNTOK CST - BANGKA STRAIT
TIME | WINDS |  |  |  | SEA |  | SWELL |  |  |  |  | VISIBILITY | WEATHER CONDITION |  |  | ISPS Port Status
| DIR | SPEED
00:00 hrs | SE | 10 - 12 KNOTS |  |  | SLIGHT |  | 0,5 - 1,0 M |  |  |  |  | GOOD | CLAUDY |  |  | Level 1
VESSEL STATUS
Start Onhire Date |  |  |  | 24/10/2020 16:30:00 PM |  |  | Down Time 02/10/2020 18:00:00 PM |  |  |  |  | 0:00
Last Fuel Meter Calibration | [6 empty] | Start Time
Last Dry Docking | [6 empty] | Finish Time
Scheduled out of Service Start | [6 empty] | Reason
Scheduled out of Service End
|  |  |  | Running Hrs | FO Consumption |  | CONSUMABLES SUMMARY
[7 empty] | Fuel Oil | [7 empty] | Remarks
Main Engine |  |  |  | 2:00 | 640 | Liters | MDO Open stock | [5 empty] | 54425 | Liters
[7 empty] | MDO Received | [6 empty] | Liters
Auxiliary Engine No.1 |  |  |  | 24:00 | 320 | Liters | MDO Transferred | [6 empty] | Liters
Auxiliary Engine No.2 |  |  |  | 0:00 | 0 | Liters | ROB MDO | [5 empty] | 53465 | Liters
Auxiliary Engine No.3 |  |  |  | 0 | 0 | Liters | FW Open Stock | [5 empty] | 26100 | Liters
[7 empty] | FW Consumption | [5 empty] | 3000 | Liters
Bow Thruster |  |  |  | 0 |  | Liters | FW Received | [6 empty] | Liters
[7 empty] | FW Transferred | [6 empty] | Liters
FI - FI |  |  |  | 0 |  | Liters | ROB FW | [5 empty] | 23100 | Liters
|  | Total FO Consumption |  |  | 960 | Liters
VESSEL ACTIVITY DETAIL REPORT
HSE: | [7 empty] | CONTRACT NUMBER : |  |  |  | CS-17629760
Incident |  | : Nil | [5 empty] | CONTRACT OWNER : |  |  |  | CST OPERATION
I Care |  | : (Safe Cond) Deck Dept : | [5 empty] | LOCATION : |  |  |  | CONOCOPHILLIPS (GRISSIK) LTD - CST MUNTOK | [5 empty] | 1 hour | 0.041667
: (Safe Cond) Engine Dept :
Immediate Action Taken |  | : Nil
Near Miss |  | : Nil
Hazard Hunting |  | : Nil
Start | Finish | Main Engine Status | Auxiliary Engine No.1 | Auxiliary Engine No.2 | Auxiliary Engine No.3 | Bow Thruster | FI - FI | Remarks |  |  |  |  | Detail Activity |  |  | Location |  | Durations | Main Engine Status | Aux 1 | Aux 2 | Aux 3 | Bow | FI - FI
00:00 | 0.083333 |  | RUN |  |  |  |  | Tug Standby tide up aft CST Ship III |  |  |  |  | Berthing/ Unberthing
0.083333 | 0.125 | RUN | RUN |  |  |  |  | SBE, Reposition back straight aft CST Ship III |  |  |  |  | Berthing/ Unberthing
0.125 | 0.13333 |  | RUN |  |  |  |  | FWE, Finish reposition |  |  |  |  | Berthing/ Unberthing
0.13333 | 0.16667 |  | RUN |  |  |  |  | Tug Standby tide up aft CST Ship III |  |  |  |  | Berthing/ Unberthing
0.16667 | 0.33333 |  | RUN |  |  |  |  | Tug Standby tide up aft CST Ship III |  |  |  |  | Berthing/ Unberthing
0.33333 | 0.5 |  | RUN |  |  |  |  | Tug Standby tide up aft CST Ship III |  |  |  |  | Berthing/ Unberthing
0.5 | 0.66667 |  | RUN |  |  |  |  | Tug Standby tide up aft CST Ship III |  |  |  |  | Berthing/ Unberthing
0.66667 | 0.76667 |  | RUN |  |  |  |  | Tug Standby tide up aft CST Ship III |  |  |  |  | Berthing/ Unberthing
0.76667 | 0.77431 | RUN | RUN |  |  |  |  | SBE, Prepare shifting from aft to port side CST Ship III to PJSM Lifting |  |  |  |  | Berthing/ Unberthing
0.77431 | 0.78125 | RUN | RUN |  |  |  |  | Disconnect tug line tide up, process to port side CST Ship III |  |  |  |  | Berthing/ Unberthing
0.78125 | 0.79167 | RUN | RUN |  |  |  |  | Arrival at port side CST Ship III, Process along side at S Anna |  |  |  |  | Berthing/ Unberthing
0.79167 | 0.79861 | RUN | RUN |  |  |  |  | Finish along side |  |  |  |  | Berthing/ Unberthing
0.79861 | 0.8 |  | RUN |  |  |  |  | FWE |  |  |  |  | Berthing/ Unberthing
0.8 | 0.83333 |  | RUN |  |  |  |  | Tug Standby along side at S Anna |  |  |  |  | Berthing/ Unberthing
0.83333 | 1899-12-31 |  | RUN |  |  |  |  | Tug Standby along side at S Anna |  |  |  |  | Berthing/ Unberthing
STATUS SHIPS / CREW DOCUMENT TO BE EXPIRED NEXT MONTH | [6 empty] | MA / SATGAS ON BOARD
No | Name |  |  |  | Remark |  | No | Name
1 | Shifting Permit / SPOGK |  |  |  | Exp : 21 JANUARY 2021
QTY | STATUS COMMUNICATION EQUIPMENT |  |  |  | REMARK
1 | asd-rhayden@ekanuri.com |  |  |  | GOOD
2 | VHF |  |  |  | GOOD
6 | HT |  |  |  | GOOD
PERSONNEL ON BOARD
No. | Name |  |  |  |  | Position |  |  | Onboard Date | Estimate Sign off |  | MCU / Expired |  | PTS Number
1 | PURWANDOYO |  |  |  |  | Master |  |  | 23 OCTOBER 2020 | AFTER CH OFFICER |  | 15 OCKTOBER 2021 |  | 19820365
2 | BAHKTIAR |  |  |  |  | Chief Officer |  |  | 2020-12-18 | AFTER MASTER |  | 07 JUNE 2021 |  | 19822289
3 | B.LOIS MANGALIK |  |  |  |  | 2nd Officer |  |  | 2020-10-24 | AFTER 2ND OFFICER |  | 21 OCTOBER 2021 |  | 19827309
4 | DIAN APRIZAL |  |  |  |  | Chief Engineer |  |  | 2020-10-23 | AFTER 3RD ENGINEER |  | 05 OCTOBER 2021 |  | 19820757
5 | ASMADI |  |  |  |  | 2nd Engineer |  |  | 10 Desember 2020 | AFTER Ch ENGINEER |  | 21 OKTOBER 2021 |  | 19821563
6 | MISBAK |  |  |  |  | 3rd Engineer |  |  | 21 AUGUST 2020 | "24 June 2020 | AFTER 2ND ENGINEER |  | 03 AUGUST 2021 | 19822822
7 | AWALUDIN |  |  |  |  | AB I |  |  | 15 SEPTEMBER 2020 | AFTER RISKI WIBOWO |  | 15 SEPTEMBER 2021 |  | 19816081
8 | RISKI WIBOWO |  |  |  |  | AB II |  |  | 15 SEPTEMBER 2020 | AFTER COOK |  | 01 SEPTEMBER 2021 |  | 19822993
9 | HASRUL GUNAWAN |  |  |  |  | Oiler |  |  | 10 Desember 2020 | 10 Maret 2021 |  | 30 Maret 2021 |  | 19823732
10 | AMRAN BONE PASAU |  |  |  |  | COOK |  |  | 25 JUNE 2020 | 2021-01-15 |  | 22 JUNE 2021 |  | 19820178 |  |  | Level 2
Level 3
[18 empty] | RUN |  | Asst Exp Tanker/Assist Maintenance |  |  |  | Batam | 1:46
[18 empty] | STOP |  | Asst Exp Tanker/ to Berthing |  |  |  | Bayat
[20 empty] | Asst Exp Tanker/ to Unberthing |  |  |  | Belanak FPSO | 24:00
[20 empty] | Berthing/ Berthing |  |  |  | Belanak WHPA | 0:00
[20 empty] | Berthing/ Unberthing |  |  |  | Belanak WHPB | 0:00
[20 empty] | Bunker/ Transfer In |  |  |  | Belida DPPA
[20 empty] | Drop off/ Cargo |  |  |  | Kerisi
[20 empty] | Drop off/ Combination |  |  |  | Kabil
[20 empty] | Inspection |  |  |  | Matak
[20 empty] | Pick Up/ Meals |  |  |  | North Belut CPP
[20 empty] | Pick Up/ Pax |  |  |  | North Belut WHPC
[20 empty] | Pick and Drop/ Cargo |  |  |  | North Belut WHPD
[20 empty] | Pick and Drop/ Combination |  |  |  | OOB Belanak
[20 empty] | Pick and Drop / Meals |  |  |  | Sailing
[20 empty] | Sailing |  |  |  | Tanjung Uban
[20 empty] | Security Patrol |  |  |  | Belida DPPA Buoy
[20 empty] | Stand By/ Chopper |  |  |  | Belida WHPB Buoy
[20 empty] | Stand By/ Drifting |  |  |  | Belanak Spar Buoy
[20 empty] | Stand By/ Steaming |  |  |  | North Belut CPP Buoy
Stattic/ Towing
Vessel hire/ Vessel Offhire
Vessel hire / Vessel Onhire
Port Activity / Anchor
Port Activity / Loading Cargo
Port Activity / Unloading Cargo
Port Activity / Fresh water Bunker
Note on F11: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F12: Format: MM/DD/YY Example: 4/14/15
Note on O12: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on O13: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F14: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F15: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15

## Compatibility Report
Compatibility Report for DOL CONOCO 25 SEPTEMBER 2017.xls
Run on 9/25/2017 17:13
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 80 | Excel 97-2003