## Vessel daily report
BOAT ACTIVITIES DAILY REPORT FOR ASD ENC RHAYDEN - CALL SIGN : YDA6366
REPORTED DATE 26 AUGUST 2019 | [11 empty] | POSITION : MUNTOK CST - BANGKA STRAIT
TIME | WINDS |  |  |  | SEA |  | SWELL |  |  |  | VISIBILITY | WEATHER CONDITION |  |  | ISPS Port Status
| DIR | SPEED
00:00 hrs | SE | 7 - 9 KNOT |  |  | SLIGHT |  | 0.5 - 1.0 M |  |  |  | GOOD | CLAUDY |  |  | Level 1
VESSEL STATUS
Start Onhire Date |  |  |  | 31/01/2019 08:00:00 PM |  |  | Down Time |  |  |  | 0:00
Last Fuel Meter Calibration | [6 empty] | Start Time
Last Dry Docking | [6 empty] | Finish Time
Scheduled out of Service Start | [6 empty] | Reason
Scheduled out of Service End
|  |  |  | Running Hrs | FO Consumption |  | CONSUMABLES SUMMARY
[7 empty] | Fuel Oil | [6 empty] | Remarks
Main Engine |  |  |  | 3:00 | 960 | Liters | MDO Open stock |  |  |  |  | 68851 | Liters
[7 empty] | MDO Received | [5 empty] | Liters
Auxiliary Engine No.1 |  |  |  | 0:00 | 0 | Liters | MDO Transferred | [5 empty] | Liters
Auxiliary Engine No.2 |  |  |  | 24.00 | 320 | Liters | ROB MDO |  |  |  |  | 67571 | Liters
Auxiliary Engine No.3 |  |  |  | 0 |  | Liters | FW Open Stock |  |  |  |  | 20700 | Liters
[7 empty] | FW Consumption |  |  |  |  | 4000 | Liters
Bow Thruster |  |  |  | 0 |  | Liters | FW Received | [5 empty] | Liters
[7 empty] | FW Transferred | [5 empty] | Liters
FI - FI |  |  |  | 0 |  | Liters | ROB FW |  |  |  |  | 16700 | Liters
|  | Total FO Consumption |  |  | 1280 | Liters
VESSEL ACTIVITY DETAIL REPORT
HSE: | [7 empty] | CONTRACT NUMBER : |  |  | CS-17629760
Incident |  | : Nil | [5 empty] | CONTRACT OWNER : |  |  | CST OPERATION
I Care |  | : (Safe Cond) Deck Dept : Proses pengangkatan spare part mesin dari jetty ke kapal menggunakan deck crane berjalan aman karena crew menjalankan prosedur yang benar. By Awaludin | [5 empty] | LOCATION : |  |  | CONOCOPHILLIPS (GRISSIK) LTD - CST MUNTOK | [5 empty] | 1 hour | 0.041667
: (Safe Cond) Engine Dept : Kerjasama antara crew deck dan crew mesin terlihat kompak, sehingga setiap kegiatan berjalan aman dan lancar. By Dian Aprizal
Immediate Action Taken |  | : Nil
Near Miss |  | : Nil
Hazard Hunting |  | : Nil
Start | Finish | Main Engine Status | Auxiliary Engine No.1 | Auxiliary Engine No.2 | Auxiliary Engine No.3 | Bow Thruster | FI - FI | Remarks |  |  |  | Detail Activity |  |  | Location |  | Durations | Main Engine Status | Aux 1 | Aux 2 | Aux 3 | Bow | FI - FI
0:00 | 0.16667 |  |  | RUN |  |  |  | Tug still continue standby, drop anchor at Muntok area |  |  |  | Port Activity / Anchor
0.16667 | 0.33333 |  |  | RUN |  |  |  | Tug still continue standby, drop anchor at Muntok area |  |  |  | Port Activity / Anchor
0.33333 | 0.45833 |  |  | RUN |  |  |  | Tug still continue standby, drop anchor at Muntok area |  |  |  | Port Activity / Anchor
0.45833 | 0.4625 | RUN |  | RUN |  |  |  | SBE to jetty for pick up spare part engine |  |  |  | Berthing/ Unberthing
0.4625 | 0.47222 | RUN |  | RUN |  |  |  | Anchor up, move to jetty |  |  |  | Berthing/ Unberthing
0.47222 | 0.49306 | RUN |  | RUN |  |  |  | Arrival jetty, continue pick up spare part |  |  |  | Berthing/ Unberthing
0.49306 | 0.53472 | RUN |  | RUN |  |  |  | Clear pick up spare part, back to anchorage |  |  |  | Port Activity / Loading Cargo
0.53472 | 0.57639 | RUN |  | RUN |  |  |  | Clear drop anchor |  |  |  | Port Activity / Anchor
0.57639 | 0.58333 |  |  | RUN |  |  |  | F.W.E |  |  |  | Port Activity / Anchor
0.58333 | 0.66667 |  |  | RUN |  |  |  | Tug still continue standby, drop anchor at Muntok area |  |  |  | Port Activity / Anchor
0.66667 | 0.83333 |  |  | RUN |  |  |  | Tug still continue standby, drop anchor at Muntok area |  |  |  | Port Activity / Anchor
0.83333 | 1899-12-31 |  |  | RUN |  |  |  | Tug still continue standby, drop anchor at Muntok area |  |  |  | Port Activity / Anchor
STATUS SHIPS / CREW DOCUMENT TO BE EXPIRED NEXT MONTH | [6 empty] | MA / SATGAS ON BOARD
No | Name |  |  |  | Remark |  | No | Name
1 | Shifting Permit |  |  |  | Exp : 12 Sept 2019
QTY | STATUS COMMUNICATION EQUIPMENT |  |  |  | REMARK
1 | asd-rhayden@ekanuri.com |  |  |  | GOOD
2 | VHF |  |  |  | GOOD
6 | HT |  |  |  | GOOD
PERSONNEL ON BOARD
No. | Name |  |  |  |  | Position |  |  | Onboard Date | Estimate Sign off | MCU / Expired |  | PTS Number
1 | TAUFIK FAISAL |  |  |  |  | Master |  |  | 12 June 2019 | 12 Sept 2019 | 29 Nov 2020 |  | 19821581
3 | PURWANDOYO |  |  |  |  | Chief Officer |  |  | 17 July 2019 | 17 Oct 2019 | 09 July 2021 |  | 19820365
3 | SAMGAR ARTHUR RATUMBANUA |  |  |  |  | 2nd Officer |  |  | 01 May 2019 | 04 Sept 2019 | 16 Apr 2021 |  | 19816083
4 | DIAN APRIZAL |  |  |  |  | Chief Engineer |  |  | 01 Augt 2019 | 01 Nov 2019 | 05 July 2021 |  | 19820757
5 | YONATHAN RAMBA |  |  |  |  | 2nd Engineer |  |  | 29 May 2019 | 04 Sept 2019 | 04 Sep 2020 |  | 19821563
6 | MISBAK |  |  |  |  | 3rd Engineer |  |  | 02 July 2019 | 02 Oct 2019 | 04 Feb 2021 |  | 19822822
7 | FERRY FIRMANTO |  |  |  |  | AB I |  |  | 02 July 2019 | 02 Oct 2019 | 13 June 2021 |  | 19820177 |  |  | Level 2
8 | AWALUDIN |  |  |  |  | AB II |  |  | 01 Augt 2019 | 01 Nov 2019 | 2021-02-22 |  | 19816081 |  |  | Level 3
9 | BAYU TRI PRABOWO |  |  |  |  | OILER |  |  | 01 May 2019 | 28 Augt 2019 | 24 Apr 2021 |  | 19820179
10 | AMRAN BONE PASAU |  |  |  |  | COOK |  |  | 22 May 2019 | 04 Sept 2019 | 04 Dec 2020 |  | 19820178
[17 empty] | RUN |  | Asst Exp Tanker/Assist Maintenance |  |  |  | Batam | 2:50
[17 empty] | STOP |  | Asst Exp Tanker/ to Berthing |  |  |  | Bayat
[19 empty] | Asst Exp Tanker/ to Unberthing |  |  |  | Belanak FPSO | 0:00
[19 empty] | Berthing/ Berthing |  |  |  | Belanak WHPA | 24:00
[19 empty] | Berthing/ Unberthing |  |  |  | Belanak WHPB | 0:00
[19 empty] | Bunker/ Transfer In |  |  |  | Belida DPPA
[19 empty] | Drop off/ Cargo |  |  |  | Kerisi
[19 empty] | Drop off/ Combination |  |  |  | Kabil
[19 empty] | Inspection |  |  |  | Matak
[19 empty] | Pick Up/ Meals |  |  |  | North Belut CPP
[19 empty] | Pick Up/ Pax |  |  |  | North Belut WHPC
[19 empty] | Pick and Drop/ Cargo |  |  |  | North Belut WHPD
[19 empty] | Pick and Drop/ Combination |  |  |  | OOB Belanak
[19 empty] | Pick and Drop / Meals |  |  |  | Sailing
[19 empty] | Sailing |  |  |  | Tanjung Uban
[19 empty] | Security Patrol |  |  |  | Belida DPPA Buoy
[19 empty] | Stand By/ Chopper |  |  |  | Belida WHPB Buoy
[19 empty] | Stand By/ Drifting |  |  |  | Belanak Spar Buoy
[19 empty] | Stand By/ Steaming |  |  |  | North Belut CPP Buoy
Stattic/ Towing
Vessel hire/ Vessel Offhire
Vessel hire / Vessel Onhire
Port Activity / Anchor
Port Activity / Loading Cargo
Port Activity / Unloading Cargo
Port Activity / Fresh water Bunker
Note on F11: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F12: Format: MM/DD/YY Example: 4/14/15
Note on O12: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on O13: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F14: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on F15: Format: MM/DD/YY_hh:mm Example: 4/14/15 13:15
Note on B38: Format: hh:mm Example: 13:01

## Compatibility Report
Compatibility Report for DOL CONOCO 25 SEPTEMBER 2017.xls
Run on 9/25/2017 17:13
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 80 | Excel 97-2003