## 08-11
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 08 November, 2019 |  |  |  | Location (Midnight) |  |  |  | Cinta Terminal ( SPM export ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT Mitra Anugerah 32 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI/SAMUDERA INDO
Contract No. | [7 empty] | Master Name |  |  |  | ANDI MUHAMMAD AMRI |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 8 |  | / |  | Person | 0 | 0.05 | [8 empty] | 0.05 | standby di SBM export.
[17 empty] | 0.05 | 0.24167 |  |  | 0.17083 | 0.016667 |  | 0.0041667 |  |  |  | tahan posisi kapal menjauh dari hose,arus dan angin berlawanan.
WEATHER CONDITION | [16 empty] | 0.24167 | 0.3125 | [8 empty] | 0.070833 | standby di SBM export.
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.3125 | 0.3375 |  |  | 0.016667 | 0.0041667 |  | 0.0041667 |  |  |  | lepas tali jemput crew mega 5 - 114
Wind (Dir/speed) |  |  |  | W 15-24 Knot |  |  | W 15-24 Knot |  |  | W 1,0-12 Knot |  |  |  | W 16-20Knot |  |  | 0.3375 | 0.35417 |  |  | 0.0041667 | 0.0083333 |  | 0.0041667 |  |  |  | pic up 2 orang dari briliance - -114
Sea (Wave Height) |  |  |  | sling sea / 1.0-2.0 m |  |  | sling sea / 1.0-2.0 m |  |  | Sling sea / 1.0-1.5 m |  |  |  | Moderate sea/ 1.0.-1.5 m |  |  | 0.35417 | 0.37083 |  |  | 0.0083333 | 0.0041667 |  | 0.0041667 |  |  |  | 114 - ina p1,ikat di belakang.
Visibility | [16 empty] | 0.37083 | 0.47917 | [8 empty] | 0.10833 | standby di belakang ina p1.
[17 empty] | 0.47917 | 0.525 |  |  | 0.0375 | 0.0041667 |  | 0.0041667 |  |  |  | tool box mitting.
HSSE | [16 empty] | 0.525 | 0.5375 | [8 empty] | 0.0125 | MA 32 gantung di belakang ina p1.
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.5375 | 0.57917 |  |  | 0.033333 | 0.0041667 |  | 0.0041667 |  |  |  | jemput makanan di kanan belakang 114.
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.57917 | 0.60833 |  |  | 0.020833 | 0.0041667 |  | 0.0041667 |  |  |  | surveillance dari SBM storage - SBM export.
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.60833 | 0.75833 |  |  | 0.125 | 0.016667 |  | 0.0083333 |  |  |  | MA 32 lanjut conex di cross oper.
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.75833 | 0.7875 |  |  | 0.020833 | 0.0041667 |  | 0.0041667 |  |  |  | MA 32,lepas dari cross oper.
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.7875 | 0.8 |  |  | 0.0041667 | 0.0041667 |  | 0.0041667 |  |  |  | MA 32,servis mooring line dn stanby di posisi mooring line.
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.8 | 1899-12-31 | [8 empty] | 0.2 | standby di SBM export.
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.44167 | 0.070833 |  | 0.045833 | 0 |  | 0.44167
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 10284 |  | Ltrs | 1950 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 8334 | Ltrs | 1 p - 14 cm = 452 ltr
Economical Speed (Eco) | [5 empty] | 10:36 |  | 120 |  | Ltrs | 1272 |  | Ltrs |  | FRESH WATER |  |  | 44 |  | Ltrs | 4 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 40 | Ltrs | 1 S - 8 cm = 196 ltr
Slow speed (Slow) | [5 empty] | 1:42 |  | 89 |  | Ltrs | 151.3 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs | 2 p - 27 cm = 1289 ltr
Maneuvering (Manu) | [5 empty] | 1:06 |  | 89 |  | Ltrs | 97.9 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | 2 S - 30 cm = 1545 ltr
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | 3 p - 75 cm = 2295 ltr
Standby (S/B) | [5 empty] | 10:36 |  | 40 |  | Ltrs | 424 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | 3 S - 45 cm = 799 ltr
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | DT - 105 cm = 1758
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 1 |  |  |  |  | 1945.2 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : | HERMAN | Suwartono | [12 empty] | Name : | ANDI MUHAMMAD AMRI | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative