## 13-19
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 13 October, 2019 |  |  |  | Location (Midnight) |  |  |  | Cinta Terminal ( SPM export ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT Mitra Anugerah 32 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI/SAMUDERA INDO
Contract No. | [7 empty] | Master Name |  |  |  | ANDI MUHAMMAD AMRI |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 10 |  | / | 0 | Person | 0 | 0.016667 | [8 empty] | 0.016667 | MA 32 standby di SBM export.
[17 empty] | 0.016667 | 0.12917 |  |  | 0.098611 | 0.010417 |  | 0.0034722 |  |  |  | Tahan posisi kapal menjauh dari SBM export,arus dari buritan kapal.
WEATHER CONDITION | [16 empty] | 0.12917 | 0.22917 | [8 empty] | 0.1 | MA 32 standby di SBM export.
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.22917 | 0.27917 |  |  | 0.040278 | 0.0069444 |  | 0.0027778 |  |  |  | tarik putar SBM export luruskan hose,sejajarkan dengan arus.
Wind (Dir/speed) |  |  |  | E 4-6 Knot |  |  | E 07-10 Knot |  |  | E 10-14 Knot |  |  |  | E 8- 10 Knot |  |  | 0.27917 | 0.32917 | [8 empty] | 0.05 | MA 32 standby di SBM export.
Sea (Wave Height) |  |  |  | Slight / 0.0-0.6 m |  |  | Moderate / 0.6-1.0 m |  |  | Moderate / 1.0-1.5 m |  |  |  | Slight / 0.0-0.6 m |  |  | 0.32917 | 0.35417 |  |  | 0.020139 | 0.0027778 |  | 0.0020833 |  |  |  | SBM export - 114.
Visibility | [16 empty] | 0.35417 | 0.3625 |  |  | 0.0034722 | 0.0027778 |  | 0.0020833 |  |  |  | picup material dan naikkan 2 personil
[17 empty] | 0.3625 | 0.37083 |  |  | 0.0034722 | 0.0027778 |  | 0.0020833 |  |  |  | drop material dan drop personil ke SBM storage.
HSSE | [16 empty] | 0.37083 | 0.4125 |  |  | 0.034722 | 0.0034722 |  | 0.0034722 |  |  |  | SBM storage - SBM export.
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.4125 | 0.45417 | [8 empty] | 0.041667 | MA 32 standby di SBM export.
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.45417 | 0.47917 |  |  | 0.020139 | 0.0027778 |  | 0.0020833 |  |  |  | SBM export - SBM storage.
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.47917 | 0.4875 |  |  | 0.0041667 | 0.0020833 |  | 0.0020833 |  |  |  | pic up material dan 2 personil ke 114.
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.4875 | 0.51667 |  |  | 0.019444 | 0.0069444 |  | 0.0027778 |  |  |  | drop 3 personil ke 114.
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.51667 | 0.55417 | [8 empty] | 0.0375 | MA 32,ikat di lambung kiri 114.
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.55417 | 0.5875 |  |  | 0.026389 | 0.0034722 |  | 0.0034722 |  |  |  | cast off,pic up 2 personil/kembali ke SBM export.
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.5875 | 0.62083 |  |  | 0.026389 | 0.0034722 |  | 0.0034722 |  |  |  | survey line dari storage - SBM export.
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative |  | 0.62083 | 0.6375 |  |  | 0.011806 | 0.0027778 |  | 0.0020833 |  |  |  | selesai survey line,ikat di belakang mega 5.
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.6375 | 0.75417 | [8 empty] | 0.11667 | MA 32 standby di SBM export.
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.75417 | 0.87083 |  |  | 0.10556 | 0.0069444 |  | 0.0041667 |  |  |  | tarik putar SBM expor,luruskan hose,sejajarkan dengan arus.
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.87083 | 1899-12-31 | [8 empty] | 0.12917 | MA 32 standby di SBM export.
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.41458 | 0.057639 |  | 0.036111 | 0 |  | 0.49167
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 16084 |  | Ltrs | 1881 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 14203 | Ltrs | 13.30 s/d 14.24,survey line dari SBM storage - SBM
Economical Speed (Eco) | [5 empty] | 9:57 |  | 120 |  | Ltrs | 1194 |  | Ltrs |  | FRESH WATER |  |  | 53 |  | Ltrs | 4 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 49 | Ltrs | export.
Slow speed (Slow) | [5 empty] | 1:23 |  | 89 |  | Ltrs | 123.1167 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 0:52 |  | 89 |  | Ltrs | 77.1333 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 11:48 |  | 40 |  | Ltrs | 472 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 1866.25 |  | Ltrs
Prepared by, | [9 empty] | l;;; | [20 empty] | Acknowledged by,
Name : | HERMAN | Suwartono | [12 empty] | Name : | ANDI MUHAMMAD AMRI | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative