## 20-19
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 20 October, 2019 |  |  |  | Location (Midnight) |  |  |  | Cinta Terminal ( SPM export ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT Mitra Anugerah 32 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI/SAMUDERA INDO
Contract No. | [7 empty] | Master Name |  |  |  | ANDI MUHAMMAD AMRI |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 9 |  | / | 0 | Person | 0 | 0.0083333 | [8 empty] | 0.0083333 | MA 32 stanby di sbm export
[17 empty] | 0.0083333 | 0.24583 |  |  | 0.22014 | 0.013889 |  | 0.0034722 |  |  |  | tahan posisi kapal menjauh dari sbm export arus dan angin berlawanan
WEATHER CONDITION | [16 empty] | 0.24583 | 0.29583 | [8 empty] | 0.05 | MA 32 stanby di sbm export
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.29583 | 0.32917 |  |  | 0.023611 | 0.0069444 |  | 0.0027778 |  |  |  | gantikan posisi mega 5 di mooring line
Wind (Dir/speed) |  |  |  | E 00-06 Knot |  |  | E 0.0-07 Knot |  |  | E 0.2-06 Knot |  |  |  | E 0.3-0.7 Knot |  |  | 0.32917 | 0.43333 | [8 empty] | 0.10417 | MA 32 stanby di sbm export
Sea (Wave Height) |  |  |  | Calm sea / 0.0-0.6 m |  |  | Calm sea / 0.0/0,5 m |  |  | Calm sea / 1.0-1.5 m |  |  |  | Calm sea/ 0.0-0.6 m |  |  | 0.43333 | 0.50417 |  |  | 0.055556 | 0.010417 |  | 0.0048611 |  |  |  | Tarik putar sbm export arus mulai berubah
Visibility | [16 empty] | 0.50417 | 0.67083 | [8 empty] | 0.16667 | MA 32 stanby di sbm export
[17 empty] | 0.67083 | 0.7125 |  |  | 0.033333 | 0.0048611 |  | 0.0034722 |  |  |  | surveillance ke sbm export
HSSE | [16 empty] | 0.7125 | 0.8 | [8 empty] | 0.0875 | MA 32 stanby di sbm export
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.8 | 0.87083 |  |  | 0.0625 | 0.0048611 |  | 0.0034722 |  |  |  | tahan posisi MA 32 menjauh dari hose arus dan angin kuat dari haluan
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.87083 | 1899-12-31 | [8 empty] | 0.12917 | MA 32 stanby di sbm export
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.39514 | 0.040972 |  | 0.018056 | 0 |  | 0.54583
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 17216 |  | Ltrs | 1819 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 15397 | Ltrs | D.T- 67 cm=1005 lt
Economical Speed (Eco) | [5 empty] | 9:29 |  | 120 |  | Ltrs | 1138 |  | Ltrs |  | FRESH WATER |  |  | 28 |  | Ltrs | 4 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 24 | Ltrs | 2.P- 15 cm=505 lt
Slow speed (Slow) | [5 empty] | 0:59 |  | 89 |  | Ltrs | 87.5167 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs | 2.S- 20 cm=815 lt
Maneuvering (Manu) | [5 empty] | 0:26 |  | 89 |  | Ltrs | 38.5667 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | 3.P - 55 cm=4639
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | 3.S - 53 cm=4202
Standby (S/B) | [5 empty] | 13:06 |  | 40 |  | Ltrs | 524 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | 4.P- 71 cm=2057 lt
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | 4.S- 73 cm=2057 lt
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | draf depan=2 m/draf belakang=2.8 m
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 1788.0833 |  | Ltrs
Prepared by, | [9 empty] | l;;; | [20 empty] | Acknowledged by,
Name : | HERMAN | Suwartono | [12 empty] | Name : | ANDI MUHAMMAD AMRI | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative