## 26-19
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 26 October, 2019 |  |  |  | Location (Midnight) |  |  |  | Cinta Terminal ( SPM export ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT Mitra Anugerah 32 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI/SAMUDERA INDO
Contract No. | [7 empty] | Master Name |  |  |  | ANDI MUHAMMAD AMRI |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 9 |  | / | 10 | Person | 0 | 0.0875 | [8 empty] | 0.0875 | MA32 standby di SBM export.
[17 empty] | 0.0875 | 0.24583 |  |  | 0.13403 | 0.017361 |  | 0.0069444 |  |  |  | tahan posisi kapal menjauh dari SBM export,arus dari buritan
WEATHER CONDITION | [16 empty] | 0.24583 | 0.3125 | [8 empty] | 0.066667 | MA32 standby di SBM export.
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.3125 | 0.3375 |  |  | 0.018056 | 0.0041667 |  | 0.0027778 |  |  |  | MA 32 gantikan posisi mega 5 di mooring line.
Wind (Dir/speed) |  |  |  | E 00-06 Knot |  |  | E 0.0-07 Knot |  |  | E 0.2-06 Knot |  |  |  | E 0.3-0.7 Knot |  |  | 0.3375 | 0.45 |  |  | 0.096528 | 0.010417 |  | 0.0055556 |  |  |  | tarik putar SBM export,luruskan hose,sejajarkan dengan arus.
Sea (Wave Height) |  |  |  | Calm sea / 0.0-0.6 m |  |  | Calm sea / 0.0/0,5 m |  |  | Calm sea / 1.0-1.5 m |  |  |  | Calm sea/ 0.0-0.6 m |  |  | 0.45 | 0.55833 | [8 empty] | 0.10833 | MA 32 standby di SBM export.
Visibility | [16 empty] | 0.55833 | 0.5875 |  |  | 0.023611 | 0.0034722 |  | 0.0020833 |  |  |  | MA 32 gantikan posisi mega 5 di mooring line.
[17 empty] | 0.5875 | 0.6875 | [8 empty] | 0.1 | MA 32 standby di SBM export.
HSSE | [16 empty] | 0.6875 | 0.825 |  |  | 0.11806 | 0.013889 |  | 0.0055556 |  |  |  | tahan posisi kapal menjauh dari benturan hose,angin dan arus berlawanan.
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.825 | 1899-12-31 | [8 empty] | 0.175 | MA 32 standby di SBM export.
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.39028 | 0.049306 |  | 0.022917 | 0 |  | 0.5375
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 20320 |  | Ltrs | 1799 |  | Ltrs |  |  | Ltrs | 0 |  | Ltrs | 18521 | Ltrs | D.T- 100 cm=1659 lt
Economical Speed (Eco) | [5 empty] | 9:22 |  | 120 |  | Ltrs | 1124 |  | Ltrs |  | FRESH WATER |  |  | 29 |  | Ltrs | 3 |  | Ltrs |  |  | Ltrs | 0 |  | Ltrs | 26 | Ltrs | 2.P- 14 cm=506 lt
Slow speed (Slow) | [5 empty] | 1:11 |  | 89 |  | Ltrs | 105.3167 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs | 2.S- 21 cm=990 lt
Maneuvering (Manu) | [5 empty] | 0:33 |  | 89 |  | Ltrs | 48.95 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | 3.P -25 cm=1266 lt
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | 3.S - 25 cm=1266 lt
Standby (S/B) | [5 empty] | 12:54 |  | 40 |  | Ltrs | 516 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | 4.P- 155 cm=6556 lt
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | 4.S- 150 cm=6278 lt
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft | draf depan=2.50 m/draf belakang=2.80 m
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 1794.2667 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : | HERMAN | Suwartono | [12 empty] | Name : | ANDI MUHAMMAD AMRI | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative