## 02 Nov 19
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 07 November ,2019 |  |  |  | Location (Midnight) |  |  |  | Widuri Terminal ( SPM#1 ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT MITRA ANUGERAH 35 |  |  |  | Owner/Operator |  |  |  | PT EKA NURI
Contract No. | [7 empty] | Master Name |  |  |  | Akhmad Shokib |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 10 |  | / | 0 | Person | 0 | 0.041667 | [8 empty] | 0.041667 | Standby di SBM II
[17 empty] | 0.041667 | 0.13542 | [5 empty] | 0.09375 |  |  |  | Tahan posisi kapal dari SBM II, cuaca buruk
WEATHER CONDITION | [16 empty] | 0.13542 | 0.29167 | [8 empty] | 0.15625 | Standby di SBM II
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.29167 | 0.34722 | [5 empty] | 0.055556 |  |  |  | Tahan posisi kapal, cuaca buruk
Wind (Dir/speed) |  |  |  | E 8-10 Knot |  |  | E 16-18 Knot |  |  | E 8-10 Knot |  |  |  | E 12-14 Knot |  |  | 0.34722 | 0.52083 | [8 empty] | 0.17361 | Standby di SBM II
Sea (Wave Height) |  |  |  | Slight / 0.0-0.6 m |  |  | Moderate / 0.6-1.2 m |  |  | Slight / 0.0-0.6 m |  |  |  | Moderate / 0.6-1.2 m |  |  | 0.52083 | 0.54861 |  |  | 0.013889 | 0.0069444 |  | 0.0069444 |  |  |  | Sbm II ke Federal II, jemput surveyor BKI
Visibility | [16 empty] | 0.54861 | 0.58333 |  |  | 0.017361 | 0.0069444 |  | 0.010417 |  |  |  | Federal II ke Superior, antar BKI
[17 empty] | 0.58333 | 0.60417 | [5 empty] | 0.020833 |  |  |  | Stby di kanan Superior, tunggu Pasangger/ persoinil dari Superior
HSSE | [16 empty] | 0.60417 | 0.63542 |  |  | 0.017361 | 0.0069444 |  | 0.0069444 |  |  |  | Superior ke Federal II, antar personil IT
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.63542 | 0.66319 |  |  | 0.013889 |  |  | 0.013889 |  |  |  | Federal II ke SBM II, tarik dan putar SBM II
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.66319 | 0.82292 | [8 empty] | 0.15972 | Standby di SBM II
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.82292 | 0.84722 |  |  | 0.017361 |  |  | 0.0069444 |  |  |  | SBM II ke Federal II, jemput crew IT
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.84722 | 0.88542 |  |  | 0.017361 | 0.010417 |  | 0.010417 |  |  |  | Federal II ke BG. Superior, drop crew IT
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.88542 | 0.91667 |  |  | 0.017361 | 0.0069444 |  | 0.0069444 |  |  |  | Selesai drop kembali ke SBM II, Tarik putar SBM II arus berubah
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.91667 | 1899-12-31 | [8 empty] | 0.083333 | Standby di SBM II
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.11458 | 0.038194 |  | 0.23264 | 0 |  | 0.61458
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 27847 |  | Ltrs | 1022 |  | Ltrs |  |  | Ltrs | 0 |  | Ltrs | 26825 | Ltrs
Economical Speed (Eco) | [5 empty] | 2:45 |  | 120 |  | Ltrs | 330 |  | Ltrs |  | FRESH WATER |  |  | 47 |  | Ltrs | 2 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 45 | Ltrs
Slow speed (Slow) | [5 empty] | 0:55 |  | 89 |  | Ltrs | 81.5833 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 5:35 |  | 89 |  | Ltrs | 496.9167 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 14:45 |  | 8 |  | Ltrs | 118 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 1026.5 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : | Sudirman | Suwartono | [12 empty] | Name : | Ahmad Shokib | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative

## Sheet3
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 02 November ,2019 |  |  |  | Location (Midnight) |  |  |  | Widuri Terminal ( SPM#1 ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT MITRA ANUGERAH 35 |  |  |  | Owner/Operator |  |  |  | PT EKA NURI
Contract No. | [7 empty] | Master Name |  |  |  | Akhmad Shokib |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 10 |  | / | 0 | Person | 0 | 0.052083 | [8 empty] | 0.052083 | Standby di SBM I
[17 empty] | 0.052083 | 0.125 | [5 empty] | 0.072917 |  |  |  | Tahan mundur posisi kapal arus angin berubah
WEATHER CONDITION | [16 empty] | 0.125 | 0.25 | [8 empty] | 0.125 | Standby di SBM I
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.25 | 0.29861 | [5 empty] | 0.048611 |  |  |  | Putar SBM I, arus berubah
Wind (Dir/speed) |  |  |  | E 8-10 Knot |  |  | E 16-18 Knot |  |  | E 8-10 Knot |  |  |  | E 12-14 Knot |  |  | 0.29861 | 0.40625 | [8 empty] | 0.10764 | Standby di SBM I
Sea (Wave Height) |  |  |  | Slight / 0.0-0.6 m |  |  | Moderate / 0.6-1.2 m |  |  | Slight / 0.0-0.6 m |  |  |  | Moderate / 0.6-1.2 m |  |  | 0.40625 | 0.45833 | [5 empty] | 0.052083 |  |  |  | Putar SBM I, sejajarkan arus
Visibility | [16 empty] | 0.45833 | 0.51389 | [8 empty] | 0.055556 | Standby di SBM I
[17 empty] | 0.51389 | 0.58333 | [5 empty] | 0.069444 |  |  |  | Tarik SBM I, menjauh dari hose bertahan di posisi
HSSE | [16 empty] | 0.58333 | 0.63194 | [8 empty] | 0.048611 | Standby di SBM I
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.63194 | 0.66667 | [5 empty] | 0.034722 |  |  |  | Tarik SBM I, luruskan hose
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0 | 0 |  | 0.27778 | 0 |  | 0.38889
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 17193 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 17193 | Ltrs
Economical Speed (Eco) | [5 empty] | 0:00 |  | 120 |  | Ltrs | 0 |  | Ltrs |  | FRESH WATER |  |  | 57 |  | Ltrs | 2 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 55 | Ltrs
Slow speed (Slow) | [5 empty] | 0:00 |  | 89 |  | Ltrs | 0 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 6:40 |  | 89 |  | Ltrs | 593.3333 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 9:20 |  | 8 |  | Ltrs | 74.6667 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 0.66667 |  |  |  |  | 668 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : | Sudirman | Suwartono | [12 empty] | Name : | Ahmad Shokib | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative