## 02 Nov 19
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 19 November ,2019 |  |  |  | Location (Midnight) |  |  |  | Widuri Terminal ( SPM#1 ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT MITRA ANUGERAH 35 |  |  |  | Owner/Operator |  |  |  | PT EKA NURI
Contract No. | [7 empty] | Master Name |  |  |  | Akhmad Shokib |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 10 |  | / | 0 | Person | 0 | 0.020833 | [8 empty] | 0.020833 | Standby di SBM I
[17 empty] | 0.020833 | 0.12917 | [5 empty] | 0.10833 |  |  |  | Reposisi Masengger line di SBM I
WEATHER CONDITION | [16 empty] | 0.12917 | 0.27083 | [8 empty] | 0.14167 | Standby di SBM I
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.27083 | 0.3 |  |  | 0.013889 | 0.0069444 |  | 0.0083333 |  |  |  | SBM I ke Federal II, drop crew
Wind (Dir/speed) |  |  |  | E 8-10 Knot |  |  | E 16-18 Knot |  |  | E 8-10 Knot |  |  |  | E 12-14 Knot |  |  | 0.3 | 0.325 |  |  | 0.013889 |  |  | 0.011111 |  |  |  | Federal II ke SBM I, ikat di masengger line
Sea (Wave Height) |  |  |  | Slight / 0.0-0.6 m |  |  | Moderate / 0.6-1.2 m |  |  | Slight / 0.0-0.6 m |  |  |  | Moderate / 0.6-1.2 m |  |  | 0.325 | 0.41667 | [8 empty] | 0.091667 | Standby di SBM I
Visibility | [16 empty] | 0.41667 | 0.5 | [5 empty] | 0.083333 |  |  |  | Reposisi Masengger line di SBM I
[17 empty] | 0.5 | 0.59167 | [8 empty] | 0.091667 | Standby di SBM I
HSSE | [16 empty] | 0.59167 | 0.61667 |  |  | 0.017361 |  |  | 0.0076389 |  |  |  | SBM I ke Superior, jemput personil
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.61667 | 0.64583 |  |  | 0.017361 | 0.0069444 |  | 0.0048611 |  |  |  | Superior ke SBM I, ikat di msengger line
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.64583 | 0.69167 | [5 empty] | 0.045833 |  |  |  | Tarik putar SBM I , arus berubah
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.69167 | 0.725 |  |  | 0.019444 | 0.0069444 |  | 0.0069444 |  |  |  | SBM I ke SBM II, ikat di buritan INA. P2
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.725 | 0.79167 | [8 empty] | 0.066667 | Standby di SBM II
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.79167 | 0.825 | [5 empty] | 0.033333 |  |  |  | Tarik putar SBM II , arus berubah
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.825 | 1899-12-31 | [8 empty] | 0.175 | Standby di SBM II
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.081944 | 0.020833 |  | 0.30972 | 0 |  | 0.5875
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 17084 |  | Ltrs | 1051 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 16033 | Ltrs
Economical Speed (Eco) | [5 empty] | 1:58 |  | 120 |  | Ltrs | 236 |  | Ltrs |  | FRESH WATER |  |  | 43 |  | Ltrs | 2 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 41 | Ltrs
Slow speed (Slow) | [5 empty] | 0:30 |  | 89 |  | Ltrs | 44.5 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 7:26 |  | 89 |  | Ltrs | 661.5667 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 14:06 |  | 8 |  | Ltrs | 112.8 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 1054.8667 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : | Sudirman | Suwartono | [12 empty] | Name : | Ahmad Shokib | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative

## Sheet3
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 02 November ,2019 |  |  |  | Location (Midnight) |  |  |  | Widuri Terminal ( SPM#1 ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT MITRA ANUGERAH 35 |  |  |  | Owner/Operator |  |  |  | PT EKA NURI
Contract No. | [7 empty] | Master Name |  |  |  | Akhmad Shokib |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 10 |  | / | 0 | Person | 0 | 0.052083 | [8 empty] | 0.052083 | Standby di SBM I
[17 empty] | 0.052083 | 0.125 | [5 empty] | 0.072917 |  |  |  | Tahan mundur posisi kapal arus angin berubah
WEATHER CONDITION | [16 empty] | 0.125 | 0.25 | [8 empty] | 0.125 | Standby di SBM I
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.25 | 0.29861 | [5 empty] | 0.048611 |  |  |  | Putar SBM I, arus berubah
Wind (Dir/speed) |  |  |  | E 8-10 Knot |  |  | E 16-18 Knot |  |  | E 8-10 Knot |  |  |  | E 12-14 Knot |  |  | 0.29861 | 0.40625 | [8 empty] | 0.10764 | Standby di SBM I
Sea (Wave Height) |  |  |  | Slight / 0.0-0.6 m |  |  | Moderate / 0.6-1.2 m |  |  | Slight / 0.0-0.6 m |  |  |  | Moderate / 0.6-1.2 m |  |  | 0.40625 | 0.45833 | [5 empty] | 0.052083 |  |  |  | Putar SBM I, sejajarkan arus
Visibility | [16 empty] | 0.45833 | 0.51389 | [8 empty] | 0.055556 | Standby di SBM I
[17 empty] | 0.51389 | 0.58333 | [5 empty] | 0.069444 |  |  |  | Tarik SBM I, menjauh dari hose bertahan di posisi
HSSE | [16 empty] | 0.58333 | 0.63194 | [8 empty] | 0.048611 | Standby di SBM I
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.63194 | 0.66667 | [5 empty] | 0.034722 |  |  |  | Tarik SBM I, luruskan hose
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0 | 0 |  | 0.27778 | 0 |  | 0.38889
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 17193 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 17193 | Ltrs
Economical Speed (Eco) | [5 empty] | 0:00 |  | 120 |  | Ltrs | 0 |  | Ltrs |  | FRESH WATER |  |  | 57 |  | Ltrs | 2 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 55 | Ltrs
Slow speed (Slow) | [5 empty] | 0:00 |  | 89 |  | Ltrs | 0 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 6:40 |  | 89 |  | Ltrs | 593.3333 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 9:20 |  | 8 |  | Ltrs | 74.6667 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 0.66667 |  |  |  |  | 668 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : | Sudirman | Suwartono | [12 empty] | Name : | Ahmad Shokib | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative