## 01 Sept
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 01 September ,2019 |  |  |  | Location (Midnight) |  |  |  | Widuri Terminal ( SPM#1 ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT Megawati 17 |  |  |  | Owner/Operator |  |  |  | PT.REJEKI ABADI SAKTI
Contract No. | [7 empty] | Master Name |  |  |  | Nixon Makaganza |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 6 |  | / | 0 | Person | 0 | 0.18403 |  |  | 0.041667 | 0.017361 |  | 0.125 |  |  |  | Tarik tahan hose persiapan unmooring MT.SANANA
[17 empty] | 0.18403 | 0.22222 |  |  | 0.013889 | 0.0069444 |  | 0.017361 |  |  |  | Service hose & messenger line
WEATHER CONDITION | [16 empty] | 0.22222 | 0.34722 | [8 empty] | 0.125 | Stby di SPM#01
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.34722 | 0.46875 | [5 empty] | 0.12153 |  |  |  | Tahan posisi kapal menjauh dari benturan hose
Wind (Dir/speed) |  |  |  | E 8-10 Knot |  |  | E 16-18 Knot |  |  | E 8-10 Knot |  |  |  | E 12-14 Knot |  |  | 0.46875 | 0.54514 | [8 empty] | 0.076389 | Stby di SPM#01
Sea (Wave Height) |  |  |  | Slight / 0.0-0.6 m |  |  | Moderate / 0.6-1.2 m |  |  | Slight / 0.0-0.6 m |  |  |  | Moderate / 0.6-1.2 m |  |  | 0.54514 | 0.60069 | [5 empty] | 0.055556 |  |  |  | Tarik putar messenger line arus berubah
Visibility | [16 empty] | 0.60069 | 0.66667 | [8 empty] | 0.065972 | Stby di SPM#01
[17 empty] | 0.66667 | 0.75 | [5 empty] | 0.083333 |  |  |  | Tahan posisi kapal arus dan angin berlawanan
HSSE | [16 empty] | 0.75 | 0.78125 |  |  | 0.024306 | 0.0034722 |  | 0.0034722 |  |  |  | SPM#01 - FD2 drop crew
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.78125 | 0.86458 | [8 empty] | 0.083333 | Stby di FD2
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.86458 | 0.89583 |  |  | 0.024306 | 0.0034722 |  | 0.0034722 |  |  |  | FD2 jemput crew antar ke Mega 5 dan HT IP2
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.89583 | 0.9375 |  |  | 0.034722 | 0.0034722 |  | 0.0034722 |  |  |  | Mega 5 - IP2 drop crew
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.9375 | 24:00 | [8 empty] | 0.0625 | Stby di SPM#01
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.13889 | 0.034722 |  | 0.41319 | 0 |  | 0.41319
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 14750 |  | Ltrs | 1440 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 13310 | Ltrs
Economical Speed (Eco) | [5 empty] | 3:20 |  | 115 |  | Ltrs | 383.3333 |  | Ltrs |  | FRESH WATER |  |  | 3 |  | Ltrs | 1 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 2 | Ltrs
Slow speed (Slow) | [5 empty] | 0:50 |  | 102 |  | Ltrs | 85 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 9:55 |  | 90 |  | Ltrs | 892.5 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 9:55 |  | 6 |  | Ltrs | 59.5 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 1 |  |  |  |  | 1420.3333 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : |  | Suwartono | [12 empty] | Name : | [6 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative

## 08 (2)
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 10 September ,2019 |  |  |  | Location (Midnight) |  |  |  | Widuri Terminal ( SPM#1 ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT Mitra Anugerah 35 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI
Contract No. | [7 empty] | Master Name |  |  |  | ANWAR |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 10 |  | / | 0 | Person | 0 | 0.44792 | [8 empty] | 0.44792 | Stby di SBM II
[17 empty] | 0.44792 | 0.46181 | [5 empty] | 0.013889 |  |  |  | Shifting
WEATHER CONDITION | [16 empty] | 0.46181 | 0.72917 | [8 empty] | 0.26736 | Stby di SBM II
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.72917 | 0.74653 | [5 empty] | 0.017361 |  |  |  | Shifting
Wind (Dir/speed) |  |  |  | E 4-6 Knot |  |  | E 12-14 Knot |  |  | E 5-7 Knot |  |  |  | NE 8- 10 Knot |  |  | 0.74653 | 0.77778 | [8 empty] | 0.03125 | Stby di SBM II
Sea (Wave Height) |  |  |  | Slight / 0.0-0.6 m |  |  | Moderate / 0.6-1.2 m |  |  | Slight / 0.0-0.6 m |  |  |  | Slight / 0.0-0.6 m |  |  | 0.77778 | 0.82639 |  |  | 0.041667 |  |  | 0.0069444 |  |  |  | Kapal pindah posisi ke SBM I
Visibility | [16 empty] | 0.82639 | 0.86458 | [8 empty] | 0.038194 | Stby di SBM I, gantikan posisi TB Megawati 17
[17 empty] | 0.86458 | 0.9375 |  |  | 0.048611 | 0.017361 |  | 0.0069444 |  |  |  | Memperbaiki posisi Hose SBM I. kembali ke SBM II
HSSE | [16 empty] | 0.9375 | 1899-12-31 | [8 empty] | 0.0625 | Stby di SBM II
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.090278 | 0.017361 |  | 0.045139 | 0 |  | 0.84722
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 41589 |  | Ltrs | 552 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 41037 | Ltrs
Economical Speed (Eco) | [5 empty] | 2:10 |  | 120 |  | Ltrs | 260 |  | Ltrs |  | FRESH WATER |  |  | 27 |  | Ltrs | 3 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 24 | Ltrs
Slow speed (Slow) | [5 empty] | 0:25 |  | 89 |  | Ltrs | 37.0833 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 1:05 |  | 89 |  | Ltrs | 96.4167 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 20:20 |  | 8 |  | Ltrs | 162.6667 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 556.1667 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : | Sudirman | Suwartono | [12 empty] | Name : | Anwar | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative

## 26 0CT
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 26 Oktober 2019 |  |  |  | Location (Midnight) |  |  |  | Widuri Terminal ( SPM#1 ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT Mitra Anugerah 35 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI
Contract No. | [7 empty] | Master Name |  |  |  | AKHMAD SHOKIB |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 10 |  | / | 0 | Person | 0 | 0.010417 | [8 empty] | 0.010417 | Stby di SBM 1
[17 empty] | 0.010417 | 0.09375 | [5 empty] | 0.083333 |  |  |  | Tarik SBM 1 menjauh dari hose
WEATHER CONDITION | [16 empty] | 0.09375 | 0.13889 | [8 empty] | 0.045139 | Stby di SBM 1
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.13889 | 0.27083 | [5 empty] | 0.13194 |  |  |  | Tarik SBM 1 sejajarkan dengan arus
Wind (Dir/speed) |  |  |  | E 4-6 Knot |  |  | E 12-14 Knot |  |  | E 5-7 Knot |  |  |  | NE 8- 10 Knot |  |  | 0.27083 | 0.39583 | [8 empty] | 0.125 | Stby di SBM 1
Sea (Wave Height) |  |  |  | Slight / 0.0-0.6 m |  |  | Moderate / 0.6-1.2 m |  |  | Slight / 0.0-0.6 m |  |  |  | Slight / 0.0-0.6 m |  |  | 0.39583 | 0.53125 | [5 empty] | 0.13542 |  |  |  | Tahan Posisi Kapal Menjauh Dari Hose
Visibility | [16 empty] | 0.53125 | 0.625 | [8 empty] | 0.09375 | Stby di SBM 1
[17 empty] | 0.625 | 0.65972 | [5 empty] | 0.034722 |  |  |  | Tarik dan putar SBM I
HSSE | [16 empty] | 0.65972 | 1899-12-31 | [8 empty] | 0.34028 | Stby di SBM 1
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0 | 0 |  | 0.38542 | 0 |  | 0.61458
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 24484 |  | Ltrs | 935 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 23549 | Ltrs
Economical Speed (Eco) | [5 empty] | 0:00 |  | 120 |  | Ltrs | 0 |  | Ltrs |  | FRESH WATER |  |  | 56 |  | Ltrs | 2 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 54 | Ltrs
Slow speed (Slow) | [5 empty] | 0:00 |  | 89 |  | Ltrs | 0 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 9:15 |  | 89 |  | Ltrs | 823.25 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 14:45 |  | 8 |  | Ltrs | 118 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 1 |  |  |  |  | 941.25 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : | Sudirman | Suwartono | [12 empty] | Name : | Akhmad Shokib | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative

## 27 0CT
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 27 Oktober 2019 |  |  |  | Location (Midnight) |  |  |  | Widuri Terminal ( SPM#1 ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT Mitra Anugerah 35 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI
Contract No. | [7 empty] | Master Name |  |  |  | AKHMAD SHOKIB |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 10 |  | / | 0 | Person | 0 | 0.055556 | [8 empty] | 0.055556 | Stby di SBM 1
[17 empty] | 0.055556 | 0.125 | [5 empty] | 0.069444 |  |  |  | Luruskan hose
WEATHER CONDITION | [16 empty] | 0.125 | 0.25 | [8 empty] | 0.125 | Stby di SBM 1
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.25 | 0.29167 | [5 empty] | 0.041667 |  |  |  | Luruskan hose
Wind (Dir/speed) |  |  |  | E 4-6 Knot |  |  | E 12-14 Knot |  |  | E 5-7 Knot |  |  |  | NE 8- 10 Knot |  |  | 0.29167 | 0.33333 |  |  | 0.017361 | 0.013889 |  | 0.010417 |  |  |  | bergerak dari SBM I ke Federal II
Sea (Wave Height) |  |  |  | Slight / 0.0-0.6 m |  |  | Moderate / 0.6-1.2 m |  |  | Slight / 0.0-0.6 m |  |  |  | Slight / 0.0-0.6 m |  |  | 0.33333 | 0.34722 | [5 empty] | 0.013889 |  |  |  | Drop crew ke Federal II, stby di lambung kanan Fedral II
Visibility | [16 empty] | 0.34722 | 0.47917 | [8 empty] | 0.13194 | Stby di lambung kanan Fedral II
[17 empty] | 0.47917 | 0.55903 |  |  | 0.020833 | 0.013889 |  | 0.045139 |  |  |  | Bergerak dari Federal II ke SBM II,
HSSE | [16 empty] | 0.55903 | 1899-12-31 | [8 empty] | 0.44097 | Stby di SBM II
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.038194 | 0.027778 |  | 0.18056 | 0 |  | 0.75347
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 23549 |  | Ltrs | 697 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 22852 | Ltrs
Economical Speed (Eco) | [5 empty] | 0:55 |  | 120 |  | Ltrs | 110 |  | Ltrs |  | FRESH WATER |  |  | 54 |  | Ltrs | 2 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 52 | Ltrs
Slow speed (Slow) | [5 empty] | 0:40 |  | 89 |  | Ltrs | 59.3333 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 4:20 |  | 89 |  | Ltrs | 385.6667 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 18:05 |  | 8 |  | Ltrs | 144.6667 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 699.6667 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : | Sudirman | Suwartono | [12 empty] | Name : | Akhmad Shokib | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative

## 28 OCT
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 28 Oktober 2019 |  |  |  | Location (Midnight) |  |  |  | Widuri Terminal ( SPM#1 ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT Mitra Anugerah 35 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI
Contract No. | [7 empty] | Master Name |  |  |  | AKHMAD SHOKIB |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 10 |  | / | 0 | Person | 0 | 0.083333 | [8 empty] | 0.083333 | Stby di SBM II
[17 empty] | 0.083333 | 0.13889 | [5 empty] | 0.055556 |  |  |  | Putar SBM II, Sejajarkan Dengan Arus
WEATHER CONDITION | [16 empty] | 0.13889 | 0.20486 | [8 empty] | 0.065972 | Stby di SBM II
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.20486 | 0.24306 |  |  | 0.03125 |  |  | 0.0069444 |  |  |  | Bergerak dari SBM II ke SBM I, ganti TB Mega 17
Wind (Dir/speed) |  |  |  | E 4-6 Knot |  |  | E 12-14 Knot |  |  | E 5-7 Knot |  |  |  | NE 8- 10 Knot |  |  | 0.24306 | 0.28125 | [5 empty] | 0.038194 |  |  |  | Luruskan hose SBM I
Sea (Wave Height) |  |  |  | Slight / 0.0-0.6 m |  |  | Moderate / 0.6-1.2 m |  |  | Slight / 0.0-0.6 m |  |  |  | Slight / 0.0-0.6 m |  |  | 0.28125 | 0.36806 | [8 empty] | 0.086806 | Stby di SBM I
Visibility | [16 empty] | 0.36806 | 0.39236 |  |  | 0.017361 | 0.0069444 | [5 empty] | Bergerak dari SBM I ke Federal II
[17 empty] | 0.39236 | 0.44792 | [5 empty] | 0.055556 |  |  |  | Bantu crew Federal II Drill Rescue Boat
HSSE | [16 empty] | 0.44792 | 0.47917 |  |  | 0.020833 | 0.0034722 |  | 0.0069444 |  |  |  | Kembali ke SBM I
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.47917 | 0.50694 | [8 empty] | 0.027778 | Stby di SBM I
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.50694 | 0.57639 |  |  | 0.055556 | 0.0069444 |  | 0.0069444 |  |  |  | Dari SBM I ke Bg Cossl 021 jemput crewchange
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.57639 | 0.64583 |  |  | 0.055556 | 0.0069444 |  | 0.0069444 |  |  |  | Jemput personil antar ke Superior-Federal II
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.64583 | 0.67708 |  |  | 0.024306 | 0.0034722 |  | 0.0034722 |  |  |  | Federal II ke IP2 jemput crew antar ke FEDERAL II
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.67708 | 0.73264 |  |  | 0.020833 | 0.0069444 |  | 0.027778 |  |  |  | Federal II ke SBM II
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.73264 | 0.75 | [8 empty] | 0.017361 | Stby di SBM II
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.75 | 0.76389 | [5 empty] | 0.013889 |  |  |  | Shifting, tukar posisi dgn IP 2
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative |  | 0.76389 | 0.875 | [8 empty] | 0.11111 | Stby di SBM II
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.875 | 0.91667 |  |  | 0.03125 |  |  | 0.010417 |  |  |  | SBM II ke Federal II lanjut ke SBM I, antar crew Mega 17
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.91667 | 0.94792 |  |  | 0.024306 |  |  | 0.0069444 |  |  |  | SBM I ke SBM II
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.94792 | 1899-12-31 | [8 empty] | 0.052083 | Stby di SBM II
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.28125 | 0.034722 |  | 0.23958 | 0 |  | 0.44444
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 22852 |  | Ltrs | 1475 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 21377 | Ltrs
Economical Speed (Eco) | [5 empty] | 6:45 |  | 120 |  | Ltrs | 810 |  | Ltrs |  | FRESH WATER |  |  | 52 |  | Ltrs | 2 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 50 | Ltrs
Slow speed (Slow) | [5 empty] | 0:50 |  | 89 |  | Ltrs | 74.1667 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 5:45 |  | 89 |  | Ltrs | 511.75 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 10:40 |  | 8 |  | Ltrs | 85.3333 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 1481.25 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : | Sudirman | Suwartono | [12 empty] | Name : | Akhmad Shokib | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative

## 29 0CT
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 29 Oktober 2019 |  |  |  | Location (Midnight) |  |  |  | Widuri Terminal ( SPM#1 ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT Mitra Anugerah 35 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI
Contract No. | [7 empty] | Master Name |  |  |  | AKHMAD SHOKIB |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 10 |  | / | 0 | Person | 0 | 0.090278 | [8 empty] | 0.090278 | Stby di SBM II
[17 empty] | 0.090278 | 0.13889 | [5 empty] | 0.048611 |  |  |  | Tarik dan luruskan SBM II
WEATHER CONDITION | [16 empty] | 0.13889 | 0.30556 | [8 empty] | 0.16667 | Stby di SBM II
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.30556 | 0.375 | [5 empty] | 0.069444 |  |  |  | Tarik dan luruskan SBM II
Wind (Dir/speed) |  |  |  | E 4-6 Knot |  |  | E 12-14 Knot |  |  | E 5-7 Knot |  |  |  | NE 8- 10 Knot |  |  | 0.375 | 0.40972 |  |  | 0.024306 | 0.0034722 |  | 0.0069444 |  |  |  | SBM II ke SBM I,
Sea (Wave Height) |  |  |  | Slight / 0.0-0.6 m |  |  | Moderate / 0.6-1.2 m |  |  | Slight / 0.0-0.6 m |  |  |  | Slight / 0.0-0.6 m |  |  | 0.40972 | 0.4375 |  |  | 0.013889 | 0.0069444 |  | 0.0069444 |  |  |  | SBM I ke Federal II, drop personil crewchange
Visibility | [16 empty] | 0.4375 | 0.45833 |  |  | 0.017361 |  |  | 0.0034722 |  |  |  | Federal II ke SBM II
[17 empty] | 0.45833 | 0.5 | [8 empty] | 0.041667 | Stby di SBM II
HSSE | [16 empty] | 0.5 | 0.54167 |  |  | 0.027778 | 0.0069444 |  | 0.0069444 |  |  |  | SBM II ke Federal II, jemput crew, lanjut ke Superior
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.54167 | 0.56597 | [5 empty] | 0.024306 |  |  |  | Proses Angkat belanjaan
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.56597 | 0.58333 |  |  | 0.013889 |  |  | 0.0034722 |  |  |  | Superior ke SBM I, antar belanjaan Mega 17
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.58333 | 0.59375 |  |  | 0.010417 | [6 empty] | SBM I ke Fedral II
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.59375 | 0.625 |  |  | 0.013889 | 0.0069444 |  | 0.010417 |  |  |  | Federal II ke SBM II, antar crew IP 2
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.625 | 0.64236 |  |  | 0.010417 |  |  | 0.0069444 |  |  |  | SBM II ke Federal II, antar crew IP II, stby dikanan Federal II
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.64236 | 0.65625 | [8 empty] | 0.013889 | Stby di lambung kanan Fedral II
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.65625 | 0.68403 |  |  | 0.017361 | 0.0034722 |  | 0.0069444 |  |  |  | Federal II ke Superior, ambil barang
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative |  | 0.68403 | 0.70139 |  |  | 0.013889 |  |  | 0.0034722 |  |  |  | Superior ke Federal II, drop barang
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.70139 | 0.79167 | [8 empty] | 0.090278 | Stby di lambung kanan Fedral II
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.79167 | 0.83681 |  |  | 0.027778 | 0.0069444 |  | 0.010417 |  |  |  | Fderal II ke SBM I, jemput crew Mega 17, balik ke Fdral II
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.83681 | 0.93056 | [8 empty] | 0.09375 | Stby dilambung kanan Federal II
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.93056 | 0.97569 |  |  | 0.034722 | 0.0034722 |  | 0.0069444 |  |  |  | Federal II ke Mega 17 lanjut ke SBM II, antar crew
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.97569 | 1899-12-31 | [8 empty] | 0.024306 | Stby di SBM II
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.22569 | 0.038194 |  | 0.21528 | 0 |  | 0.52083
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 21377 |  | Ltrs | 1284 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 20093 | Ltrs
Economical Speed (Eco) | [5 empty] | 5:25 |  | 120 |  | Ltrs | 650 |  | Ltrs |  | FRESH WATER |  |  | 50 |  | Ltrs | 2 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 48 | Ltrs
Slow speed (Slow) | [5 empty] | 0:55 |  | 89 |  | Ltrs | 81.5833 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 5:10 |  | 89 |  | Ltrs | 459.8333 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 12:30 |  | 8 |  | Ltrs | 100 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 1291.4167 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : | Sudirman | Suwartono | [12 empty] | Name : | Akhmad Shokib | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative