## 01 AGUSTUS 2020
PT PERTAMINA HULU ENERGI | [17 empty] | VESSEL DAILY REPORT
MARINE & AVIATION TEAM | [17 empty] | (Every Midnight)
GENERAL INFORMATION | [18 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 2020-08-01 |  |  |  | Location (Midnight) |  |  |  | SPM 01, WIDURI TERMINAL | [6 empty] | TIME |  |  |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [11 empty] | ACTIVITIES
Vessel Name |  |  |  | TB.MITRA ANUGERAH 35 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI
Contract No. |  |  |  | 4710002973 |  |  |  | Master Name |  |  |  | AHMAD SHOKIB | [6 empty] | Start |  | Finish |  | High |  | Normal | Slow |  | Manu |  | Tow |  | A/H | S/B
Contract Period |  |  |  | 2020-09-01 | - | 30-Agst-20 |  | Number of Crew / Pax |  |  |  | 8 |  | / | 10 |  | Person |  | 0 |  | 0.23333 | [11 empty] | 0.23333 |  | Stby di SPM 02
[19 empty] | 0.23333 |  | 0.27083 |  |  |  | 0.029167 | 0.0041667 |  | 0.0041667 | [6 empty] | SPM 02 ke Federal II ambil makanan , antar ke MT.Emmanuel
WEATHER CONDITION | [18 empty] | 0.27083 |  | 0.30833 |  |  |  | 0.029167 |  |  | 0.0083333 | [6 empty] | Selesai antar makanan kembali ke SPM 01
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  |  |  | 0.30833 |  | 0.46667 | [11 empty] | 0.15833 |  | Stby di SPM 02
Wind (Dir/speed) |  |  |  | E 9-11 Knot |  |  | NE 10-11 Knot |  |  | E 8 - 10 Knot |  |  |  | E 10- 12 Knot |  |  |  |  | 0.46667 |  | 0.5125 |  |  |  | 0.033333 | 0.0041667 |  | 0.0083333 | [6 empty] | SPM 02 ke Federal II ambil makanan , antar ke MT.Emmanuel
Sea (Wave Height) |  |  |  | Slight / 0,6 M - 1,1 M |  |  | Slight / 0,7 M - 1,2 M |  |  | Calm / 0,5 M - 1 M |  |  |  | Calm / 1 M - 1,5 m |  |  |  |  | 0.5125 |  | 0.54583 |  |  |  | 0.029167 |  |  | 0.0041667 | [6 empty] | Selesai drop makanan kembali ke SPM 02
Visibility | [18 empty] | 0.54583 |  | 0.55417 | [11 empty] | 0.0083333 |  | Stby di SPM 02
[19 empty] | 0.55417 |  | 0.575 |  |  |  | 0.016667 |  |  | 0.0041667 | [6 empty] | SPM 02 ke Federal II jemput Agent
HSSE | [18 empty] | 0.575 |  | 0.69583 | [11 empty] | 0.12083 |  | Stby di lambung kanan Federal II Tunggu Agent
A. | HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  |  |  | 0.69583 |  | 0.72083 |  |  |  | 0.016667 |  |  | 0.0083333 | [6 empty] | Antar agent ke MT.Emmanuel
1 | O & I Card Submission (e.g. TUNTAS, STOP, etc.) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0.72083 |  | 0.84167 | [6 empty] | 0.12083 | [6 empty] | Persiapan UN mooring MT.Emmanuel, tahan - tahan hose
2 | Ijin Kerja / PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0.84167 |  | 1899-12-31 | [11 empty] | 0.15833 |  | Stby di SPM 01
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify: | [5 empty] | ) | 0 |  |  | 0 |  |  | 0 |  |  |  | TOTAL |  |  |  | 0 |  | 0.15417 | 0.0083333 |  | 0.15833 |  | 0 |  | 0 | 0.67917
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE | [5 empty] | Opening (ROB from Previous Day) |  |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  |  | Transferred |  |  | Closing |  |  | Remarks
High Speed (High) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL | [5 empty] | 16543 |  |  | Ltrs | 926 |  | Ltrs | 0 |  |  | Ltrs | 0 |  | Ltrs | 15617 |  | Ltrs
Normal Speed (Normal) | [5 empty] | 3:42 |  | 120 |  | Ltrs | 444 |  | Ltrs |  | FRESH WATER | [5 empty] | 47000 |  |  | Ltrs | 2000 |  | Ltrs | 0 |  |  | Ltrs | 0 |  | Ltrs | 45000 |  | Ltrs
Slow speed (Slow) | [5 empty] | 0:12 |  | 89 |  | Ltrs | 17.8 |  | Ltrs |  | DRILL WATER | [5 empty] | 0 |  |  | Ltrs |  |  |  | 0 |  |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs
Maneuvering (Manu) - Including DP | [5 empty] | 3:48 |  | 89 |  | Ltrs | 338.2 |  | Ltrs |  | BARITE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Towing (Tow) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Anchor Handling (A/H) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | CEMENT BLENDED | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Standby (S/B) | [5 empty] | 16:18 |  | 8 |  | Ltrs | 130.4 |  | Ltrs |  | CEMENT G | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | BRINE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | OTHERS |  | (_________________) |  |  |  | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
|  |  | Total Daily |  |  | 1 |  |  |  |  | 930.4 |  | Ltrs
Prepared by, | [36 empty] | Acknowledged by,
Name: |  | ANDRI SUMARDI | [12 empty] | Name: |  | AKHMAD SHOKIB | [19 empty] | Name:
Title: CHIEF ENGINEER | [14 empty] | Title: MASTER | [21 empty] | Title: PHE Representative
VDR Rev. 4 - Dec. 2019
Attachment 1 | [27 empty] | Attachment 2
Vessel Daily Engine Parameter Log | [27 empty] | Crew & Passenger List
Date |  |  |  | 2020-08-01 | [23 empty] | Date |  |  |  | 2020-08-01
Vessel Name |  |  |  | TB.MITRA ANUGERAH 35 | [23 empty] | Vessel Name |  |  |  | TB.MITRA ANUGERAH 35
| PERHATIAN! 1. Laporan ini wajib dilengkapi setiap hari, pada saat kapal bergerak dengan kecepatan operasi normal. 2. Laporan ini tidak perlu di cetak. 3. Jika terdapat data yang NAIK atau TURUN secara signifikan dari data normal harian, wajib dianalisa, telusuri dan laporkan ke Port Engineer masing-masing perusahaan/kontraktor. | [26 empty] | PERHATIAN! 1. Laporan ini wajib dilengkapi setiap hari. 2. Laporan ini tidak perlu di cetak. 3. Nama yang dimasukkan dalam Passenger List hanya untuk penumpang yang bermalam atau yang tinggal selama 24 jam di atas kapal.
No | Observed Data / Indicators | [5 empty] | Unit | Main Engines Data | [9 empty] | Aux. Engines Data | [9 empty] | No | Vessel Crew List | [8 empty] | Passenger List
[8 empty] | Ref. Value |  | Port |  | Stbd |  | Center |  | Other ________ |  | Ref. Value |  | Port |  | Stbd |  | Other _______ |  |  |  |  | Name |  |  |  |  | Ranks |  |  |  | Name | Company
1 | Engine Revolution | [5 empty] | RPM | NA |  | 0 |  | 0 |  | 0 |  | 0 |  | NA |  | 0 |  | 0 | [5 empty] | 1 | AHMAD SHOKIB |  |  |  |  | MASTER CUTI
2 | Oil Pressure | [5 empty] | Bar | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 2 | A. WIRPIAN IRVAN |  |  |  |  | C/O
3 | Coolant Temperature Inlet | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 3 | ADE EKA SETYAWAN |  |  |  |  | 2/O
4 | Coolant Temperature Outlet | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 4 | ABDUL AFIF M |  |  |  |  | 3/O
5 | Exhaust Temperature Cyl. #1 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 5 | ANDRI SUMARDI |  |  |  |  | C/E
6 | Exhaust Temperature Cyl. #2 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 6 | MUSTOPA |  |  |  |  | 2/E
7 | Exhaust Temperature Cyl. #3 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 7 | BASTIAN BASRI |  |  |  |  | 3/E
8 | Exhaust Temperature Cyl. #4 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 8 | ABDUL KARIM DAENG |  |  |  |  | A/B
9 | Exhaust Temperature Cyl. #5 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 9 | HASDI |  |  |  |  | A/B |  | CUTI
10 | Exhaust Temperature Cyl. #6 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 10 | ASHAR |  |  |  |  | OILER
11 | Exhaust Temperature Cyl. #7 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 11
12 | Exhaust Temperature Cyl. #8 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 12
13 | Exhaust Temperature Cyl. #9 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 13
14 | Exhaust Temperature Cyl. #10 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 14
15 | Exhaust Temperature Cyl. #11 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 15
16 | Exhaust Temperature Cyl. #12 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 16
17 | Exhaust Temperature Cyl. #13 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 17
18 | Exhaust Temperature Cyl. #14 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 18
19 | Exhaust Temperature Cyl. #15 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 19
20 | Exhaust Temperature Cyl. #16 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 20
21 | Gear Box Oil Temperature | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 21
22 | Gear Box Oil Pressure | [5 empty] | Bar | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 02 AGUSTUS 2020 (2)
PT PERTAMINA HULU ENERGI | [17 empty] | VESSEL DAILY REPORT
MARINE & AVIATION TEAM | [17 empty] | (Every Midnight)
GENERAL INFORMATION | [18 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 2020-08-02 |  |  |  | Location (Midnight) |  |  |  | SPM 01, WIDURI TERMINAL | [6 empty] | TIME |  |  |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [11 empty] | ACTIVITIES
Vessel Name |  |  |  | TB.MITRA ANUGERAH 35 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI
Contract No. |  |  |  | 4710002973 |  |  |  | Master Name |  |  |  | AHMAD SHOKIB | [6 empty] | Start |  | Finish |  | High |  | Normal | Slow |  | Manu |  | Tow |  | A/H | S/B
Contract Period |  |  |  | 2020-09-01 | - | 30-Agst-20 |  | Number of Crew / Pax |  |  |  | 8 |  | / | 10 |  | Person |  | 0 |  | 0.025 | [11 empty] | 0.025 |  | Stmby di SPM 01
[19 empty] | 0.025 |  | 0.1125 | [6 empty] | 0.0875 | [6 empty] | Reposisi messenger line
WEATHER CONDITION | [18 empty] | 0.1125 |  | 0.27083 | [11 empty] | 0.15833 |  | Stmby di SPM 01
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  |  |  | 0.27083 |  | 0.29167 |  |  |  | 0.0125 | 0.0041667 |  | 0.0041667 | [6 empty] | SPM 01 ke FEDERAL II Jemput personil SBM
Wind (Dir/speed) |  |  |  | E 9-11 Knot |  |  | NE 10-11 Knot |  |  | E 8 - 10 Knot |  |  |  | E 10- 12 Knot |  |  |  |  | 0.29167 |  | 0.325 |  |  |  | 0.025 | 0.0041667 |  | 0.0041667 | [6 empty] | FEDERAL II ke SPM 01
Sea (Wave Height) |  |  |  | Slight / 0,6 M - 1,1 M |  |  | Slight / 0,7 M - 1,2 M |  |  | Calm / 0,5 M - 1 M |  |  |  | Calm / 1 M - 1,5 m |  |  |  |  | 0.325 |  | 0.42917 | [11 empty] | 0.10417 |  | Stmby di SPM 01
Visibility | [18 empty] | 0.42917 |  | 0.4875 |  |  |  | 0.05 | 0.0041667 |  | 0.0041667 | [6 empty] | SPM 0 1 ke FEDERAL II lanjut kasih naik morring box
[19 empty] | 0.4875 |  | 0.52917 | [6 empty] | 0.041667 | [6 empty] | Stmby lambung kanan tumggu personil
HSSE | [18 empty] | 0.52917 |  | 0.78333 |  |  |  | 0.24583 | 0.0041667 |  | 0.0041667 | [6 empty] | FEDERAL II ke PETREK antar personil
A. | HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  |  |  | 0.78333 |  | 1899-12-31 |  |  |  | 0.20833 | 0.0041667 |  | 0.0041667 | [6 empty] | PETREK ke WIDURI TERMINAL
1 | O & I Card Submission (e.g. TUNTAS, STOP, etc.) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Ijin Kerja / PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify: | [5 empty] | ) | 0 |  |  | 0 |  |  | 0 |  |  |  | TOTAL |  |  |  | 0 |  | 0.54167 | 0.020833 |  | 0.15 |  | 0 |  | 0 | 0.2875
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE | [5 empty] | Opening (ROB from Previous Day) |  |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  |  | Transferred |  |  | Closing |  |  | Remarks
High Speed (High) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL | [5 empty] | 15617 |  |  | Ltrs | 1975 |  | Ltrs | 0 |  |  | Ltrs | 0 |  | Ltrs | 13642 |  | Ltrs
Normal Speed (Normal) | [5 empty] | 13:00 |  | 120 |  | Ltrs | 1560 |  | Ltrs |  | FRESH WATER | [5 empty] | 45000 |  |  | Ltrs | 2000 |  | Ltrs | 0 |  |  | Ltrs | 0 |  | Ltrs | 43000 |  | Ltrs
Slow speed (Slow) | [5 empty] | 0:30 |  | 89 |  | Ltrs | 44.5 |  | Ltrs |  | DRILL WATER | [5 empty] | 0 |  |  | Ltrs |  |  |  | 0 |  |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs
Maneuvering (Manu) - Including DP | [5 empty] | 3:36 |  | 89 |  | Ltrs | 320.4 |  | Ltrs |  | BARITE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Towing (Tow) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Anchor Handling (A/H) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | CEMENT BLENDED | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Standby (S/B) | [5 empty] | 6:54 |  | 8 |  | Ltrs | 55.2 |  | Ltrs |  | CEMENT G | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | BRINE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | OTHERS |  | (_________________) |  |  |  | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 1980.1 |  | Ltrs
Prepared by, | [36 empty] | Acknowledged by,
Name: |  | ANDRI SUMARDI | [12 empty] | Name: |  | AKHMAD SHOKIB | [19 empty] | Name:
Title: CHIEF ENGINEER | [14 empty] | Title: MASTER | [21 empty] | Title: PHE Representative
VDR Rev. 4 - Dec. 2019
Attachment 1 | [27 empty] | Attachment 2
Vessel Daily Engine Parameter Log | [27 empty] | Crew & Passenger List
Date |  |  |  | 2020-08-02 | [23 empty] | Date |  |  |  | 2020-08-02
Vessel Name |  |  |  | TB.MITRA ANUGERAH 35 | [23 empty] | Vessel Name |  |  |  | TB.MITRA ANUGERAH 35
| PERHATIAN! 1. Laporan ini wajib dilengkapi setiap hari, pada saat kapal bergerak dengan kecepatan operasi normal. 2. Laporan ini tidak perlu di cetak. 3. Jika terdapat data yang NAIK atau TURUN secara signifikan dari data normal harian, wajib dianalisa, telusuri dan laporkan ke Port Engineer masing-masing perusahaan/kontraktor. | [26 empty] | PERHATIAN! 1. Laporan ini wajib dilengkapi setiap hari. 2. Laporan ini tidak perlu di cetak. 3. Nama yang dimasukkan dalam Passenger List hanya untuk penumpang yang bermalam atau yang tinggal selama 24 jam di atas kapal.
No | Observed Data / Indicators | [5 empty] | Unit | Main Engines Data | [9 empty] | Aux. Engines Data | [9 empty] | No | Vessel Crew List | [8 empty] | Passenger List
[8 empty] | Ref. Value |  | Port |  | Stbd |  | Center |  | Other ________ |  | Ref. Value |  | Port |  | Stbd |  | Other _______ |  |  |  |  | Name |  |  |  |  | Ranks |  |  |  | Name | Company
1 | Engine Revolution | [5 empty] | RPM | NA |  | 0 |  | 0 |  | 0 |  | 0 |  | NA |  | 0 |  | 0 | [5 empty] | 1 | AHMAD SHOKIB |  |  |  |  | MASTER CUTI
2 | Oil Pressure | [5 empty] | Bar | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 2 | A. WIRPIAN IRVAN |  |  |  |  | C/O
3 | Coolant Temperature Inlet | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 3 | ADE EKA SETYAWAN |  |  |  |  | 2/O
4 | Coolant Temperature Outlet | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 4 | ABDUL AFIF M |  |  |  |  | 3/O
5 | Exhaust Temperature Cyl. #1 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 5 | ANDRI SUMARDI |  |  |  |  | C/E
6 | Exhaust Temperature Cyl. #2 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 6 | MUSTOPA |  |  |  |  | 2/E
7 | Exhaust Temperature Cyl. #3 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 7 | BASTIAN BASRI |  |  |  |  | 3/E
8 | Exhaust Temperature Cyl. #4 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 8 | ABDUL KARIM DAENG |  |  |  |  | A/B
9 | Exhaust Temperature Cyl. #5 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 9 | HASDI |  |  |  |  | A/B |  | CUTI
10 | Exhaust Temperature Cyl. #6 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 10 | ASHAR |  |  |  |  | OILER
11 | Exhaust Temperature Cyl. #7 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 11
12 | Exhaust Temperature Cyl. #8 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 12
13 | Exhaust Temperature Cyl. #9 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 13
14 | Exhaust Temperature Cyl. #10 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 14
15 | Exhaust Temperature Cyl. #11 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 15
16 | Exhaust Temperature Cyl. #12 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 16
17 | Exhaust Temperature Cyl. #13 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 17
18 | Exhaust Temperature Cyl. #14 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 18
19 | Exhaust Temperature Cyl. #15 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 19
20 | Exhaust Temperature Cyl. #16 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 20
21 | Gear Box Oil Temperature | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 21
22 | Gear Box Oil Pressure | [5 empty] | Bar | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 03 AGUSTUS 2020 (2)
PT PERTAMINA HULU ENERGI | [17 empty] | VESSEL DAILY REPORT
MARINE & AVIATION TEAM | [17 empty] | (Every Midnight)
GENERAL INFORMATION | [18 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 2020-08-03 |  |  |  | Location (Midnight) |  |  |  | SPM 01, WIDURI TERMINAL | [6 empty] | TIME |  |  |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [11 empty] | ACTIVITIES
Vessel Name |  |  |  | TB.MITRA ANUGERAH 35 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI
Contract No. |  |  |  | 4710002973 |  |  |  | Master Name |  |  |  | AHMAD SHOKIB | [6 empty] | Start |  | Finish |  | High |  | Normal | Slow |  | Manu |  | Tow |  | A/H | S/B
Contract Period |  |  |  | 2020-09-01 | - | 30-Agst-20 |  | Number of Crew / Pax |  |  |  | 8 |  | / | 10 |  | Person |  | 0 |  | 0.029167 |  |  |  | 0.025 |  |  | 0.0041667 | [6 empty] | Dari PETREK ke widuri terminal
[19 empty] | 0.029167 |  | 0.13333 | [11 empty] | 0.10417 |  | Stby di SPM 02
WEATHER CONDITION | [18 empty] | 0.13333 |  | 0.20833 | [6 empty] | 0.075 | [6 empty] | Reposisi messengger line arus berubah
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  |  |  | 0.20833 |  | 0.3125 | [11 empty] | 0.10417 |  | Stby di SPM 02
Wind (Dir/speed) |  |  |  | E 9-11 Knot |  |  | NE 10-11 Knot |  |  | E 8 - 10 Knot |  |  |  | E 10- 12 Knot |  |  |  |  | 0.3125 |  | 0.36667 |  |  |  | 0.045833 | 0.0041667 |  | 0.0041667 | [6 empty] | SPM 02 ke PROSES Widuri terminal antar barang
Sea (Wave Height) |  |  |  | Slight / 0,6 M - 1,1 M |  |  | Slight / 0,7 M - 1,2 M |  |  | Calm / 0,5 M - 1 M |  |  |  | Calm / 1 M - 1,5 m |  |  |  |  | 0.36667 |  | 0.41667 |  |  |  | 0.041667 | 0.0041667 |  | 0.0041667 | [6 empty] | Slesai drop barang SPM 01
Visibility | [18 empty] | 0.41667 |  | 0.4875 | [6 empty] | 0.070833 | [6 empty] | SPM 01 perbaiki hose yang menumpuk /menyilang
[19 empty] | 0.4875 |  | 0.66667 | [11 empty] | 0.17917 |  | Stby di SPM 02
HSSE | [18 empty] | 0.66667 |  | 0.73333 | [6 empty] | 0.066667 | [6 empty] | Tarik putar SPM 01 arus berubah dan luruskan hose
A. | HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  |  |  | 0.73333 |  | 0.8125 | [11 empty] | 0.079167 |  | Stby di SPM 02
1 | O & I Card Submission (e.g. TUNTAS, STOP, etc.) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0.8125 |  | 0.88333 | [6 empty] | 0.070833 | [6 empty] | Reposisi messengger line arus berubah
2 | Ijin Kerja / PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0.88333 |  | 1899-12-31 | [11 empty] | 0.11667 |  | Stby di SPM 02
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify: | [5 empty] | ) | 0 |  |  | 0 |  |  | 0 |  |  |  | TOTAL |  |  |  | 0 |  | 0.1125 | 0.0083333 |  | 0.29583 |  | 0 |  | 0 | 0.58333
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE | [5 empty] | Opening (ROB from Previous Day) |  |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  |  | Transferred |  |  | Closing |  |  | Remarks
High Speed (High) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL | [5 empty] | 13642 |  |  | Ltrs | 1082 |  | Ltrs | 0 |  |  | Ltrs | 0 |  | Ltrs | 12560 |  | Ltrs
Normal Speed (Normal) | [5 empty] | 2:42 |  | 120 |  | Ltrs | 324 |  | Ltrs |  | FRESH WATER | [5 empty] | 43000 |  |  | Ltrs | 2000 |  | Ltrs | 0 |  |  | Ltrs | 0 |  | Ltrs | 41000 |  | Ltrs
Slow speed (Slow) | [5 empty] | 0:12 |  | 89 |  | Ltrs | 17.8 |  | Ltrs |  | DRILL WATER | [5 empty] | 0 |  |  | Ltrs |  |  |  | 0 |  |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs
Maneuvering (Manu) - Including DP | [5 empty] | 7:06 |  | 89 |  | Ltrs | 631.9 |  | Ltrs |  | BARITE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Towing (Tow) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Anchor Handling (A/H) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | CEMENT BLENDED | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Standby (S/B) | [5 empty] | 14:00 |  | 8 |  | Ltrs | 112 |  | Ltrs |  | CEMENT G | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | BRINE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | OTHERS |  | (_________________) |  |  |  | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 1085.7 |  | Ltrs
Prepared by, | [36 empty] | Acknowledged by,
Name: |  | ANDRI SUMARDI | [12 empty] | Name: |  | AKHMAD SHOKIB | [19 empty] | Name:
Title: CHIEF ENGINEER | [14 empty] | Title: MASTER | [21 empty] | Title: PHE Representative
VDR Rev. 4 - Dec. 2019
Attachment 1 | [27 empty] | Attachment 2
Vessel Daily Engine Parameter Log | [27 empty] | Crew & Passenger List
Date |  |  |  | 2020-08-03 | [23 empty] | Date |  |  |  | 2020-08-03
Vessel Name |  |  |  | TB.MITRA ANUGERAH 35 | [23 empty] | Vessel Name |  |  |  | TB.MITRA ANUGERAH 35
| PERHATIAN! 1. Laporan ini wajib dilengkapi setiap hari, pada saat kapal bergerak dengan kecepatan operasi normal. 2. Laporan ini tidak perlu di cetak. 3. Jika terdapat data yang NAIK atau TURUN secara signifikan dari data normal harian, wajib dianalisa, telusuri dan laporkan ke Port Engineer masing-masing perusahaan/kontraktor. | [26 empty] | PERHATIAN! 1. Laporan ini wajib dilengkapi setiap hari. 2. Laporan ini tidak perlu di cetak. 3. Nama yang dimasukkan dalam Passenger List hanya untuk penumpang yang bermalam atau yang tinggal selama 24 jam di atas kapal.
No | Observed Data / Indicators | [5 empty] | Unit | Main Engines Data | [9 empty] | Aux. Engines Data | [9 empty] | No | Vessel Crew List | [8 empty] | Passenger List
[8 empty] | Ref. Value |  | Port |  | Stbd |  | Center |  | Other ________ |  | Ref. Value |  | Port |  | Stbd |  | Other _______ |  |  |  |  | Name |  |  |  |  | Ranks |  |  |  | Name | Company
1 | Engine Revolution | [5 empty] | RPM | NA |  | 0 |  | 0 |  | 0 |  | 0 |  | NA |  | 0 |  | 0 | [5 empty] | 1 | AHMAD SHOKIB |  |  |  |  | MASTER CUTI
2 | Oil Pressure | [5 empty] | Bar | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 2 | A. WIRPIAN IRVAN |  |  |  |  | C/O
3 | Coolant Temperature Inlet | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 3 | ADE EKA SETYAWAN |  |  |  |  | 2/O
4 | Coolant Temperature Outlet | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 4 | ABDUL AFIF M |  |  |  |  | 3/O
5 | Exhaust Temperature Cyl. #1 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 5 | ANDRI SUMARDI |  |  |  |  | C/E
6 | Exhaust Temperature Cyl. #2 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 6 | MUSTOPA |  |  |  |  | 2/E
7 | Exhaust Temperature Cyl. #3 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 7 | BASTIAN BASRI |  |  |  |  | 3/E
8 | Exhaust Temperature Cyl. #4 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 8 | ABDUL KARIM DAENG |  |  |  |  | A/B
9 | Exhaust Temperature Cyl. #5 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 9 | HASDI |  |  |  |  | A/B |  | CUTI
10 | Exhaust Temperature Cyl. #6 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 10 | ASHAR |  |  |  |  | OILER
11 | Exhaust Temperature Cyl. #7 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 11
12 | Exhaust Temperature Cyl. #8 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 12
13 | Exhaust Temperature Cyl. #9 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 13
14 | Exhaust Temperature Cyl. #10 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 14
15 | Exhaust Temperature Cyl. #11 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 15
16 | Exhaust Temperature Cyl. #12 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 16
17 | Exhaust Temperature Cyl. #13 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 17
18 | Exhaust Temperature Cyl. #14 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 18
19 | Exhaust Temperature Cyl. #15 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 19
20 | Exhaust Temperature Cyl. #16 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 20
21 | Gear Box Oil Temperature | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 21
22 | Gear Box Oil Pressure | [5 empty] | Bar | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 04 AGUSTUS 2020 (2)
PT PERTAMINA HULU ENERGI | [17 empty] | VESSEL DAILY REPORT
MARINE & AVIATION TEAM | [17 empty] | (Every Midnight)
GENERAL INFORMATION | [18 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 2020-08-04 |  |  |  | Location (Midnight) |  |  |  | SPM 01, WIDURI TERMINAL | [6 empty] | TIME |  |  |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [11 empty] | ACTIVITIES
Vessel Name |  |  |  | TB.MITRA ANUGERAH 35 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI
Contract No. |  |  |  | 4710002973 |  |  |  | Master Name |  |  |  | AHMAD SHOKIB | [6 empty] | Start |  | Finish |  | High |  | Normal | Slow |  | Manu |  | Tow |  | A/H | S/B
Contract Period |  |  |  | 2020-09-01 | - | 30-Agst-20 |  | Number of Crew / Pax |  |  |  | 8 |  | / | 10 |  | Person |  | 0 |  | 0.05 | [11 empty] | 0.05 |  | Stby di SPM 01
[19 empty] | 0.05 |  | 0.12917 | [6 empty] | 0.079167 | [6 empty] | Reposisi massenger line di SPM 01
WEATHER CONDITION | [18 empty] | 0.12917 |  | 0.29167 | [11 empty] | 0.1625 |  | Stby di SPM 01
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  |  |  | 0.29167 |  | 0.35417 | [6 empty] | 0.0625 | [6 empty] | Tarik putar SPM 01 luruskan hose
Wind (Dir/speed) |  |  |  | E 9-11 Knot |  |  | NE 10-11 Knot |  |  | E 8 - 10 Knot |  |  |  | E 10- 12 Knot |  |  |  |  | 0.35417 |  | 0.72917 | [11 empty] | 0.375 |  | Stby di SPM 01
Sea (Wave Height) |  |  |  | Slight / 0,6 M - 1,1 M |  |  | Slight / 0,7 M - 1,2 M |  |  | Calm / 0,5 M - 1 M |  |  |  | Calm / 1 M - 1,5 m |  |  |  |  | 0.72917 |  | 0.825 | [6 empty] | 0.095833 | [6 empty] | Reposisi massenger line di SPM 01 arus berubah
Visibility | [18 empty] | 0.825 |  | 0.85417 | [11 empty] | 0.029167 |  | Stby di SPM 01
[19 empty] | 0.85417 |  | 0.90417 | [6 empty] | 0.05 | [6 empty] | Tarik putar SPM 01 arus berubah
HSSE | [18 empty] | 0.90417 |  | 1899-12-31 | [11 empty] | 0.095833 |  | Stby di SPM 01
A. | HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly
1 | O & I Card Submission (e.g. TUNTAS, STOP, etc.) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Ijin Kerja / PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify: | [5 empty] | ) | 0 |  |  | 0 |  |  | 0 |  |  |  | TOTAL |  |  |  | 0 |  | 0 | 0 |  | 0.2875 |  | 0 |  | 0 | 0.7125
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE | [5 empty] | Opening (ROB from Previous Day) |  |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  |  | Transferred |  |  | Closing |  |  | Remarks
High Speed (High) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL | [5 empty] | 12560 |  |  | Ltrs | 748 |  | Ltrs | 0 |  |  | Ltrs | 0 |  | Ltrs | 11812 |  | Ltrs
Normal Speed (Normal) | [5 empty] | 0:00 |  | 120 |  | Ltrs | 0 |  | Ltrs |  | FRESH WATER | [5 empty] | 41000 |  |  | Ltrs | 2000 |  | Ltrs | 0 |  |  | Ltrs | 0 |  | Ltrs | 39000 |  | Ltrs
Slow speed (Slow) | [5 empty] | 0:00 |  | 89 |  | Ltrs | 0 |  | Ltrs |  | DRILL WATER | [5 empty] | 0 |  |  | Ltrs |  |  |  | 0 |  |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs
Maneuvering (Manu) - Including DP | [5 empty] | 6:54 |  | 89 |  | Ltrs | 614.1 |  | Ltrs |  | BARITE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Towing (Tow) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Anchor Handling (A/H) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | CEMENT BLENDED | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Standby (S/B) | [5 empty] | 17:06 |  | 8 |  | Ltrs | 136.8 |  | Ltrs |  | CEMENT G | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | BRINE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | OTHERS |  | (_________________) |  |  |  | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 750.9 |  | Ltrs
Prepared by, | [36 empty] | Acknowledged by,
Name: |  | ANDRI SUMARDI | [12 empty] | Name: |  | AKHMAD SHOKIB | [19 empty] | Name:
Title: CHIEF ENGINEER | [14 empty] | Title: MASTER | [21 empty] | Title: PHE Representative
VDR Rev. 4 - Dec. 2019
Attachment 1 | [27 empty] | Attachment 2
Vessel Daily Engine Parameter Log | [27 empty] | Crew & Passenger List
Date |  |  |  | 2020-08-04 | [23 empty] | Date |  |  |  | 2020-08-04
Vessel Name |  |  |  | TB.MITRA ANUGERAH 35 | [23 empty] | Vessel Name |  |  |  | TB.MITRA ANUGERAH 35
| PERHATIAN! 1. Laporan ini wajib dilengkapi setiap hari, pada saat kapal bergerak dengan kecepatan operasi normal. 2. Laporan ini tidak perlu di cetak. 3. Jika terdapat data yang NAIK atau TURUN secara signifikan dari data normal harian, wajib dianalisa, telusuri dan laporkan ke Port Engineer masing-masing perusahaan/kontraktor. | [26 empty] | PERHATIAN! 1. Laporan ini wajib dilengkapi setiap hari. 2. Laporan ini tidak perlu di cetak. 3. Nama yang dimasukkan dalam Passenger List hanya untuk penumpang yang bermalam atau yang tinggal selama 24 jam di atas kapal.
No | Observed Data / Indicators | [5 empty] | Unit | Main Engines Data | [9 empty] | Aux. Engines Data | [9 empty] | No | Vessel Crew List | [8 empty] | Passenger List
[8 empty] | Ref. Value |  | Port |  | Stbd |  | Center |  | Other ________ |  | Ref. Value |  | Port |  | Stbd |  | Other _______ |  |  |  |  | Name |  |  |  |  | Ranks |  |  |  | Name | Company
1 | Engine Revolution | [5 empty] | RPM | NA |  | 0 |  | 0 |  | 0 |  | 0 |  | NA |  | 0 |  | 0 | [5 empty] | 1 | AHMAD SHOKIB |  |  |  |  | MASTER CUTI
2 | Oil Pressure | [5 empty] | Bar | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 2 | A. WIRPIAN IRVAN |  |  |  |  | C/O
3 | Coolant Temperature Inlet | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 3 | ADE EKA SETYAWAN |  |  |  |  | 2/O
4 | Coolant Temperature Outlet | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 4 | ABDUL AFIF M |  |  |  |  | 3/O
5 | Exhaust Temperature Cyl. #1 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 5 | ANDRI SUMARDI |  |  |  |  | C/E
6 | Exhaust Temperature Cyl. #2 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 6 | MUSTOPA |  |  |  |  | 2/E
7 | Exhaust Temperature Cyl. #3 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 7 | BASTIAN BASRI |  |  |  |  | 3/E
8 | Exhaust Temperature Cyl. #4 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 8 | ABDUL KARIM DAENG |  |  |  |  | A/B
9 | Exhaust Temperature Cyl. #5 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 9 | HASDI |  |  |  |  | A/B |  | CUTI
10 | Exhaust Temperature Cyl. #6 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 10 | ASHAR |  |  |  |  | OILER
11 | Exhaust Temperature Cyl. #7 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 11
12 | Exhaust Temperature Cyl. #8 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 12
13 | Exhaust Temperature Cyl. #9 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 13
14 | Exhaust Temperature Cyl. #10 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 14
15 | Exhaust Temperature Cyl. #11 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 15
16 | Exhaust Temperature Cyl. #12 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 16
17 | Exhaust Temperature Cyl. #13 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 17
18 | Exhaust Temperature Cyl. #14 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 18
19 | Exhaust Temperature Cyl. #15 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 19
20 | Exhaust Temperature Cyl. #16 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 20
21 | Gear Box Oil Temperature | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 21
22 | Gear Box Oil Pressure | [5 empty] | Bar | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## 05 AGUSTUS 2020
PT PERTAMINA HULU ENERGI | [17 empty] | VESSEL DAILY REPORT
MARINE & AVIATION TEAM | [17 empty] | (Every Midnight)
GENERAL INFORMATION | [18 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 2020-08-05 |  |  |  | Location (Midnight) |  |  |  | SPM 01, WIDURI TERMINAL | [6 empty] | TIME |  |  |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [11 empty] | ACTIVITIES
Vessel Name |  |  |  | TB.MITRA ANUGERAH 35 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI
Contract No. |  |  |  | 4710002973 |  |  |  | Master Name |  |  |  | AHMAD SHOKIB | [6 empty] | Start |  | Finish |  | High |  | Normal | Slow |  | Manu |  | Tow |  | A/H | S/B
Contract Period |  |  |  | 2020-09-01 | - | 30-Agst-20 |  | Number of Crew / Pax |  |  |  | 8 |  | / | 10 |  | Person |  | 0 |  | 0.083333 | [11 empty] | 0.083333 |  | Stby di SPM 01
[19 empty] | 0.083333 |  | 0.18333 | [6 empty] | 0.1 | [6 empty] | Reposisi massenger line di S PM 01
WEATHER CONDITION | [18 empty] | 0.18333 |  | 0.29167 | [11 empty] | 0.10833 |  | Stby di SPM 01
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  |  |  | 0.29167 |  | 0.31667 | [6 empty] | 0.025 | [6 empty] | Stby di SPM 01 jke federal II
Wind (Dir/speed) |  |  |  | E 9-11 Knot |  |  | NE 10-11 Knot |  |  | E 8 - 10 Knot |  |  |  | E 10- 12 Knot |  |  |  |  | 0.31667 |  | 0.34167 |  |  |  | 0.016667 | 0.0041667 |  | 0.0041667 | [6 empty] | Federal II ke SPM 01 drop personil di SPM 01
Sea (Wave Height) |  |  |  | Slight / 0,6 M - 1,1 M |  |  | Slight / 0,7 M - 1,2 M |  |  | Calm / 0,5 M - 1 M |  |  |  | Calm / 1 M - 1,5 m |  |  |  |  | 0.34167 |  | 0.39583 | [11 empty] | 0.054167 |  | Stby di SPM 01
Visibility | [18 empty] | 0.39583 |  | 0.42083 |  |  |  | 0.016667 | 0.0041667 |  | 0.0041667 | [6 empty] | SPM 01 ke Federal II drop personil SBM
[19 empty] | 0.42083 |  | 0.44583 |  |  |  | 0.016667 | 0.0041667 |  | 0.0041667 | [6 empty] | Selesai drop personil balik ke SPM 10
HSSE | [18 empty] | 0.44583 |  | 0.55 | [11 empty] | 0.10417 |  | Stby di SPM 01
A. | HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  |  |  | 0.55 |  | 0.60417 | [6 empty] | 0.054167 | [6 empty] | Tarik putar SPM 01 arus berubah
1 | O & I Card Submission (e.g. TUNTAS, STOP, etc.) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0.60417 |  | 0.79167 | [11 empty] | 0.1875 |  | Stby di SPM 01
2 | Ijin Kerja / PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0.79167 |  | 0.87917 | [6 empty] | 0.0875 | [6 empty] | Reposisi massenger line di S PM 01
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0 |  |  |  | 0.87917 |  | 1899-12-31 | [11 empty] | 0.12083 |  | Stby di SPM 01
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify: | [5 empty] | ) | 0 |  |  | 0 |  |  | 0 |  |  |  | TOTAL |  |  |  | 0 |  | 0.05 | 0.0125 |  | 0.27917 |  | 0 |  | 0 | 0.65833
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE | [5 empty] | Opening (ROB from Previous Day) |  |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  |  | Transferred |  |  | Closing |  |  | Remarks
High Speed (High) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL | [5 empty] | 11812 |  |  | Ltrs | 890 |  | Ltrs | 0 |  |  | Ltrs | 0 |  | Ltrs | 10922 |  | Ltrs
Normal Speed (Normal) | [5 empty] | 1:12 |  | 120 |  | Ltrs | 144 |  | Ltrs |  | FRESH WATER | [5 empty] | 37000 |  |  | Ltrs | 2000 |  | Ltrs | 0 |  |  | Ltrs | 0 |  | Ltrs | 35000 |  | Ltrs
Slow speed (Slow) | [5 empty] | 0:18 |  | 89 |  | Ltrs | 26.7 |  | Ltrs |  | DRILL WATER | [5 empty] | 0 |  |  | Ltrs |  |  |  | 0 |  |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs
Maneuvering (Manu) - Including DP | [5 empty] | 6:42 |  | 89 |  | Ltrs | 596.3 |  | Ltrs |  | BARITE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Towing (Tow) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Anchor Handling (A/H) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | CEMENT BLENDED | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Standby (S/B) | [5 empty] | 15:48 |  | 8 |  | Ltrs | 126.4 |  | Ltrs |  | CEMENT G | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | BRINE | [5 empty] | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | OTHERS |  | (_________________) |  |  |  | 0 |  |  | cuft |  |  |  | 0 |  |  | cuft | 0 |  | cuft | 0 |  | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 893.4 |  | Ltrs
Prepared by, | [36 empty] | Acknowledged by,
Name: |  | ANDRI SUMARDI | [12 empty] | Name: |  | AKHMAD SHOKIB | [19 empty] | Name:
Title: CHIEF ENGINEER | [14 empty] | Title: MASTER | [21 empty] | Title: PHE Representative
VDR Rev. 4 - Dec. 2019
Attachment 1 | [27 empty] | Attachment 2
Vessel Daily Engine Parameter Log | [27 empty] | Crew & Passenger List
Date |  |  |  | 2020-08-05 | [23 empty] | Date |  |  |  | 2020-08-05
Vessel Name |  |  |  | TB.MITRA ANUGERAH 35 | [23 empty] | Vessel Name |  |  |  | TB.MITRA ANUGERAH 35
| PERHATIAN! 1. Laporan ini wajib dilengkapi setiap hari, pada saat kapal bergerak dengan kecepatan operasi normal. 2. Laporan ini tidak perlu di cetak. 3. Jika terdapat data yang NAIK atau TURUN secara signifikan dari data normal harian, wajib dianalisa, telusuri dan laporkan ke Port Engineer masing-masing perusahaan/kontraktor. | [26 empty] | PERHATIAN! 1. Laporan ini wajib dilengkapi setiap hari. 2. Laporan ini tidak perlu di cetak. 3. Nama yang dimasukkan dalam Passenger List hanya untuk penumpang yang bermalam atau yang tinggal selama 24 jam di atas kapal.
No | Observed Data / Indicators | [5 empty] | Unit | Main Engines Data | [9 empty] | Aux. Engines Data | [9 empty] | No | Vessel Crew List | [8 empty] | Passenger List
[8 empty] | Ref. Value |  | Port |  | Stbd |  | Center |  | Other ________ |  | Ref. Value |  | Port |  | Stbd |  | Other _______ |  |  |  |  | Name |  |  |  |  | Ranks |  |  |  | Name | Company
1 | Engine Revolution | [5 empty] | RPM | NA |  | 0 |  | 0 |  | 0 |  | 0 |  | NA |  | 0 |  | 0 | [5 empty] | 1 | AHMAD SHOKIB |  |  |  |  | MASTER CUTI
2 | Oil Pressure | [5 empty] | Bar | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 2 | A. WIRPIAN IRVAN |  |  |  |  | C/O
3 | Coolant Temperature Inlet | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 3 | ADE EKA SETYAWAN |  |  |  |  | 2/O
4 | Coolant Temperature Outlet | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 4 | ABDUL AFIF M |  |  |  |  | 3/O
5 | Exhaust Temperature Cyl. #1 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 5 | ANDRI SUMARDI |  |  |  |  | C/E
6 | Exhaust Temperature Cyl. #2 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 6 | MUSTOPA |  |  |  |  | 2/E
7 | Exhaust Temperature Cyl. #3 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 7 | BASTIAN BASRI |  |  |  |  | 3/E
8 | Exhaust Temperature Cyl. #4 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 8 | ABDUL KARIM DAENG |  |  |  |  | A/B
9 | Exhaust Temperature Cyl. #5 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 9 | HASDI |  |  |  |  | A/B |  | CUTI
10 | Exhaust Temperature Cyl. #6 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 10 | ASHAR |  |  |  |  | OILER
11 | Exhaust Temperature Cyl. #7 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 11
12 | Exhaust Temperature Cyl. #8 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 12
13 | Exhaust Temperature Cyl. #9 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 13
14 | Exhaust Temperature Cyl. #10 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 14
15 | Exhaust Temperature Cyl. #11 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 15
16 | Exhaust Temperature Cyl. #12 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 16
17 | Exhaust Temperature Cyl. #13 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 17
18 | Exhaust Temperature Cyl. #14 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 18
19 | Exhaust Temperature Cyl. #15 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 19
20 | Exhaust Temperature Cyl. #16 | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 20
21 | Gear Box Oil Temperature | [5 empty] | °C | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 21
22 | Gear Box Oil Pressure | [5 empty] | Bar | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [5 empty] | 22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40