## 05-19
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 05 October, 2019 |  |  |  | Location (Midnight) |  |  |  | Cinta Terminal ( SPM export ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT Mitra Anugerah 32 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI/SAMUDERA INDO
Contract No. | [7 empty] | Master Name |  |  |  | ANDI MUHAMMAD AMRI |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 9 |  | / | 0 | Person | 0 | 0.016667 | [8 empty] | 0.016667 | MA 32 stand by di sbm eksport
[17 empty] | 0.016667 | 0.15833 |  |  | 0.13125 | 0.0069444 |  | 0.0034722 |  |  |  | tahan posisi kapal menjauh dari hose,arus berubah
WEATHER CONDITION | [16 empty] | 0.15833 | 0.2125 | [8 empty] | 0.054167 | MA 32 stand by di sbm eksport
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.2125 | 0.2875 |  |  | 0.063194 | 0.0069444 |  | 0.0048611 |  |  |  | tarik putar SBM export,angin dan arus berlawanan.
Wind (Dir/speed) |  |  |  | E 4-6 Knot |  |  | E 07-10 Knot |  |  | E 10-14 Knot |  |  |  | E 8- 10 Knot |  |  | 0.2875 | 0.33333 | [8 empty] | 0.045833 | MA 32 standby di SBM export.
Sea (Wave Height) |  |  |  | Slight / 0.0-0.6 m |  |  | Moderate / 0.6-1.0 m |  |  | Moderate / 1.0-1.5 m |  |  |  | Slight / 0.0-0.6 m |  |  | 0.33333 | 0.35 |  |  | 0.0097222 | 0.0041667 |  | 0.0027778 |  |  |  | MA 32 gantikan posisi megawati 5
Visibility | [16 empty] | 0.35 | 0.37917 | [8 empty] | 0.029167 | standby di SBM export.
[17 empty] | 0.37917 | 0.43333 |  |  | 0.04375 | 0.0069444 |  | 0.0034722 |  |  |  | tarik putar posisi mooring line,luruskan hose,sejajarkan dengan arus.
HSSE | [16 empty] | 0.43333 | 0.50417 | [8 empty] | 0.070833 | MA 32 standby di SBM export.
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.50417 | 0.62083 |  |  | 0.10625 | 0.00625 |  | 0.0041667 |  |  |  | tahan posisi kapal menjauh dari hose.
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.62083 | 0.72917 | [8 empty] | 0.10833 | MA 32 standby di SBM expor.
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.72917 | 0.82917 |  |  | 0.086806 | 0.0097222 |  | 0.0034722 |  |  |  | tarik putar SBM export arus mulai berubah.
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.82917 | 0.87917 | [8 empty] | 0.05 | MA 32 standby di SBM export.
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.87917 | 0.95417 |  |  | 0.065972 | 0.0055556 |  | 0.0034722 |  |  |  | tahan posisi kapal menjauh dari SBM expor,arus dari buritan kapal.
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.95417 | 1899-12-31 | [8 empty] | 0.045833 | MA 32 standby di SBM export.
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.50694 | 0.046528 |  | 0.025694 | 0 |  | 0.42083
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 16216 |  | Ltrs | 2028 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 14188 | Ltrs
Economical Speed (Eco) | [5 empty] | 12:10 |  | 120 |  | Ltrs | 1460 |  | Ltrs |  | FRESH WATER |  |  | 27 |  | Ltrs | 3 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 24 | Ltrs
Slow speed (Slow) | [5 empty] | 1:07 |  | 89 |  | Ltrs | 99.3833 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 0:37 |  | 89 |  | Ltrs | 54.8833 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 10:06 |  | 40 |  | Ltrs | 404 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 2018.2667 |  | Ltrs
Prepared by, | [9 empty] | l;;; | [20 empty] | Acknowledged by,
Name : | HERMAN | Suwartono | [12 empty] | Name : | ANDI MUHAMMAD AMRI | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative