## 31-19
PT. PERTAMINA HULU ENERGI OFFSHORE SOUTH EAST SUMATERA
Lifting and Marine Operation Dept.
GENERAL INFORMATION | [16 empty] | DETAIL OF DAILY OPERATIONAL ACTIVITIES
Date |  |  |  | 31 October, 2019 |  |  |  | Location (Midnight) |  |  |  | Cinta Terminal ( SPM export ) |  |  |  |  | TIME |  | Operating Mode Duration (hh:mm) - Except Maintenance & Downtime | [8 empty] | ACTIVITIES
Vessel Name |  |  |  | LHT Mitra Anugerah 32 |  |  |  | Owner/Operator |  |  |  | PT.EKA NURI/SAMUDERA INDO
Contract No. | [7 empty] | Master Name |  |  |  | ANDI MUHAMMAD AMRI |  |  |  |  | Start | Finish | Full |  | Eco | Slow |  | Manu | T/AH |  | S/B
Contract Period |  |  |  |  | - |  |  | Number of Crew / Pax |  |  |  | 8 |  | / | 10 | Person | 0 | 0.1 |  |  | 0.086111 | 0.010417 |  | 0.0034722 |  |  |  | tarik putar SBM export,arus berubah.
[17 empty] | 0.1 | 0.12917 | [8 empty] | 0.029167 | standby di SBM export.
WEATHER CONDITION | [16 empty] | 0.12917 | 0.27083 |  |  | 0.12361 | 0.013889 |  | 0.0041667 |  |  |  | tahan posisi kapal,angin mulai berubah.
Weather/Time |  |  |  | 0000 - 0600 hrs |  |  | 0600 - 1200 hrs |  |  | 1200 - 1800 hrs |  |  |  | 1800 - 2400 hrs |  |  | 0.27083 | 0.36667 | [8 empty] | 0.095833 | standby di SBM export.
Wind (Dir/speed) |  |  |  | E 00-06 Knot |  |  | E 0.0-07 Knot |  |  | E 0.2-06 Knot |  |  |  | E 0.3-0.7 Knot |  |  | 0.36667 | 0.55417 |  |  | 0.12569 | 0.055556 |  | 0.00625 |  |  |  | tarik mooring line,dan perbaiki hose yang melingkar,arus mutar.
Sea (Wave Height) |  |  |  | Calm sea / 0.0-0.6 m |  |  | Calm sea / 0.0/0,5 m |  |  | Calm sea / 1.0-1.5 m |  |  |  | Calm sea/ 0.0-0.6 m |  |  | 0.55417 | 0.6375 |  |  | 0.068056 | 0.010417 |  | 0.0048611 |  |  |  | lanjut suport lifting MT.GEDE.
Visibility | [16 empty] | 0.6375 | 0.65 |  |  | 0.00625 | 0.0041667 |  | 0.0020833 |  |  |  | stndby di sebelah kanan MT.GEDE,tunggu agen turun dari tanker.
[17 empty] | 0.65 | 0.68333 |  |  | 0.027778 | 0.0034722 |  | 0.0020833 |  |  |  | pic up agen - ke 114,drop agen.
HSSE | [16 empty] | 0.68333 | 0.70417 | [8 empty] | 0.020833 | standby di lambung kiri 114.
| HSSE STATISTICS (INPUT) | [7 empty] | Previous |  |  | Today |  |  | Monthly |  | 0.70417 | 0.72569 |  |  | 0.014583 | 0.0034722 |  | 0.0034722 |  |  |  | MA 32 pindah posisi dari lambung kiri 114 ke lambung kanan 114.
1 | Observation Card Submission | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.72569 | 0.75417 | [8 empty] | 0.028472 | standby di lambung kanan 114.
2 | PTW issued | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.75417 | 0.8375 |  |  | 0.041667 | 0.020833 |  | 0.020833 |  |  |  | tahan posisi kapal,menjauh dari benturan lambung 114,arus berubah.
3 | Tool Box Talk | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.8375 | 0.87917 | [8 empty] | 0.041667 | standby di lambung kanan 114.
4 | HSSE Induction (New Comer & Visitor) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.87917 | 0.925 |  |  | 0.038889 | 0.0041667 |  | 0.0027778 |  |  |  | 114 - tanker,drop makanan.
5 | Emergency Drills | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.925 | 0.9625 |  |  | 0.030556 | 0.0034722 |  | 0.0034722 |  |  |  | lanjut ikat di belakang ina p2,ombak dan angin dari haluan.
6 | Internal Audit (by Office) | [7 empty] | 0 |  |  | 0 |  |  | 0 |  | 0.9625 | 1899-12-31 |  |  | 0.018056 | 0.013889 |  | 0.0055556 |  |  |  | tahan posisi kapal,ombak dan angin dari haluan kapal.
B. | HSSE STATISTICS (OUTPUT) | [7 empty] | Previous |  |  | Today |  |  | Cumulative
1 | Safe Manhours Worked (Vessel Crew) | [7 empty] | 0 |  |  | 0 |  |  | 0
2 | Number of Accident/Incident | [7 empty] | 0 |  |  | 0 |  |  | 0
| - | Lost Time Injury | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | First Aid Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Medical Treatment Case | [6 empty] | 0 |  |  | 0 |  |  | 0
| - | Others (specify:__________________) | [6 empty] | 0 |  |  | 0 |  |  | 0 |  | TOTAL |  | 0 |  | 0.58125 | 0.14375 |  | 0.059028 | 0 |  | 0.21597
SUMMARY OF DAILY OPERATING DATA | [14 empty] | SUMMARY OF DAILY FUEL, WATER and CARGOES REMAINING ONBOARD
Operating Mode | [5 empty] | Total Time (hh:mm) |  | Contractual Fuel Cons. Remuneration Figure |  |  | Daily Fuel Cons. by Remuneration Figure |  |  |  | TYPE |  |  | Opening (ROB from Previous Day) |  |  | Consumption (Based on Actual Sounding) |  |  | Received |  |  | Transferred |  |  | Closing |  | Remarks
Full Speed (Full) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | FUEL OIL |  |  | 11138 |  | Ltrs | 2320 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 8818 | Ltrs | DT-117 cm=1996 lt
Economical Speed (Eco) | [5 empty] | 13:57 |  | 120 |  | Ltrs | 1674 |  | Ltrs |  | FRESH WATER |  |  | 14 |  | Ltrs | 3 |  | Ltrs | 0 |  | Ltrs | 0 |  | Ltrs | 11 | Ltrs
Slow speed (Slow) | [5 empty] | 3:27 |  | 89 |  | Ltrs | 307.05 |  | Ltrs |  | DRILL WATER |  |  | 0 |  | Ltrs |  |  |  | 0 |  | Ltrs | 0 |  | Ltrs | 0 | Ltrs
Maneuvering (Manu) | [5 empty] | 1:25 |  | 89 |  | Ltrs | 126.0833 |  | Ltrs |  | BARITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Towing/Anchor Handling (T/AH) | [5 empty] | 0:00 |  | 0 |  | Ltrs | 0 |  | Ltrs |  | BENTONITE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Standby (S/B) | [5 empty] | 5:11 |  | 40 |  | Ltrs | 207.3333 |  | Ltrs |  | CEMENT BLENDED |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Maintenance | [5 empty] | 0:00 | [8 empty] | CEMENT G |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
Down Time | [5 empty] | 0:00 | [8 empty] | BRINE |  |  | 0 |  | cuft |  |  |  | 0 |  | cuft | 0 |  | cuft | 0 | cuft
|  |  | Total Daily |  |  | 1899-12-31 |  |  |  |  | 2314.4667 |  | Ltrs
Prepared by, | [30 empty] | Acknowledged by,
Name : | HERMAN | Suwartono | [12 empty] | Name : | ANDI MUHAMMAD AMRI | [5 empty] | Name : | [8 empty] | Name :
Title : CHIEF ENGINEER | [14 empty] | Title : MASTER | [6 empty] | Title : SECURITY | [8 empty] | Title : PHE OSES Representative